## Index
Nessovo HumanOS Work Intelligence — Project Plan Workbook
Initial research-backed planning workbook for task-aware work observability, capability verification, coaching, and HumanOS self-improvement.
Workbook section | Purpose | Primary users | Status | Decision summary
Executive Charter | Product purpose, principles, scope, non-goals, and strategic thesis | CEO/CTO/Product | Draft | Recommendation | Proceed as a controlled HumanOS module, starting with AI-assisted software-development teams.
Market Landscape | Commercial and category-level competitors / references | Product/Strategy | Draft | Strategic position | Not employee surveillance as the headline. Position as task assurance, capability development, AI-work governance and organisational learning.
GitHub OSS Scan | Open-source and source-available references to inspect or learn from | Engineering/Architecture | Draft | Architecture principle | Java/Spring Boot for core domain microservices; Python for AI/evaluation pipelines; native desktop agents for OS telemetry; event streaming for evidence flow.
Gap Matrix | Capability comparison between market categories and Nessovo target | Product/Strategy | Draft | Delivery model | 13 stages total: Stage 0 governance/charter plus 12 build-and-rollout stages.
Delivery Stages | Stage-by-stage plan with duration and acceptance criteria | Program/Product/Engineering | Draft | Critical condition | Human review, employee access, secure-field blocking and evidence-based confidence are mandatory from day one.
Microservices Map | Proposed HumanOS microservice boundaries and runtime choices | Architecture/Backend | Draft
MVP Backlog | Initial product backlog for the internal pilot | Product/Engineering | Draft
Event Data Model | Core event/entity model and evidence graph | Backend/Data/AI | Draft
AI Capability System | Capability graph, role contracts, AI evaluators, training loop | AI/Product/L&D | Draft
Governance | Privacy, legal, security, employee-review controls | Legal/Security/HR | Draft
Risk Register | Major technical, legal, market and trust risks with mitigations | Leadership/Governance | Draft
KPI Dashboard | Summary metrics for scope, duration, risk and readiness | Leadership | Draft
Source Register | Source URLs used for initial market, OSS and technical research | All | Draft

## Executive Charter
Executive Charter
Definition of the Nessovo HumanOS Work Intelligence module.
Area | Content
Product name | HumanOS Work Intelligence
Strategic thesis | A HumanOS operating layer that understands how people and AI jointly execute work, verifies task outcomes, measures demonstrated capability, coaches employees, informs managers, and improves organisational skills.
Core modules | Work Observer; Task Assurance; Capability Graph; Growth Coach; Skill Forge; Governance & Review; Reporting & Analytics.
Primary starting vertical | AI-assisted software development, because objective evidence exists through Git diffs, tests, builds, PRs, agent traces, terminal commands and code reviews.
Expansion path | After software-development validation: customer support, finance operations, recruitment, design, sales operations, legal operations, compliance and general back-office workflows.
Core differentiation | Most market tools collect activity or mine processes. Nessovo must connect activity to assigned tasks, acceptance criteria, capability claims, training, AI-agent provenance and self-improving skills.
Non-goal | Do not build a crude bossware dashboard or a hidden surveillance tool. Raw capture is the evidence substrate, not the product message.
Governance principle | No automatic consequential employment decisions. AI produces findings and recommendations; authorised humans review decisions with evidence and employee response.
Technology principle | Use event-driven microservices, policy-as-code, evidence graphs, immutable audit logs, on-device redaction, and modular AI evaluators.
Stack baseline | Java 21+/Spring Boot/Spring Cloud for core services; Python/FastAPI/Celery or Temporal workers for AI; Kafka-compatible event bus; PostgreSQL; object storage; vector DB; graph capability/evidence store; OpenTelemetry.

## Market Landscape
Market Landscape
Commercial and category references: what exists, what to learn, and where Nessovo differentiates.
Reference | Category | Relevant capabilities | Lesson for Nessovo | Gap vs Nessovo target | Build/Buy/Watch | Priority | Source URL
Teramind | Employee monitoring / insider risk | Live view, historical playback, screenshots, keystrokes, app/web activity, alerts, DLP-style monitoring. | Raw monitoring and investigation workflows are commercially mature. | Does not deeply verify task acceptance criteria, capability claims, role readiness, AI-agent provenance or training outcomes. | Watch / benchmark | High | https://www.teramind.co/solutions/employee-monitoring/
ActivTrak AI Insights | Workforce analytics / AI usage | AI tool adoption, productivity impact, workforce analytics, enablement insight. | AI usage measurement is becoming a management category. | Does not reconstruct task execution or validate technical work quality. | Watch / benchmark | High | https://support.activtrak.com/hc/en-us/articles/50125731483675-AI-Insights-Add-on
UiPath Task Capture / Task Mining | Task mining / automation discovery | Screenshots per click/keyboard action, UI element capture, process documentation and automation skeletons. | Click + screenshot + UI element capture is a proven workflow-mining pattern. | Built for process discovery and automation, not continuous role capability verification or employee growth coaching. | Learn from | High | https://docs.uipath.com/task-capture/standalone/2021.10/user-guide/capture-settings
ABBYY Timeline Task Mining | Task mining / process intelligence | Screen snapshots, buttons clicked, text entered, task definitions, analysis modules. | Associating user actions to task definitions is market-validated. | Focuses on task/process mining, not full work assurance and capability development. | Learn from | High | https://help.abbyy.com/en-us/timeline/6/user_guide/task-mining
Microsoft Power Automate Recorder / AI Recorder | Desktop automation recording | Mouse/keyboard capture, UI elements, OCR/image-based capture, converts demonstrations to flows. | Record-and-convert-to-procedure is a useful pattern for Skill Forge. | Automation creation, not work monitoring, capability verification or self-improving HR intelligence. | Watch / integrate ideas | Medium | https://learn.microsoft.com/en-us/power-automate/desktop-flows/create-flow-using-ai-recorder
Soroco Scout | Work graph / process intelligence | Team-machine interaction analysis, process variants, workarounds, effort leakage, automation opportunity discovery. | Work graph framing aligns with Nessovo evidence graph. | Generally aggregate/team/process oriented rather than individual task assurance and training. | Watch | Medium | https://soroco.com/
Workfellow | Process intelligence / task mining | Process/task mining, workflow analysis, automation opportunity analysis. | Confirms demand for work-pattern visibility and process-improvement intelligence. | Less focused on exact employee-device evidence and HumanOS capability graph. | Watch | Medium | https://www.workfellow.ai/
Codex Hooks | AI agent lifecycle extensibility | UserPromptSubmit, PreToolUse, PostToolUse, Stop, SessionStart and other deterministic hooks for analytics, policy and validation. | Instrument AI agents through official lifecycle hooks rather than only screen capture. | Nessovo must generalise this across Codex, Claude Code, Cursor, terminal and IDEs. | Integrate | High | https://developers.openai.com/codex/hooks
OpenAI Record & Replay | Workflow demonstration to reusable skill | Demonstrate a workflow once and convert it into a reusable skill. | Excellent mental model for Skill Forge and role-specific workflow training. | Not a full monitoring/capability platform; initial availability excludes UK/EEA/Switzerland. | Learn from | Medium | https://developers.openai.com/codex/record-and-replay
OpenTelemetry GenAI | AI observability standardisation | Common semantic conventions for GenAI traces, metrics and logs. | Use OTel conventions for AI-agent spans to avoid vendor lock-in. | Needs Nessovo-specific domain ontology for task/capability/evidence semantics. | Adopt | High | https://opentelemetry.io/docs/concepts/semantic-conventions/

## GitHub OSS Scan
GitHub / OSS Scan
Open-source and source-available systems that can inform architecture, capture, observability, and AI memory.
Repository | Category | Relevance | Useful patterns | Limitations / risk | Licence note | Adopt stance | Priority | Source URL
screenpipe/screenpipe | Local screen/audio/AI memory | Closest OSS/source-available reference for desktop activity memory. | Event-driven screen capture, accessibility tree, OCR fallback, local-first search, AI pipes. | Source-available/commercial licence; not a task assurance/capability platform. | Commercial use requires licence per repo README. | Study / license / selectively integrate | High | https://github.com/screenpipe/screenpipe
ActivityWatch/activitywatch | Time/activity tracking | Mature privacy-first active window/browser/AFK tracking architecture. | Watcher model, local server, extensibility, browser watchers. | Low fidelity; no exact text/screen intelligence or task correctness. | Open source; check MPL-2.0 implications. | Use ideas / possible integration | High | https://github.com/ActivityWatch/activitywatch
OpenAdaptAI/openadapt-desktop | Workflow capture and replay | Strong reference for GUI workflow teaching/recording and governed replay. | Record -> compile -> certify -> replay -> repair/teach pattern. | Experimental desktop product; not production validated end to end. | MIT in desktop repo. | Study / prototype ideas | High | https://github.com/OpenAdaptAI/openadapt-desktop
thedotmack/claude-mem | AI memory for Claude Code | Good lifecycle-hook memory pattern for agent work sessions. | Hooks, local worker, SQLite/FTS5, summaries, real-time memory viewer. | Claude-centric; not OS-level observation. | Apache-2.0 per repo metadata. | Study / adapt pattern | High | https://github.com/thedotmack/claude-mem
rebelytics/one-skill-to-rule-them-all | Skill improvement methodology | Strong model for Skill Forge: observe corrections, propose improvements, retain human review. | Observation log, issue/improvement/principle format, review cycle. | Methodology only, not a recorder or platform. | CC BY 4.0 per repo README. | Adapt methodology | High | https://github.com/rebelytics/one-skill-to-rule-them-all
wakatime/wakatime-cli | Developer time telemetry | Reference for editor/plugin-based developer activity instrumentation. | CLI ingestion, editor plugin ecosystem, developer activity heartbeat model. | Developer-tool focused; not universal desktop/task assurance. | BSD-style? verify before use. | Study / optional connector | Medium | https://github.com/wakatime/wakatime-cli
open-telemetry/semantic-conventions-genai | GenAI observability standards | Reference for standardising agent traces and tool calls. | GenAI spans, metrics, events, MCP/provider conventions. | Does not define work/capability/task ontologies. | Apache-2.0. | Adopt conventions | High | https://github.com/open-telemetry/semantic-conventions-genai
temporalio/sdk-java | Durable workflow orchestration | Useful for long-running review/coaching/skill-approval workflows in Java. | Durable execution, workflows, activities, retries. | Adds operational complexity; should not replace domain services. | Apache-2.0. | Consider | Medium | https://github.com/temporalio/sdk-java
temporalio/sdk-python | Durable workflow orchestration | Useful for Python AI pipelines requiring retries and workflow state. | Durable AI/evaluation activities and approval loops. | Needs disciplined boundary with Java services. | MIT. | Consider | Medium | https://github.com/temporalio/sdk-python

## Gap Matrix
Competitive Gap Matrix
Where market categories stop and Nessovo HumanOS Work Intelligence must go further.
Capability | Employee monitoring | Task mining | Developer telemetry | AI-agent memory | Nessovo target | Differentiation note | Priority | MVP
App/window/browser tracking | Strong | Medium | Medium | Low | Strong | Commodity capture requirement. | High | Yes
Screen snapshots / replay | Strong | Strong | Low | Low | Strong | Need event-driven capture with privacy controls. | High | Yes
Keystroke / text capture | Strong | Medium | Low | Low | Controlled strong | Reconcile keystrokes with resulting text; block secrets. | High | Yes
Task association | Medium | Strong | Low | Low | Strong | Must bind every episode to task contracts and plan. | High | Yes
Acceptance-criteria verification | Low | Low | Medium | Low | Strong | Core differentiator: activity is not outcome. | High | Yes
Human vs AI vs automation provenance | Low | Low | Medium | Medium | Strong | Critical for modern AI-assisted work. | High | Yes
Capability graph vs job description | Low | Low | Low | Low | Strong | Role-readiness and skill levels from evidence. | High | Yes
Real-time coaching | Medium | Low | Low | Medium | Strong | Nudge, assist, teach, escalate with confidence thresholds. | High | Yes
Training effectiveness loop | Low | Low | Low | Low | Strong | Capability should rise only after demonstrated application. | High | Yes
Self-improving skills/plugins | Low | Low | Low | Strong | Strong | Skill Forge with evaluations, review and canary release. | Medium | No
Governed employment decision workflow | Medium | Medium | Low | Low | Strong | Human review, dispute, audit and purpose-limited access. | High | Yes
Multi-vertical HumanOS expansion | Low | Medium | Low | Low | Strong | Domain adapters for all business verticals. | Medium | No

## Delivery Stages
Delivery Stages
13 stages total: Stage 0 plus 12 implementation stages.
Stage # | Stage | Objective | Duration weeks | Team size | Dependencies | Exit deliverables | Lead role | Status | Priority | Risk | Start date | End date | Effort PW
0 | Charter, governance and legal boundary | Define scope, lawful basis, DPIA approach, employee transparency, non-goals and decision rights. | 2 | 4 | None | Approved product charter, DPIA draft, monitoring policy, evidence hierarchy. | CEO/CTO/Legal/Product | Not Started | Critical | High | 2026-07-20 | 2026-08-02 | 8
1 | Market/OSS validation and reference architecture | Complete research, architecture options, licence review, build/buy decisions. | 2 | 4 | Stage 0 | Final competitor map, OSS licence notes, architecture decision record. | Product/Architecture | Not Started | High | Medium | 2026-08-03 | 2026-08-16 | 8
2 | Role capability and task contract ontology | Create Role Capability Contract, Task Execution Contract and capability levels. | 3 | 5 | Stage 0 | Schemas, rubrics, example software-dev roles, task templates. | Product/AI/Domain Experts | Not Started | Critical | High | 2026-08-17 | 2026-09-06 | 15
3 | Device agent foundation | Build signed Windows/macOS agent skeleton, policy sync, session control, local encrypted journal. | 5 | 7 | Stage 0,1 | Agent installs, starts sessions, records heartbeat and policy status. | Desktop/Platform | Not Started | Critical | High | 2026-09-07 | 2026-10-11 | 35
4 | Telemetry ingestion and evidence storage | Implement event gateway, schema registry, event bus, object store, audit linkage. | 4 | 6 | Stage 3 | Signed batch ingestion, dedupe, object evidence store, basic replay API. | Backend/Data | Not Started | Critical | High | 2026-10-12 | 2026-11-08 | 24
5 | Universal capture MVP | Capture app/window, mouse, keyboard metadata, event-driven screenshots, idle/process/file events. | 6 | 8 | Stage 3,4 | Correlated timeline with visual states, secure-field blocking, local redaction. | Desktop/Data | Not Started | Critical | High | 2026-11-09 | 2026-12-20 | 48
6 | Development semantics and AI-agent adapters | Add browser, terminal, Git, Codex, Claude Code, IDE/toolchain adapters. | 6 | 8 | Stage 5 | Agent traces, terminal commands, git diff events, build/test detection. | Integrations/AI | Not Started | High | High | 2026-12-21 | 2027-01-31 | 48
7 | Provenance and task assurance engine | Build episode segmentation, task alignment, actor attribution and acceptance-criteria evaluation. | 7 | 8 | Stage 2,6 | Task evidence graph, assurance findings, confidence scores, blocker detection. | AI/Backend | Not Started | Critical | High | 2027-02-01 | 2027-03-21 | 56
8 | Capability graph and baseline assessment | Map job descriptions to capabilities, track claims, build evidence-weighted levels. | 5 | 6 | Stage 2,7 | Capability profile, claim-evidence discrepancy workflow, role readiness model. | AI/Product/Backend | Not Started | High | Medium | 2027-03-22 | 2027-04-25 | 30
9 | Growth coach and learning loop | Create coaching interventions, training prescriptions, worker guidance and learning outcome tracking. | 5 | 6 | Stage 7,8 | Nudge/assist/teach/escalate modes, training plans, effectiveness metrics. | AI/L&D/Product | Not Started | High | Medium | 2027-04-26 | 2027-05-30 | 30
10 | Employee and manager dashboards | Build employee timeline/corrections and manager exception-led reports. | 5 | 7 | Stage 7,8,9 | Employee portal, dispute workflow, manager task/capability reports. | Frontend/Backend | Not Started | High | High | 2027-05-31 | 2027-07-04 | 35
11 | Skill Forge and self-improvement | Create observation-to-skill-update loop with evals, approval, canary and rollback. | 6 | 6 | Stage 9,10 | Skill registry, update proposals, eval harness, review workflow. | AI/Platform | Not Started | Medium | No | 2027-07-05 | 2027-08-15 | 36
12 | Security hardening, internal pilot and rollout | Performance tuning, red-team, compliance validation, pilot measurement, rollout decision. | 6 | 8 | Stages 0-11 | Pilot report, security sign-off, launch readiness, next-domain roadmap. | All | Not Started | Critical | High | 2027-08-16 | 2027-09-26 | 48

## Microservices Map
Microservices Map
Logical bounded contexts and implementation technology for HumanOS Work Intelligence.
Service | Boundary / responsibility | Primary runtime | Data store | Consumes | Publishes | MVP | Owner | Notes / dependencies | Source / reference
Device Agent Gateway | Registers devices, syncs policy, receives agent health and session control. | Java Spring Boot | PostgreSQL | device.heartbeat, session.request | device.status, policy.applied | Yes | Platform | mTLS, device certs, update service. | Spring microservices / OPA / mTLS
Telemetry Ingestion | Accepts signed event batches, validates schema, deduplicates, partitions by tenant. | Java Spring Boot + Kafka | Kafka + PostgreSQL metadata | agent.event.batch | activity.event.normalized | Yes | Backend | High throughput, idempotent ingestion. | https://kafka.apache.org/documentation/
Evidence & Provenance | Stores events, visual states, causal graph, evidence hashes and replay timeline. | Java Spring Boot | PostgreSQL + graph store + object storage | activity.event.normalized | evidence.linked, provenance.updated | Yes | Data | Graph model for human/AI/automation causality. | OpenTelemetry + graph/event sourcing
Visual Evidence Store | Stores screenshots, changed regions, OCR/accessibility extracts and retention metadata. | Java Spring Boot | S3/MinIO + PostgreSQL | visual.state.created | visual.evidence.indexed | Yes | Data/Security | Dedup, retention, encryption, access audit. | Screenpipe / ScreenCaptureKit / Windows capture
Task Intelligence | Compiles task contracts, aligns episodes to tasks, checks acceptance criteria. | Python AI + Java orchestration | PostgreSQL + vector store | evidence.linked, task.updated | task.assessment.created | Yes | AI/Product | Uses LLM + deterministic validators. | Task mining + Codex hooks
Role & Capability | Compiles job descriptions, stores capability definitions, updates capability evidence. | Java Spring Boot + Python scoring | PostgreSQL + graph store | task.assessment.created, training.outcome | capability.updated | Yes | Product/AI | Evidence-weighted capability levels. | SFIA-style role mapping
Growth Coach | Generates worker guidance, coaching interventions and skill-gap remediation. | Python FastAPI | PostgreSQL + vector store | task.assessment.created, capability.gap | coaching.intervention.created | Yes | AI/L&D | Nudge/assist/teach/escalate modes. | LLM/skills/evals
Learning & Assessment | Manages training plans, micro-lessons, practice tasks and reassessment. | Java Spring Boot + Python evals | PostgreSQL | capability.gap, coaching.outcome | learning.assigned, learning.completed | Partial | L&D | Training only increases capability when applied in real tasks. | Capability model
Skill Forge | Captures system observations, proposes HumanOS skill/plugin/evaluator improvements. | Java + Python | PostgreSQL + Git repo + eval store | skill.observation.created, user.feedback | skill.update.proposed, skill.version.active | Later | AI Platform | Evals, approval, canary, rollback. | Claude-Mem / Task Observer / Record & Replay
AI Agent Adapter Hub | Normalises Codex, Claude Code, Cursor, terminal and IDE agent events. | Python + Java | PostgreSQL | agent.raw.event | agent.event.normalized | Yes | Integrations | Use official hooks where available. | https://developers.openai.com/codex/hooks
Governance & Review | Manages disputes, human review, evidence access requests and legal workflows. | Java Spring Boot | PostgreSQL + audit log | assessment.disputed, access.requested | review.decision.recorded | Yes | Governance | Mandatory for high-risk employment AI. | ICO / EU AI Act / policy-as-code
Reporting & Analytics | Creates employee, manager, team and executive reports. | Java Spring Boot + BI warehouse | PostgreSQL/warehouse | task.assessment, capability.updated | report.generated | Yes | Analytics | Exception-led reporting; no raw firehose by default. | Workforce analytics patterns
Policy Service | Policy-as-code for capture scope, access control, jurisdictions and exclusions. | OPA + Java Spring Boot | Policy repo + PostgreSQL | policy.query | policy.decision | Yes | Security | Decouple policy decisions from services. | https://www.openpolicyagent.org/docs
Audit & Compliance | Immutable audit logs for evidence access, AI decisions, reviews and skill changes. | Java Spring Boot | Append-only log + warehouse | all.audit.events | audit.report.generated | Yes | Security/Governance | Existing HumanOS service extension. | HumanOS foundation
Model Gateway | Routes AI requests, prompts, tools, safety checks and model usage. | Python/Java gateway | PostgreSQL + vector/cache | ai.request | ai.response, ai.audit | Yes | AI Platform | Centralised model routing and guardrails. | OpenTelemetry GenAI

## MVP Backlog
MVP Backlog
Initial epics and features for the controlled internal pilot.
Epic ID | Epic | Feature / user story | Stage | Owner | Priority | Status | Effort pts | Acceptance criteria | Dependencies | Notes
E01 | Work session control | Employee can start/pause/stop a monitored work session against a HumanOS task. | 3 | Desktop/Backend | Critical | Not Started | 8 | Session event exists; visible status; offline buffering; task ID linked. | Device Agent Gateway | No hidden mode.
E02 | Policy sync | Agent receives tenant/jurisdiction/capture policy before recording. | 3 | Platform/Security | Critical | Not Started | 8 | Policy signature verified; excluded apps/domains applied; audit emitted. | Policy Service | Policy version visible.
E03 | App/window telemetry | Capture foreground app, process, window title and transitions. | 5 | Desktop | Critical | Not Started | 5 | 99% foreground app transition capture in pilot. | Agent foundation
E04 | Click + visual state | Capture mouse click with pre/post visual states and changed region. | 5 | Desktop/AI | Critical | Not Started | 13 | 98% click-to-state correlation in supported pilot apps. | Visual Evidence Store
E05 | Text-state capture | Reconcile physical input, text deltas and resulting artefact changes in approved controls. | 5 | Desktop/Data | Critical | Not Started | 21 | 95% reconstruction in supported controls; zero secure-field leakage. | Policy / UI accessibility | Avoid raw keylogger-only logic.
E06 | File/process telemetry | Capture process tree, file create/modify/delete and build/test process markers. | 5 | Desktop/Data | High | Not Started | 13 | Event causal chain links process -> file/test output. | ETW/macOS process bridge
E07 | Browser adapter | Capture active tab, title, approved URL/domain, navigation and visible page event. | 6 | Integrations | High | Not Started | 8 | Chrome/Edge MV3 extension sends normalized events. | Native messaging
E08 | Terminal adapter | Capture command, cwd, exit code, stdout/stderr summary and process duration. | 6 | Integrations | High | Not Started | 13 | Command event links to resulting processes and files. | Shell/PTTY hooks
E09 | Git adapter | Capture branch, diff summary, commit, PR, changed files and reviewer state. | 6 | Integrations | High | Not Started | 8 | Git diff/commit events linked to task and actor. | GitHub/GitLab connectors
E10 | Codex adapter | Capture Codex prompt/tool/permission/stop lifecycle via hooks. | 6 | AI Integrations | Critical | Not Started | 8 | Agent events mapped to OTel-style spans and provenance graph. | Codex hooks
E11 | Claude Code adapter | Capture Claude Code usage through hooks/OTel/MCP where available. | 6 | AI Integrations | High | Not Started | 8 | Prompt/tool/file/command events normalized. | Claude Code config
E12 | Episode segmentation | Group raw events into meaningful 30-180 second work episodes. | 7 | AI/Data | Critical | Not Started | 21 | Episodes align with human review >=90% in pilot sample. | Evidence graph
E13 | Task alignment classifier | Classify episodes as on-task, supporting, blocked, automated-wait, idle, unrelated. | 7 | AI | Critical | Not Started | 21 | False idle below 5%; confidence calibrated. | Task contracts
E14 | Acceptance criteria validator | Determine task completion evidence and missing verification. | 7 | AI/Product | Critical | Not Started | 21 | Every criterion has evidence, status and confidence. | Task contract
E15 | Capability graph MVP | Create role capability profile and update capability evidence after assessed tasks. | 8 | AI/Backend | High | Not Started | 13 | Capability level, confidence, recency and evidence visible. | Role ontology
E16 | Growth coach MVP | Generate non-disruptive guidance when task risk or capability gap is detected. | 9 | AI/L&D | High | Not Started | 13 | Nudge/assist/teach messages audited; employee can dismiss/correct. | Task intelligence
E17 | Employee portal | Employee can see timeline, report, capability profile and dispute findings. | 10 | Frontend | Critical | Not Started | 13 | Dispute creates review workflow; employee evidence visible. | Reporting/Governance
E18 | Manager console | Lead sees exception-led task report, blockers, quality gaps and training recommendations. | 10 | Frontend/Product | Critical | Not Started | 13 | Manager report cites evidence and confidence. | Task/capability services
E19 | Skill observation log | System logs user/system corrections as candidate skill improvements. | 11 | AI Platform | Medium | Not Started | 8 | Observation includes issue, improvement, principle, evidence and confidentiality class. | Skill Forge
E20 | Pilot validation | Run internal pilot and measure capture accuracy, task alignment, worker trust and manager value. | 12 | Leadership/QA | Critical | Not Started | 21 | Pilot report with acceptance metrics and rollout decision. | All MVP epics

## Event Data Model
Event & Data Model
Core evidence graph, events, entities and provenance relationships.
Model area | Entity/Event | Purpose | Key fields | Producer | Consumer | MVP | Notes | Source/ref
Entity | WorkSession | Tracks a monitored work period and task linkage. | session_id, person_id, device_id, task_id, start/end, policy_version | Device Agent Gateway | Task Intelligence, Reporting | Yes | Supports pause/private/excluded segments.
Entity | TaskExecutionContract | Structured task expectations and acceptance criteria. | objective, criteria, evidence_required, tools, risks, reviewer | Task Intelligence | Task Assurance, Coach | Yes | Compiled from HumanOS task.
Entity | RoleCapabilityContract | Structured role/job description capability requirements. | role, level, capabilities, evidence rubrics, autonomy | Role & Capability | Capability Graph | Yes | Job description becomes measurable contract.
Event | activity.application.changed | Foreground app/window/process transition. | app, pid, window_title, timestamp, confidence | Desktop Agent | Evidence Service | Yes | Universal capture stream.
Event | activity.input.observed | Physical mouse/keyboard input metadata. | input_type, key/button, coordinate, injected_flag, secure_field | Desktop Agent | Evidence Service | Yes | Text stored separately and controlled. | Microsoft SetWindowsHookEx
Event | activity.visual.changed | Visual state changed due to click/app/action. | before_state, after_state, changed_region, screenshot_hash | Desktop Agent | Evidence Service | Yes | Event-driven capture, not brute-force video.
Event | activity.text.changed | Resulting text delta in an approved control/editor. | inserted_ref, deleted_ref, source_control, privacy_class | Desktop Agent/IDE Adapter | Evidence, Task Intelligence | Yes | Authoritative text-state > raw keys.
Event | agent.prompt.submitted | Prompt sent to Codex/Claude/Cursor/etc. | agent, prompt_ref, task_id, turn_id | AI Agent Adapter | Provenance, Coach | Yes | Use official hooks where possible. | Codex hooks
Event | agent.tool.completed | Agent tool command or file operation completed. | tool, input_ref, output_ref, exit_code, files_touched | AI Agent Adapter | Provenance | Yes | Causal parent is prompt or prior tool call. | OpenTelemetry GenAI
Event | process.completed | System command/build/test process ended. | command_ref, cwd, exit_code, duration, stdout_ref | Terminal/OS Adapter | Task Assurance | Yes | Distinguish automated wait from idle.
Event | task.criterion.verified | Task criterion satisfied or failed with evidence. | criterion_id, status, evidence_refs, confidence | Task Intelligence | Reporting/Capability | Yes | Outcome-driven assessment.
Event | capability.evidence.recorded | Capability evidence gained from a task episode. | capability_id, level_signal, confidence, evidence_refs | Role & Capability | Learning/Reporting | Yes | Repeated evidence updates profile.
Event | skill.observation.created | Candidate improvement to HumanOS skill/plugin/evaluator. | issue, improvement, principle, evidence_refs, confidentiality | Skill Forge | Skill Review | Later | Human approval before activation.

## AI Capability System
AI Capability System
How Nessovo verifies capability, improves employees, and improves HumanOS itself.
Level | Name | Meaning | Evidence examples | Manager interpretation | Employee experience
0 | Unverified | Claim exists but no reliable evidence yet. | Onboarding claim, CV, self-assessment. | Do not assume capability; assign baseline tasks. | Skill locked or greyed out.
1 | Learning | Requires direct instruction and close guidance. | Fails routine tasks without support; training in progress. | Needs guided work and mentor review. | Starter quests and basic lessons.
2 | Assisted | Can complete routine work with support. | Completes tasks when guided; recurring review required. | Suitable for scoped tasks. | Progress quests and coaching.
3 | Independent | Reliably completes standard work independently. | Multiple successful tasks with appropriate verification. | Meets normal role requirement. | Core skill unlocked.
4 | Advanced | Handles complex/non-routine work and supports others. | Solves unfamiliar variants; mentors peers; improves playbooks. | Can own complex workstreams. | Advanced challenges and mentor badges.
5 | Mastery | Defines standards, solves novel problems and coaches others. | Creates reusable methods; reviews designs; leads standards. | Can define organisational practice. | Mastery status and skill authoring.
Loop | Input | AI action | Human control | Output
Employee learning loop | Task evidence, errors, coaching response | Detect gap and recommend training/practice | Employee can challenge; manager/mentor reviews | Capability evidence and learning plan
Task assurance loop | Task contract, activity episodes, artefacts | Assess task alignment, progress, quality and completion | Lead/reviewer decides status | Evidence-backed task report
Organisational learning loop | Repeated successful work patterns | Propose playbooks/templates/workflows | Domain expert approves | HumanOS workflow / standard method
Skill Forge loop | User correction, evaluator failure, new research | Propose skill/plugin/evaluator update | Skill reviewer, tests, canary, rollback | Versioned HumanOS skill
Evaluator | Purpose | Runtime | Inputs | Outputs | MVP
Task alignment classifier | Classify episode relative to assigned task. | Python | Episode, task contract, app context, artefacts | classification + confidence + evidence refs | Yes
Provenance classifier | Classify human/AI/automation/system actor. | Python + rules | Input events, agent hooks, process tree, file deltas | actor + confidence + causal edge | Yes
Acceptance criteria verifier | Determine criterion status and missing evidence. | Python + deterministic validators | Task contract, artefacts, tests, screenshots, reports | met/partial/missing + evidence | Yes
Capability updater | Update capability confidence and level from evidence. | Python scoring + Java persistence | Task assessment, difficulty, independence, guidance | capability signal + level update proposal | Yes
Coaching selector | Choose whether/how to intervene. | Python | Risk, confidence, history, user preferences | nudge/assist/teach/escalate/observe | Yes
Skill improvement evaluator | Test proposed skill/plugin changes. | Python | Observation, skill diff, test corpus, policy constraints | pass/fail/regression/risk report | Later

## Governance
Governance & Compliance Controls
Minimum controls required because this product uses intrusive monitoring and employment-related AI.
Control area | Requirement | Implementation | Owner | MVP | Evidence | Risk reduced | Source URL | Notes
Transparency | Workers must know what is captured, why, when and how reports are used. | Visible recording indicator, policy notice, employee portal. | Legal/Product | Yes | Acknowledgement + policy version | Employee trust/legal risk | https://www.gov.uk/data-protection-your-business/monitoring-staff-at-work
DPIA | High-risk monitoring requires formal assessment before deployment. | DPIA workflow, risk register, mitigation sign-off. | DPO/Legal | Yes | Approved DPIA | Regulatory breach | https://ico.org.uk/for-organisations/uk-gdpr-guidance-and-resources/employment/monitoring-workers/data-protection-and-monitoring-workers/
Human review | AI findings cannot automatically make consequential employment decisions. | Review queue, authority checks, reviewer notes, final decision record. | HR/Managers | Yes | ReviewDecision entity | Unfair automated decision | https://ico.org.uk/for-organisations/advice-and-services/audits/data-protection-audit-framework/toolkits/artificial-intelligence/human-review/
Employee challenge | Employee can see evidence and challenge inaccurate assessments. | Dispute workflow, correction UI, response SLA. | Governance | Yes | Dispute log | False allegation/trust damage | https://ico.org.uk/for-organisations/uk-gdpr-guidance-and-resources/employment/monitoring-workers/data-protection-and-monitoring-workers/
Secure-field blocking | Passwords, secrets and sensitive fields must not be stored. | OS secure-field detection, secret scanning, redaction before upload. | Security/Desktop | Yes | Leakage tests | Credential/data breach | https://learn.microsoft.com/en-us/windows/win32/winmsg/lowlevelkeyboardproc
Purpose limitation | Raw evidence access must be purpose-limited and audited. | RBAC/ABAC, reason codes, time-limited grants, audit service. | Security | Yes | Access logs | Manager misuse | https://www.openpolicyagent.org/docs
Retention | Raw screenshots/text should have short retention unless escalated. | Retention policy engine, auto-delete, legal hold workflow. | Legal/Security | Yes | Retention job logs | Data concentration risk
Jurisdiction packs | UK, EU, Pakistan and future regions need separate deployment policies. | Policy service by tenant/location, legal review checklist. | Legal | Yes | Policy pack version | Cross-border non-compliance | https://ai-act-service-desk.ec.europa.eu/en/ai-act/annex-3
No emotion/personality inference | Do not infer emotion, personality or protected traits from behaviour. | Prohibited classifier categories and model gating. | AI Governance | Yes | Model policy tests | AI Act/high-risk harm | https://ai-act-service-desk.ec.europa.eu/en/ai-act/annex-3
Skill governance | Self-improvement must use evaluation, approval, canary and rollback. | Skill lifecycle service with signed versions and tests. | AI Platform | Later | Skill review records | Unsafe self-modification

## Risk Register
Risk Register
Initial risks and mitigations for the Nessovo HumanOS Work Intelligence programme.
Risk ID | Risk | Category | Likelihood | Impact | Score | Mitigation | Owner | Stage | Status
R01 | Employee distrust due to intrusive monitoring | Trust/Adoption | 4 | 5 | 20 | Employee portal, transparency, correction workflow, coaching value, no hidden mode. | Product/HR | 0-12 | Open
R02 | False AI conclusion damages employee | AI/Governance | 3 | 5 | 15 | Evidence links, confidence, alternative explanations, human review, dispute mechanism. | AI Governance | 7-12 | Open
R03 | Sensitive data leakage from screenshots/text | Security/Privacy | 3 | 5 | 15 | Secure-field blocking, secret detection, local redaction, retention limits, access control. | Security | 3-12 | Open
R04 | Device agent creates performance overhead | Technical | 3 | 4 | 12 | Event-driven capture, dedupe, CPU budgets, pilot telemetry, native implementation. | Desktop | 3-12 | Open
R05 | Linux/Wayland capture inconsistency | Technical | 4 | 3 | 12 | Windows/macOS first; Linux later with capability matrix. | Desktop | Post-MVP | Open
R06 | Legal non-compliance in employment AI | Legal | 3 | 5 | 15 | DPIA, jurisdiction packs, human review, policy notices, legal sign-off before pilot. | Legal/DPO | 0-12 | Open
R07 | Managers misuse raw evidence | Governance | 3 | 5 | 15 | Purpose-limited access, reason codes, approvals, audit, manager training. | Governance | 10-12 | Open
R08 | System rewards activity volume over outcomes | Product | 3 | 4 | 12 | KPIs based on acceptance criteria, quality, capability and improvement. | Product | 2-12 | Open
R09 | AI-agent provenance incomplete | Technical/AI | 3 | 4 | 12 | Official hooks, OpenTelemetry spans, process tree correlation, manual fallback. | AI Integrations | 6-7 | Open
R10 | Self-improving skills introduce regressions | AI Platform | 3 | 4 | 12 | Eval suites, canary, rollback, human approval, versioned skill registry. | AI Platform | 11 | Open
R11 | Storage cost grows too quickly | Cost | 4 | 3 | 12 | Changed-region screenshots, dedupe, local summarisation, retention tiers. | Data | 4-12 | Open
R12 | Capability model unfairly penalises thinking/research time | AI/Product | 3 | 4 | 12 | Explicit classes for reading/review/blocked/automated wait; employee explanation fields. | AI/Product | 7-10 | Open

## KPI Dashboard
KPI Dashboard
Formula-driven project summary for the initial plan.
Metric | Formula / Value | Interpretation | Leadership readout
Total stages | 13 | Includes Stage 0 plus 12 implementation stages. | 1 | Proceed with a controlled internal pilot focused on software-development teams.
Total duration weeks | 62 | Sequential planning placeholder, not a deadline commitment. | 2 | Build the desktop evidence layer first, but market the product as task assurance + capability development.
Total effort person-weeks | 421 | Stage weeks × indicative team size. | 3 | Use Java/Spring Boot for core domain services; Python for AI/evaluators; native/Rust/Swift/C# for device capture.
Critical stages | 7 | Stages marked critical priority. | 4 | Design governance and employee challenge workflows before any real employee pilot.
High-risk stages | 9 | Stages needing tighter governance/leadership review. | 5 | Adopt OpenTelemetry-style traces for AI-agent activity and extend with Nessovo task/capability semantics.
MVP backlog items | 20 | Initial pilot backlog items.
Critical backlog items | 12 | MVP backlog items requiring early delivery.
Open risks | 12 | Open risks before mitigation review. | Priority | Count
|  |  | Critical | 7
|  |  | High | 5
|  |  | Medium | 1

## Source Register
Source Register
Research sources and what they support in this planning workbook.
Source | Type | Supports | Source URL | Priority | Notes
Teramind employee monitoring | Commercial | Monitoring market baseline: screenshots, recordings, keystrokes, apps/web, active/idle. | https://www.teramind.co/solutions/employee-monitoring/ | High
Teramind screen recording feature | Commercial | Live view and historical playback capabilities. | https://www.teramind.co/features/live-desktop-view-history-playback/ | High
ActivTrak AI Insights | Commercial | AI tool usage/adoption and productivity impact market signal. | https://support.activtrak.com/hc/en-us/articles/50125731483675-AI-Insights-Add-on | High
UiPath Task Capture settings | Commercial docs | Screenshots per click/keyboard action and capture modes. | https://docs.uipath.com/task-capture/standalone/2021.10/user-guide/capture-settings | High
ABBYY Task Mining | Commercial docs | Screen snapshots, buttons clicked, text entered and task association. | https://help.abbyy.com/en-us/timeline/6/user_guide/task-mining | High
Screenpipe GitHub | OSS/source-available | Local screen/audio/activity memory, accessibility tree, OCR fallback, AI pipes. | https://github.com/screenpipe/screenpipe | High | Commercial licence needed for commercial use.
OpenAdapt Desktop GitHub | OSS | Record/compile/replay/repair/teach workflow capture concept. | https://github.com/OpenAdaptAI/openadapt-desktop | High | Experimental product boundary.
ActivityWatch GitHub | OSS | Active window/browser/AFK watcher model. | https://github.com/ActivityWatch/activitywatch | High
Claude-Mem GitHub | OSS | AI-agent memory architecture via hooks/worker/SQLite/FTS5. | https://github.com/thedotmack/claude-mem | High
Task Observer GitHub | OSS/methodology | Observation-to-skill-improvement methodology. | https://github.com/rebelytics/one-skill-to-rule-them-all | High
OpenAI Codex Hooks | Official docs | Codex lifecycle hook instrumentation. | https://developers.openai.com/codex/hooks | High
OpenAI Record & Replay | Official docs | Demonstration-to-reusable-skill reference concept. | https://developers.openai.com/codex/record-and-replay | Medium
OpenTelemetry semantic conventions | Official docs | Standard trace/log/metric naming across platforms. | https://opentelemetry.io/docs/concepts/semantic-conventions/ | High
OpenTelemetry GenAI conventions | GitHub | GenAI spans/metrics/events and MCP/provider conventions. | https://github.com/open-telemetry/semantic-conventions-genai | High
Spring microservices | Official docs | Spring Boot/Cloud for Java microservices. | https://spring.io/microservices | High
Spring Cloud compatibility | Official docs | Spring Boot and Spring Cloud release train compatibility. | https://spring.io/projects/spring-cloud/ | Medium
Apache Kafka documentation | Official docs | Event streaming for event-driven microservices. | https://kafka.apache.org/documentation/ | High
Open Policy Agent | Official docs | Policy-as-code for microservices, Kubernetes, CI/CD and APIs. | https://www.openpolicyagent.org/docs | High
Microsoft UI Automation | Official docs | Windows UI element tree and accessibility metadata. | https://learn.microsoft.com/en-us/dotnet/framework/ui-automation/ui-automation-overview | High
Microsoft Event Tracing for Windows | Official docs | Kernel/application event tracing. | https://learn.microsoft.com/en-us/windows/win32/etw/about-event-tracing | High
Microsoft SetWindowsHookEx | Official docs | Low-level mouse/keyboard hook capability and constraints. | https://learn.microsoft.com/en-us/windows/win32/api/winuser/nf-winuser-setwindowshookexw | High
Apple ScreenCaptureKit | Official docs | macOS screen/audio capture framework. | https://developer.apple.com/documentation/screencapturekit | High
Chrome tabs captureVisibleTab | Official docs | Browser visible tab capture limits and permissions. | https://developer.chrome.com/docs/extensions/mv2/reference/tabs/ | Medium
UK worker monitoring GOV.UK | Government | Workplace monitoring notification and justification. | https://www.gov.uk/data-protection-your-business/monitoring-staff-at-work | High
ICO worker monitoring guidance | Regulator | DPIA, transparency, challenge, employment monitoring controls. | https://ico.org.uk/for-organisations/uk-gdpr-guidance-and-resources/employment/monitoring-workers/data-protection-and-monitoring-workers/ | High
EU AI Act Annex III | Regulatory | High-risk employment/worker management AI categories. | https://ai-act-service-desk.ec.europa.eu/en/ai-act/annex-3 | High