## Index
Nessovo HumanOS Work Intelligence — Programme Workbook
Research-backed planning and execution system of record. Stage 0 and Stage 1 are executed as one Foundation & Validation workstream, with separate governance and architecture approval gates.
Workbook section | Purpose | Primary users | Stage | Current state | Approval state | Next action | Notes
Foundation Dashboard | Formula-driven foundation readiness, blockers, decisions and delivered artefacts. | Leadership/Programme | 0–1 | Complete | Gate approvals pending | Resolve immediate Nessovo decisions. | Primary executive entry point.
Master Prompts | Prompt-engineering principles, applied Stage 0–1 master prompt, and execution prompts for Stages 2 and 3. | Programme/Product/Architecture | 0–3 | Complete | Not applicable | Use Stage 2/3 prompts after gate decision. | Reusable execution framework.
Stage 0-1 Workplan | Detailed action plan with owners, dependencies, deliverables, acceptance criteria and formula maturity. | Programme/All leads | 0–1 | Complete | Formal owners/approvals pending | Assign names and close open actions. | 67 actions.
Product Charter v1 | Strategic purpose, value proposition, boundaries, pilot scope and product principles. | CEO/CTO/Product/HR | 0 | Draft complete | Leadership/DPO/HR approval pending | Run cross-functional charter review. | Detailed charter.
Executive Charter | Concise executive summary and decision position. | Leadership | 0–1 | Updated | Gate pending | Use with Foundation Dashboard. | Short leadership view.
Purpose Policy Matrix | Purpose, necessity, alternatives, minimisation, retention, employee visibility and access by data category. | DPO/Legal/Security/Product | 0 | Draft complete | DPIA/legal approval pending | Review every conditional capture category. | 20 categories.
Stakeholder RACI | Role-level accountability for foundation deliverables and decisions. | Leadership/Programme | 0–1 | Draft complete | Named individuals pending | Replace roles with names. | 22 responsibilities.
Market Landscape | Commercial and category-level competitor/reference research. | Product/Strategy | 1 | Updated | Architecture/product review pending | Maintain quarterly. | Source-backed.
GitHub OSS Scan | Open-source/source-available architecture, maturity, licence and reuse research. | Architecture/Legal/Security | 1 | Updated | Formal licence review pending | Complete legal dependency decisions. | Reference, not automatic reuse.
Gap Matrix | Capability comparison and proprietary-core definition. | Product/Strategy/Architecture | 1 | Updated | Leadership acceptance pending | Approve differentiation boundary. | Outcome, provenance, capability and learning focus.
Build Buy Decisions | Component-level build, buy, integrate, benchmark and defer recommendations. | CTO/Product/Legal | 1 | Draft complete | Procurement/licence approval pending | Approve proprietary core and spikes. | 26 component decisions.
Reference Architecture | HumanOS-aligned logical architecture, runtimes, data, events and deployment boundaries. | Architecture/Engineering/Security | 1 | Draft complete | Architecture Board review pending | Accept or condition ADRs. | Approximately eight initial Work Intelligence deployables.
Architecture Decisions | Versioned ADR register with alternatives, trade-offs and validation requirements. | Architecture Board/CTO | 1 | Draft complete | Review pending | Record accepted/rejected decisions. | 22 ADRs.
Stage 0-1 Gates | Formal approve/conditional/hold/reject criteria for governance and architecture. | Executive Sponsor/CTO/DPO/CISO | 0–1 | Complete criteria | Decisions pending | Close mandatory blockers and record decisions. | 33 gate items.
Assumptions Questions | Unresolved platform, pilot, legal, AI, privacy, cost and capability questions. | All accountable owners | 0–1 | Complete register | 40 items unresolved/assumed | Assign and resolve. | Do not treat assumptions as facts.
Foundation Threats | Privacy, security, AI, employment, trust, architecture and cost threats with controls. | CISO/DPO/Product/Architecture | 0–1 | Draft complete | Security/DPO review pending | Validate blocking controls. | 30 threats.
Pilot Definition | Controlled internal pilot scope, employee protections, success metrics and stop criteria. | Leadership/HR/Product/DPO | 0–12 | Draft complete | Legal/worker/leadership approval pending | Finalise cohort and jurisdiction. | 38 rules/targets.
Delivery Stages | Programme roadmap, dependencies, duration and exit criteria. | Programme/Leadership | 0–12 | Updated | Stage 0–1 gates pending | Approve Stage 2 and 3 mobilisation. | 13 stages total.
Microservices Map | Initial deployables, bounded contexts and HumanOS reuse. | Architecture/Backend/AI/SRE | 1+ | Updated | Architecture Board review pending | Validate existing HumanOS capabilities. | Avoids premature nano-services.
MVP Backlog | Initial product backlog for the controlled technical pilot. | Product/Engineering | 3–10 | Initial draft | Prioritisation pending | Refine after Stages 2 and 3.
Event Data Model | Initial event/entity model and evidence graph. | Backend/Data/AI | 2–7 | Initial draft | Stage 2/4 refinement pending | Replace with approved ontology/contracts.
AI Capability System | Initial capability, coaching and Skill Forge model. | AI/Product/L&D | 2,8–11 | Initial draft | Stage 2/8 refinement pending | Execute Stage 2 ontology prompt.
Governance | Consolidated minimum governance and compliance controls. | DPO/Legal/HR/Security | 0+ | Updated | Approval pending | Operationalise before pilot.
Risk Register | Programme-level top risks and mitigation status. | Leadership/Governance | 0–12 | Updated | Risk acceptance pending | Review monthly. | Foundation Threats is the deeper register.
KPI Dashboard | Programme-level stage, effort, risk and foundation readiness metrics. | Leadership | All | Updated | Not applicable | Use with Foundation Dashboard.
Source Register | Primary research, standards, legal and repository source traceability. | All | Updated | Not applicable | Maintain retrieval/review dates.

## Executive Charter
Executive Charter — Foundation Decision Summary
Concise leadership view. The detailed charter is maintained in Product Charter v1; governance and architecture approvals remain formally pending.
Area | Foundation decision | Current state | Required leadership action
Company | Nessovo | Confirmed | Use as canonical company name.
Platform placement | HumanOS Work Intelligence is a HumanOS module, reusing foundation microservices and supporting future business verticals. | Draft complete | Approve platform placement.
Product definition | Task-aware human-and-AI work intelligence that reconstructs evidence, assures outcomes, develops capability and improves HumanOS skills. | Draft complete | Approve charter and working product name.
Strategic position | Task execution assurance, capability development and human–AI work governance—not activity-volume surveillance. | Draft complete | Approve market position.
Initial vertical | AI-assisted software development on company-managed Windows and macOS devices. | Draft complete | Approve pilot scope and cohort.
Core proprietary capabilities | Evidence/provenance graph; Task Assurance; Capability Graph; Growth Coach; governed Skill Forge. | Draft complete | Approve build focus.
Commodity/reference capabilities | Application/window/browser activity, event streaming, object storage, operational observability and standard OS capture primitives. | Draft complete | Approve build/buy/reference strategy.
Employee value | Fair work attribution, blocker explanation, transparent evidence, correction rights, contextual coaching and skill progression. | Draft complete | Require measurable employee benefit in pilot.
Employer value | Evidence-linked task outcomes, quality, blockers, capability gaps, training effectiveness and safer AI-agent use. | Draft complete | Require exception-led reporting and human judgement.
Governance boundary | No covert general monitoring, emotion/personality inference, click/keystroke productivity scoring or solely automated consequential employment decisions. | Draft complete | Approve prohibited uses and policy enforcement.
Employee rights | Visible monitoring, own evidence access, correction, explanation, dispute and meaningful human review. | Draft complete | Approve operational rights workflow.
Data principle | Minimum necessary, task-scoped evidence with local exclusion/redaction and short raw retention. | Draft complete | Commission full DPIA and legal review.
Architecture | Rust/native endpoint agent; Java/Spring durable HumanOS domains; Python AI/evaluation workers; Kafka-compatible events; PostgreSQL/object storage first. | Draft complete | Architecture Board review.
Microservice strategy | Approximately eight initial Work Intelligence deployables plus reused HumanOS foundations; split only for proven security, scale, ownership, availability or transactional boundaries. | Draft complete | Reject premature nano-services.
Java/Spring baseline | Retain the current supported HumanOS baseline unless migration is justified; benchmark Java 25 LTS with Spring Boot 4.1 and compatible Spring Cloud for greenfield-compatible services. | Platform inventory required | Confirm current HumanOS versions and migration policy.
Stage structure | Stage 0 and Stage 1 operate as one Foundation & Validation workstream but retain separate formal gates. | Confirmed planning model | Record Stage 0 and Stage 1 decisions independently.
Current readiness | Foundation research and draft artefacts are complete; legal/DPO, worker consultation, security, licence, cost, architecture and resourcing decisions remain. | Gate pending | Resolve dashboard decision list.
Next mobilisation | Stage 2 Role/Task/Capability Ontology and Stage 3 Device Agent Foundation. | Prompts ready | Mobilise only under gate conditions and named ownership.

## Market Landscape
Market Landscape — Commercial and Category References
No single reviewed platform provides Nessovo's complete combination. The strategic gap is the integrated evidence → task assurance → capability development → governed self-improvement loop.
Vendor / system | Category | Proven market capability | Relevant lesson | Limit relative to Nessovo target | Nessovo action | Strategic relevance | Source URL | Research note
Teramind | Employee monitoring / insider risk | Screen recording/playback, keystrokes, applications, websites, active/idle and behavioural controls. | Comprehensive desktop monitoring is commercially established. | Primarily observes and governs activity; does not provide evidence-linked task contracts, capability progression and Skill Forge. | Benchmark control coverage; do not use as product core unless later enterprise connector is justified. | High | https://www.teramind.co/solutions/employee-monitoring/ | Closest commercial baseline for raw monitoring.
ActivTrak | Workforce analytics / AI adoption | Application and website analytics, work patterns, productivity/capacity views, AI usage and coaching-oriented insights. | Management demand is moving from time tracking to workforce and AI-use intelligence. | Aggregate behavioural analytics rather than exact causal task reconstruction and technical-quality assurance. | Benchmark reporting and manager experience. | High | https://support.activtrak.com/hc/en-us/articles/50125731483675-AI-Insights-Add-on | Relevant to reporting and adoption metrics.
UiPath Task Mining / Task Capture | Task mining / automation discovery | Desktop screenshots, clicks/keyboard actions, UI elements, process sequences and automation opportunity discovery. | Action-level capture and workflow reconstruction are proven enterprise patterns. | Optimised for process discovery/automation rather than individual task-outcome assurance and capability development. | Learn capture/review patterns; consider future process-platform integration. | High | https://docs.uipath.com/task-capture/standalone/2021.10/user-guide/capture-settings | Strong evidence that click + screenshot + UI context is viable.
ABBYY Timeline Task Mining | Task/process intelligence | Screen snapshots, buttons clicked, text entered, application usage and task association. | Task definitions can organise raw user actions into analysable sequences. | Does not provide the complete role-claim, capability, real-time coaching and self-improvement model. | Learn task-segmentation and process-variant concepts. | High | https://help.abbyy.com/en-us/timeline/6/user_guide/task-mining
Soroco Scout | Work graph / process intelligence | Maps team-machine interactions, process variants, workarounds, effort leakage and automation opportunities. | A work-graph framing is strategically close to Nessovo's evidence/provenance graph. | Generally team/process-oriented and privacy-minimised rather than exact individual task assurance and training. | Benchmark graph terminology and enterprise process use cases. | Medium | https://soroco.com/
Workfellow | Process intelligence / task mining | Combines process and task mining to locate workflow friction and automation potential. | There is demand for understanding how work actually flows across systems. | Limited public evidence of exact text, technical outcome validation or longitudinal capability development. | Watch and compare process-intelligence partnerships. | Medium | https://www.workfellow.ai/
Microsoft Power Automate AI Recorder | Record / replay / RPA | Records screen, voice, mouse and keyboard demonstrations and converts them into desktop automations. | A demonstrated successful workflow can become a reusable procedure. | Creates automation, not a continuous task, capability and employee-development operating system. | Adopt demonstration-to-skill mental model; do not depend on it for core capture. | Medium | https://learn.microsoft.com/en-us/power-automate/desktop-flows/create-flow-using-ai-recorder
OpenAI Codex Hooks | AI-agent lifecycle instrumentation | Lifecycle hooks around prompts, tools, permissions, session start/stop and validations. | Official semantic hooks are more accurate than screen-only inference for agent activity. | Provider-specific and limited to instrumented Codex activity. | Integrate through a provider-normalising AI Adapter Hub. | High | https://developers.openai.com/codex/hooks | Core provenance input.
OpenAI Record & Replay | Workflow demonstration to reusable skill | Converts a demonstrated stable workflow into a reusable skill with inputs, steps and verification. | Strong model for turning real work into governed reusable skills. | Not a continuous employee work-intelligence platform and availability/feature scope may vary. | Learn for Skill Forge; keep HumanOS implementation provider-neutral. | Medium | https://developers.openai.com/codex/record-and-replay
LinearB | Developer productivity and AI-work governance | Engineering workflow metrics, bottleneck analysis, AI activity detection, workflow automation, team coaching and business alignment. | Developer intelligence increasingly combines AI adoption, workflow and outcome signals. | Centred on SDLC/tool data and delivery metrics rather than universal desktop evidence, job capability claims and cross-vertical learning. | Benchmark technical-manager experience and integrate Git/SDLC data where useful. | High | https://linearb.io/platform/ai-developer-productivity-insights | Strong adjacent competitor for software-development vertical.
Jellyfish | Engineering intelligence / AI-SDLC | Combines developer-tool, allocation, delivery, AI usage, cost, bottleneck and developer-experience signals. | Task/project, PR and AI-use data can be tied to business outcomes without manual time tracking. | Does not publicly position as universal endpoint reconstruction, exact human/agent causality or role capability verification. | Benchmark outcome-based engineering reporting and AI ROI. | High | https://jellyfish.co/ | Strong adjacent competitor.
GitClear | Code quality and developer analytics | Repository-level code activity, AI-code impact, code-quality research and review analytics. | Code-change quality and attribution are more useful than raw line-count metrics. | Repository scope cannot explain all desktop work, requirements, blockers or capability context. | Consider future connector/benchmark; retain Nessovo task/provenance core. | Medium | https://www.gitclear.com/
TechWolf | Skills/work intelligence | Continuously infers skills from actual work signals and connects skills, work and market intelligence. | Self-reported skills are insufficient; dynamic work evidence is a validated market need. | Focuses on workforce skills intelligence rather than exact task execution, raw evidence and real-time technical coaching. | Benchmark skills ontology, HR integration and evidence transparency; build Nessovo Capability Graph. | High | https://www.techwolf.ai/product/skills-intelligence | Directly relevant to role-claim and capability goals.
Eightfold | Talent and work intelligence | Models skills, capabilities, aspirations and work signals for hiring, development, project staffing and career recommendations. | Live work signals are entering talent intelligence and career development. | Broader HR/talent platform; public material does not demonstrate Nessovo's exact endpoint/task-evidence and challenge model. | Benchmark role readiness, employee growth and talent-market integration. | High | https://eightfold.ai/products/
Gloat | Workforce graph / agentic HR | Dynamic skills ontology, workforce graph, task-role mapping, work orchestration, audit trails and agentic HR actions. | Workforce graphs, governed agent actions and task-level human–AI orchestration validate parts of Nessovo's direction. | HR-system and workforce orchestration focus rather than complete endpoint evidence and task-quality reconstruction. | Benchmark workforce graph, employee experience and explainable agent action. | High | https://gloat.com/platform/workforce-graph/ | Important strategic adjacent platform.
Degreed | Learning, coaching and skills development | AI-powered learning, coaching, roleplay, skill review, pathways and behaviour-change-oriented development. | Training must be personalised and measured through behaviour/application, not content completion alone. | Does not provide universal work observation, task assurance or causal provenance. | Integrate/buy content selectively; build the evidence-to-learning effectiveness loop. | High | https://degreed.com/experience/artificial-intelligence/
OpenTelemetry GenAI semantic conventions | Open standard / AI observability | Common attributes and events for model, agent, tool and provider telemetry. | Standards reduce provider lock-in and improve cross-agent correlation. | Operational conventions do not define employee, task, capability, evidence or employment governance semantics. | Adopt operational conventions and extend with Nessovo domain contracts; keep raw evidence separate. | High | https://opentelemetry.io/docs/specs/semconv/registry/attributes/gen-ai/
Nessovo HumanOS Work Intelligence | Task assurance / capability development / organisational learning | Target combination: universal evidence, task contracts, human/AI provenance, outcome verification, capability graph, coaching, employee challenge and governed Skill Forge. | The product opportunity is integration and semantics, not invention of every capture primitive. | Requires higher accuracy, governance, endpoint security and cross-domain architecture than any single adjacent category. | Build proprietary core; integrate commodity standards and tools. | Critical | Internal product definition | Strategic target.

## GitHub OSS Scan
GitHub / Open-Source and Source-Available Scan
Repository research for architecture and implementation references. Licence and security review are mandatory before code incorporation or distribution.
Repository | Category | Useful architecture / pattern | Maturity signal | Limit / risk | Verified licence posture | Recommended stance | Likely stage | Source URL | Due-diligence action
screenpipe/screenpipe | Local screen/audio/activity memory | Event-driven visual capture, accessibility-first text, OCR fallback, keyboard/app switches, local storage/search and AI pipes. | Large active source-available project with Windows/macOS/Linux support claims and desktop product. | Commercial licence for commercial use; broad capture and local AI design still require independent security/performance review. | Source-available; repository states personal/non-commercial use and commercial licence requirement. | Study and benchmark; negotiate licence only if strategically justified; do not make it the proprietary core by default. | 3–5 | https://github.com/screenpipe/screenpipe | Legal review; architecture/performance benchmark; supply-chain review.
ActivityWatch/activitywatch | Privacy-first activity tracking | Watcher/server architecture for active window, browser tab and AFK events; local data ownership and extensibility. | Long-running cross-platform project with modular watcher ecosystem. | Lower fidelity; no task assurance, screenshots or exact semantic provenance. MPL file-level obligations matter if code is modified/distributed. | MPL-2.0 verified in repository licence. | Use architecture ideas and possibly protocol-level compatibility; code reuse only after legal decision. | 3–5 | https://github.com/ActivityWatch/activitywatch | Map relevant watcher modules and MPL obligations.
ActivityWatch/aw-watcher-window | Active-window watcher | Small focused watcher producing foreground-window events to a local server. | Mature component in ActivityWatch ecosystem. | Platform-specific behaviour and title sensitivity. | Repository-family licence should be verified per component. | Reference for event semantics and tests. | 3–5 | https://github.com/ActivityWatch/aw-watcher-window | Inspect OS implementations and redaction options.
ActivityWatch/aw-watcher-web | Browser watcher | Browser-extension watcher for active tab/title/URL events. | Mature ActivityWatch companion project. | Browser permissions and sensitive URL/title collection. | Repository-family licence should be verified per component. | Reference for minimal browser adapter. | 6 | https://github.com/ActivityWatch/aw-watcher-web | Inspect extension permissions and native communication.
OpenAdaptAI/openadapt-desktop | Desktop recording / human teaching | Capture/review UI, local engine, Tauri/React shell, Python sidecar and bridge to record/compile/replay/teach. | Repository explicitly labels the desktop surface experimental and not a supported production release. | End-to-end boundaries are mocked; no validated production installer; flow engine is separate. | MIT verified by repository README/licence. | Study architecture, consent/review and teaching concepts; do not treat as deployable foundation. | 3,11 | https://github.com/OpenAdaptAI/openadapt-desktop | Inspect capture/privacy subprojects and implementation maturity.
OpenAdaptAI/openadapt-flow | Deterministic workflow compiler/runtime | Record → compile → lint/certify → replay → halt/repair/teach lifecycle. | Canonical OpenAdapt workflow engine according to desktop README. | GUI replay is a future Skill Forge capability, not initial work assurance; safety scope is significant. | Verify repository licence before reuse. | Reference for governed workflow compilation and verification. | 11+ | https://github.com/OpenAdaptAI/openadapt-flow | Licence/security review and isolated future spike.
OpenAdaptAI/openadapt-privacy | PII detection and redaction | Experimental privacy component associated with OpenAdapt capture. | Experimental supporting project. | PII/secret redaction quality must be independently evaluated against Nessovo data. | Verify repository licence and model licences. | Benchmark only; Nessovo needs its own edge policy and test corpus. | 3–5 | https://github.com/OpenAdaptAI/openadapt-privacy | Evaluate false negatives and model provenance.
thedotmack/claude-mem | AI-agent persistent memory | Lifecycle hooks, local worker, asynchronous observation compression, SQLite/FTS5, vector search and real-time viewer. | Large active project with documented architecture and multi-environment support. | Claude-centric; memory content and provider dependencies require HumanOS tenant/policy redesign. | Apache-2.0 verified in repository metadata/readme. | Adapt architecture pattern, not necessarily code; integrate official agent hooks into HumanOS memory/evidence. | 6,11 | https://github.com/thedotmack/claude-mem | Security review, provider abstraction and licence provenance.
rebelytics/one-skill-to-rule-them-all | Continuous skill improvement methodology | Structured observations of corrections/gaps, cross-cutting principles, periodic review and human-approved skill changes. | Methodology reports extensive real-world use; compact repository. | Not a recorder or runtime; file-based process is not sufficient for multi-tenant HumanOS. | CC BY 4.0 stated in repository README. | Adapt methodology with attribution into governed Skill Forge. | 11 | https://github.com/rebelytics/one-skill-to-rule-them-all | Preserve attribution; separate confidential/internal skill content.
wakatime/wakatime-cli | Developer activity telemetry | Editor/CLI heartbeat model, project/language metadata and broad plugin ecosystem. | Active Go CLI used by WakaTime integrations. | Developer-tool-only; heartbeat/time telemetry cannot establish task quality or capability. | BSD 3-Clause verified in repository licence. | Reference or optional connector for supported editor metadata. | 6 | https://github.com/wakatime/wakatime-cli | Review privacy and data fields before connector design.
open-telemetry/semantic-conventions | Operational observability standard | Cross-language semantic conventions for traces, metrics and logs. | CNCF/OpenTelemetry standard ecosystem. | Operational telemetry is not the employee evidence store; sensitive content may leak if misconfigured. | Apache-2.0 ecosystem; verify repository licence at incorporation. | Adopt conventions through existing HumanOS observability. | 3+ | https://github.com/open-telemetry/semantic-conventions | Define content policy and correlation IDs.
open-telemetry/semantic-conventions-genai | GenAI observability conventions | GenAI, agent, tool, model and MCP attributes/events. | Active standards work supporting provider-neutral instrumentation. | Does not define Nessovo task/capability/employee semantics; input/output content is sensitive. | Apache-2.0 stated in repository. | Adopt operational semantics and extend with Nessovo evidence references. | 6+ | https://github.com/open-telemetry/semantic-conventions-genai | Pin stable conventions; avoid unrestricted content capture.
cloudevents/spec | Event envelope standard | Portable event metadata and bindings for cross-service/cloud event interchange. | CNCF graduated project and broad ecosystem support. | Envelope does not solve domain schema, ordering, privacy or replay by itself. | Apache-2.0 verified in repository licence. | Adopt CloudEvents-style envelope if compatible with existing HumanOS contracts. | 1,4 | https://github.com/cloudevents/spec | Run compatibility assessment with HumanOS event schemas.
open-policy-agent/opa | Policy-as-code | Decoupled policy decision engine, bundles, decision APIs and audit patterns. | CNCF graduated project with broad ecosystem use. | Not every decision belongs in OPA; endpoint embedding/distribution and decision logs require security design. | Apache-2.0; formal repository verification required before incorporation. | Benchmark for capture/access policy; reuse existing HumanOS policy service first. | 1,3–4 | https://github.com/open-policy-agent/opa | Policy capability matrix and local bundle spike.
temporalio/sdk-java | Durable workflow SDK | Java durable workflows, activities, retries and long-running coordination. | Mature Temporal ecosystem. | Adds another control plane and programming model; may duplicate HumanOS Workflow Runtime. | MIT in Temporal SDK ecosystem; verify repository file before use. | Reference only until HumanOS workflow gaps are documented. | 1,2+ | https://github.com/temporalio/sdk-java | Workflow-runtime capability comparison.
temporalio/sdk-python | Durable workflow SDK | Python workflow/activity support for long-running AI pipelines. | Mature Temporal ecosystem. | Cross-language workflow ownership and duplicate orchestration complexity. | MIT in repository ecosystem; verify before use. | Reference only; Python evaluators should remain workers behind HumanOS orchestration initially. | 1,7+ | https://github.com/temporalio/sdk-python | Use only after architecture decision.

## Gap Matrix
Competitive Gap and Proprietary-Core Matrix
The market provides strong components. Nessovo's defensible product is the governed integration of evidence, task outcomes, provenance, capability development and organisational learning.
Capability | Employee monitoring | Task/process mining | Developer intelligence | Skills/talent intelligence | AI memory / record-replay | Nessovo target | Proprietary importance | MVP / stage | Differentiation and design note
Managed-device session and policy control | Medium | Low | Low | Low | Low | Strong | Medium | 3 | Visible, task/hour/policy-scoped device control is foundational to trust.
Application/window/browser context | Strong | Medium | Medium | Low | Low | Strong | Low | 5–6 | Commodity evidence; use minimum necessary fields and employee visibility.
Event-driven visual-state capture | Strong | Strong | Low | Low | Medium | Strong | Medium | 5 | Changed-state graph, secure exclusions and edge redaction are the value beyond screenshots.
Keyboard/input provenance and resulting text reconciliation | Strong raw keys | Medium | Low/Medium | Low | Medium in agent tools | Controlled strong | High | 5–6 | Distinguish typed, pasted, autocomplete, agent-generated and system-generated changes.
Files, Git, terminal, build and test semantics | Low | Low | Strong | Low | Medium | Strong | Medium | 6 | Prefer authoritative artefacts/results over visual inference.
AI-agent lifecycle and tool instrumentation | Emerging | Low | Strong/emerging | Medium | Strong | Strong | High | 6 | Provider-neutral Adapter Hub plus official hooks and model/skill versioning.
Human / AI / automation causal provenance | Low | Low | Medium | Low | Medium | Strong | Very High | 6–7 | Fair credit, automated-wait classification and agent supervision depend on this.
Task Execution Contract | Low | Medium task definitions | Medium ticket links | Low | Low | Strong | Very High | 2 | Transforms vague tasks into objective, versioned criteria, evidence and quality gates.
Task alignment and supporting-work classification | Medium | Strong for process patterns | Medium | Low | Low | Strong | High | 7 | Must support multiple assigned tasks, research, collaboration and environmental blockers.
Acceptance-criteria and quality verification | Low | Low | Medium | Low | Medium verification in replay | Strong | Very High | 7 | Activity is not completion; deterministic evidence and expert review are essential.
Evidence hierarchy, confidence and alternatives | Low | Low | Medium | Medium | Medium | Strong | Very High | 7–10 | Every material finding exposes sources, uncertainty, missing evidence and alternative explanation.
Employee self-access, correction and dispute | Variable | Low | Low/Medium | Medium | Low | Strong | High | 0,10 | Improves fairness, trust and training data quality.
Meaningful human employment review | Medium controls | Low | Low | Medium | Low | Strong | High | 0,7–10 | Models support decisions; they do not independently determine employment outcomes.
Job-description and capability claim model | Low | Low | Low | Strong | Low | Strong | Very High | 2,8 | Claims remain unverified until repeated, context-qualified evidence exists.
Capability level, confidence, recency and consistency | Low | Low | Low | Strong | Low | Strong | Very High | 2,8 | Transparent multi-dimensional levels rather than opaque talent scores.
Game-like employee progression and mastery paths | Low | Low | Low | Medium | Low | Strong | High | 8–9 | Private developmental skill tree; avoid public leaderboards and activity gaming.
Real-time task coaching | Medium nudges | Low | Medium recommendations | Medium career coaching | Medium | Strong | High | 9 | Observe/nudge/assist/teach/escalate with interruption controls and effectiveness tracking.
Training prescription and applied-learning verification | Low | Low | Low | Strong content/recommendations | Low | Strong | Very High | 9 | Capability increases after demonstrated application, not merely course completion.
Manager exception-led task and capability reporting | Strong activity reports | Strong process reports | Strong engineering reports | Strong talent reports | Low | Strong | Medium/High | 10 | Combine outcome, blocker, quality, support and employee response; raw evidence is drill-down.
Reusable work-method and skill extraction | Low | Medium automation discovery | Medium playbooks | Medium learning paths | Strong | Strong | Very High | 11 | Convert validated success/corrections into versioned HumanOS skills and standards.
Governed skill/evaluator self-improvement | Low | Low | Low | Emerging | Medium/Strong | Strong | Very High | 11 | Proposal → evaluation → review → canary → promotion/rollback; no uncontrolled self-modification.
Cross-vertical HumanOS extension model | Low | Medium | Low | Medium | Low | Strong | High | 2+ | Domain-neutral core plus vertical evidence adapters, task rubrics, coaching and policy packs.
Edge minimisation, secure-field blocking and local redaction | Variable/strong in security products | Medium | Low | Low | Medium | Strong | High | 3–5 | Pilot-blocking privacy engineering and major trust differentiator.
Employee and manager benefit measurement | Medium employer-centric | Medium | Strong team metrics | Strong talent metrics | Low | Strong | High | 0,12 | Product only succeeds when both task outcomes and employee development measurably improve.

## Delivery Stages
Delivery Stages
13 stages total. Stage 0 and Stage 1 are one Foundation & Validation workstream with separate approval gates; schedules are planning assumptions rather than delivery commitments.
Stage # | Stage | Objective | Duration weeks | Indicative team size | Dependencies | Exit deliverables | Lead role | Current state | Priority | Risk | Start date | End date | Effort PW
0 | Foundation — charter, governance and legal boundary | Define purpose, permitted/prohibited uses, lawful and ethical boundaries, employee rights, DPIA inputs, consultation, security principles, pilot protection and decision authority. | 2 | 8 | None | Product Charter v1; Purpose Policy Matrix; RACI; DPIA pack; threat model; pilot definition; Stage 0 gate. | Executive Sponsor / Product / DPO | Draft Complete — Gate Pending | Critical | High | 2026-07-20 | 2026-08-02 | 16
1 | Foundation — market validation and reference architecture | Validate market/OSS landscape; decide build/buy/integrate/defer; define HumanOS reference architecture, ADRs, technical spikes, licences, costs and resource conditions. | 2 | 10 | Stage 0 workstream runs in parallel; Stage 0 approval is required for implementation use | Market/OSS research; Gap Matrix; Build/Buy decisions; Reference Architecture; ADRs; Stage 1 gate; Stage 2/3 prompts. | CTO / Architecture / Product | Draft Complete — Gate Pending | Critical | High | 2026-07-20 | 2026-08-02 | 20
2 | Role capability and task contract ontology | Create domain-neutral Role Capability Contract, Task Execution Contract, evidence ontology, rubrics and implementation contracts, with software-development examples. | 3 | 7 | Conditional Stage 0 and Stage 1 approval | Schemas, rubrics, example roles/tasks, APIs/events, evaluator rules, backlog and Stage 2 gate. | Product / Capability / AI / Domain Experts | Not Started — Prompt Ready | Critical | High | 2026-08-17 | 2026-09-06 | 21
3 | Device agent foundation | Build signed Windows/macOS agent skeleton, device identity, policy sync, visible session control, encrypted journal, update/rollback and spike framework. | 5 | 8 | Conditional Stage 0 and Stage 1 approval | Installable agent skeleton; registration; signed policy; session state machine; local journal; health/update; test and threat evidence. | Desktop / Platform / Security | Not Started — Prompt Ready | Critical | High | 2026-09-07 | 2026-10-11 | 40
4 | Telemetry ingestion and evidence storage | Implement signed batch ingestion, schema governance, event bus, object evidence storage, audit linkage and replay APIs. | 4 | 7 | Stage 3 foundation and approved event contracts | Idempotent ingestion; schema registry; event topics; evidence/object storage; access and audit controls. | Backend / Data / Platform | Not Started | Critical | High | 2026-10-12 | 2026-11-08 | 28
5 | Universal capture MVP | Capture approved application/window, visual-state, input metadata/text delta, idle, process and file evidence with local exclusions and redaction. | 6 | 9 | Stages 3 and 4; DPIA and pilot control approval | Correlated endpoint timeline; secure-field blocking; visual-state graph; edge redaction; performance and privacy tests. | Desktop / Data / Security | Not Started | Critical | High | 2026-11-09 | 2026-12-20 | 54
6 | Development semantics and AI-agent adapters | Add browser, terminal, Git, tests/builds, Codex, Claude Code, IDE and toolchain adapters. | 6 | 9 | Stage 5 | Normalised agent/tool events; terminal/process semantics; Git/test/build evidence; adapter SDK. | Integrations / AI / Developer Platform | Not Started | High | High | 2026-12-21 | 2027-01-31 | 54
7 | Provenance and Task Assurance Engine | Build work episodes, task alignment, human/AI/automation causal graph, acceptance-criteria and quality evaluation. | 7 | 10 | Stages 2 and 6 | Evidence/provenance graph; task assessments; criterion state; confidence calibration; blocker detection; human review. | AI / Backend / Product | Not Started | Critical | High | 2027-02-01 | 2027-03-21 | 70
8 | Capability Graph and baseline assessment | Map role requirements and employee claims to repeated, context-qualified capability evidence and role readiness. | 5 | 8 | Stages 2 and 7 | Capability service; baseline assessment; claim-evidence discrepancy workflow; fairness/evidence tests. | Capability / HR / AI / Backend | Not Started | High | High | 2027-03-22 | 2027-04-25 | 40
9 | Growth Coach and learning loop | Provide controlled observe/nudge/assist/teach/escalate interventions, training plans and effectiveness measurement. | 5 | 8 | Stages 7 and 8 | Coaching orchestration; learning plans; mentor escalation; intervention safety; applied-learning evidence. | AI / L&D / Product | Not Started | High | Medium | 2027-04-26 | 2027-05-30 | 40
10 | Employee and manager experiences | Deliver employee timeline/corrections/capability view and manager exception-led task/capability reports. | 5 | 9 | Stages 7–9 and governance workflow | Employee portal; dispute/review workflow; manager task assurance; access controls; usability evidence. | Product / Frontend / Backend / Governance | Not Started | High | High | 2027-05-31 | 2027-07-04 | 45
11 | Skill Forge and governed self-improvement | Create observation-to-skill/evaluator improvement with evaluation, approval, canary, promotion and rollback. | 6 | 8 | Stages 9 and 10 | Skill registry; proposal/evaluation pipeline; confidentiality controls; approval/canary/rollback. | AI Platform / Governance | Not Started | High | High | 2027-07-05 | 2027-08-15 | 48
12 | Security hardening, internal pilot and rollout decision | Complete penetration/privacy/performance/evaluation testing, controlled pilot, evidence review, cost analysis and proceed/modify/restrict/stop decision. | 8 | 12 | Stages 0–11 and all pilot approvals | Pilot report; legal/DPO/security sign-off; employee/manager evidence; cost and launch-readiness decision. | Executive Sponsor / CTO / DPO / CISO / Product | Not Started | Critical | High | 2027-08-16 | 2027-10-10 | 96

## Microservices Map
Microservices and Deployment Map
Initial physical deployment plan. Logical bounded contexts can be separated later, but a new deployable requires a demonstrated security, scale, availability, ownership or transactional boundary.
Deployable / component | Includes bounded contexts | Primary responsibility | Primary runtime | Primary stores | Consumes / integrates | Publishes / exposes | HumanOS foundation reuse | Initial stage | Future split trigger | Owner / note
Endpoint Device Agent | Native core; Windows bridge; macOS bridge; local policy; session control; encrypted journal; uploader; health/update; adapter SDK. | Visible, policy-controlled endpoint evidence collection, local minimisation/redaction, offline durability and signed event batching. | Rust shared core + Swift + Windows native bridge + TypeScript browser extension | Encrypted SQLite/SQLCipher-style journal and content-addressed local cache | Device policy, HumanOS session/task context, OS/application/agent adapters | Signed event batches, device health, policy status, telemetry gaps | Device identity, policy, secrets, audit, notification | 3–6 | OS-specific components may become separate packages, not necessarily cloud services. | Desktop Platform
Deployable 1 — Device Control & Policy Gateway | Device registry; certificate lifecycle; policy distribution; session command/control; update rollout metadata; agent health. | Cloud control plane for managed devices and capture policy. | Java + Spring Boot | PostgreSQL | IAM, organisation, device attestation/MDM, policy service, secrets/KMS | Registration/session/policy/update APIs and device events | Identity, organisation, policy, secrets, audit, notification, API gateway | 3–4 | Split update service or fleet health if endpoint scale/ownership demands it. | Platform / Security
Deployable 2 — Telemetry Ingestion & Schema | Batch gateway; signature validation; idempotency; tenant partitioning; schema registry integration; quotas; reject/diagnostics. | Receive signed endpoint/adapter batches and publish normalised, replayable events. | Java + Spring Boot + Spring Kafka | Kafka-compatible bus + PostgreSQL ingestion metadata | Device certificates, tenant/IAM, schema registry, event bus | Normalised event topics, batch receipts, telemetry gap and rejection events | IAM, event infrastructure, audit, API gateway | 4 | Scale ingress independently by region or workload when measured. | Backend / Data Platform
Deployable 3 — Evidence & Timeline | Activity events; visual-state metadata; artefact references; relational provenance edges; retention; timeline/replay; evidence access. | System of record for work evidence metadata and evidence-linked timelines. | Java + Spring Boot | PostgreSQL + object storage; search indexes as needed | Normalised events, task/project context, file/Git/test/agent events, policy decisions | Evidence/timeline APIs; evidence.linked and provenance.updated events | Object/file service, policy, audit, IAM, tenant | 4–7 | Split visual/object indexing if retention/security/throughput becomes independent. | Data / Evidence
Deployable 4A — Task Assurance Domain | Task contract state; acceptance criteria; deterministic validators; assessment workflow; blocker and task-alignment state. | Own durable task-assurance lifecycle and orchestrate evaluators and human review. | Java + Spring Boot | PostgreSQL | HumanOS tasks/projects/workflow, evidence, build/test/CI, reviewer decisions | Task assessment/criterion/blocker APIs and events | Task/project service, workflow, policy, audit, notification | 2,7 | Separate task-contract compiler or validator workers only after independent scale/ownership. | Product / Backend
Deployable 4B — Task & Activity Evaluators | Episode segmentation; task alignment; visual/text interpretation; quality reasoning; confidence calibration; evaluation harness. | Return versioned, evidence-linked AI findings without owning final employment or task state. | Python + FastAPI/worker runtime | Evaluation/model artefact store + approved vector/search index | Evidence references and minimised approved content through Model Gateway | Evaluator findings, confidence, missing evidence and model/skill metadata | Model Gateway, policy, audit, secrets, observability | 7 | Separate model-specific worker pools based on compute/security class. | AI / Evaluation
Deployable 5A — Capability & Learning Domain | Role capability contracts; claims; evidence state; role readiness; learning plans; intervention workflow; employee capability view. | Own transparent capability and learning lifecycle across HumanOS verticals. | Java + Spring Boot | PostgreSQL | Organisation/roles, task assessments, baseline assessments, training outcomes, review decisions | Capability evidence/state, gap, learning and role-readiness APIs/events | Organisation/role, workflow, HR integrations, policy, audit, notification | 2,8–9 | Split learning marketplace/content integration if volume and ownership justify. | Capability Product / L&D
Deployable 5B — Capability Scoring & Coaching AI | Evidence weighting; confidence/recency/consistency; gap classification; coaching generation; training recommendations; effectiveness evaluation. | Provide explainable recommendations to the durable Capability & Learning domain. | Python + FastAPI/worker runtime | Evaluation store + approved skill/content index | Qualified capability evidence, task context, employee request and approved learning content | Scoring/coaching recommendations with explanations and version metadata | Model Gateway, policy, audit, workflow | 8–9 | Separate coaching latency path from batch capability scoring if required. | AI / L&D
Deployable 6 — AI Adapter & Memory Hub | Codex/Claude/IDE agent adapters; provider-normalised lifecycle; prompt/tool observation; approved session memory; model/evaluation routing extensions. | Connect AI work surfaces to HumanOS evidence and provide provider-neutral agent provenance. | Python adapters + Java API/orchestration; extend existing HumanOS Model Gateway | PostgreSQL metadata + approved search/vector index | Official agent hooks, MCP/tool events, Model Gateway, evidence/task context | Normalised agent events, memory/search APIs and AI audit | Model Gateway, secrets, policy, audit, event bus | 6,11 | Split provider adapters or memory service when scale/security/ownership demands it. | AI Platform / Integrations
Deployable 7 — Governance & Human Review | Employee evidence access; corrections; disputes; manager raw-evidence requests; human review; policy/decision reasons; consequential-decision safeguards. | Operationalise employee rights and meaningful human review before assessments are used. | Java + Spring Boot | PostgreSQL + immutable audit references | Assessment/dispute/access requests, identity/organisation, workflow and policy | Review/correction/access decision APIs and events | Workflow Runtime, IAM, policy, audit, notification | 0,7–10 | Split access-control admin from review case management only if security ownership differs. | Governance / HR / DPO
Deployable 8 — Reporting & Analytics | Employee timeline read model; manager task assurance; capability views; pilot KPI; team/process and executive reporting. | Deliver role-appropriate, exception-led views without making raw evidence the default experience. | Java APIs + frontend/BI; Python/SQL analytics where justified | PostgreSQL read models; warehouse/lakehouse later | Task, capability, review, workflow and aggregated evidence events | Reports, dashboards, exports and analytics APIs | IAM, organisation, audit, notification, existing analytics platform | 10 | Separate analytics pipeline/warehouse after data-volume and governance proof. | Product Analytics
Skill Forge Module — initially inside AI Platform | Skill observation; proposal generation; version registry; evaluation suites; approvals; canary; promotion/rollback; confidentiality classification. | Improve HumanOS skills, prompts, adapters and evaluators through governed evidence and feedback. | Java lifecycle + Python generation/evaluation | PostgreSQL + Git/artifact/evaluation stores | User corrections, successful patterns, model/evaluator feedback, research candidates | Skill proposal/version/deployment events | Workflow, Model Gateway, policy, audit, secrets, notification | 11 | Become an independent deployable when cross-HumanOS usage and ownership justify it. | AI Platform / Governance
Shared HumanOS — Identity & Organisation | Identity, tenant, person, team, manager, role assignment and service authentication. | Remain authoritative for people, organisations and access context. | Existing Java/Spring services | Existing HumanOS stores | Corporate identity/HR integrations | Tokens, claims and organisation/role events | Authoritative foundation | All | Do not duplicate in Work Intelligence. | HumanOS Platform
Shared HumanOS — Projects, Tasks & Plans | Projects, assigned tasks, daily plans, status, deadlines and integration adapters. | Remain authoritative for assigned work; Task Assurance compiles/evaluates contracts but does not replace task ownership. | Existing Java/Spring services | Existing HumanOS stores | HumanOS/project-management integrations | Task/project APIs and events | Authoritative foundation | 2+ | Extend only where Task Execution Contract linkage is missing. | HumanOS Product Platform
Shared HumanOS — Workflow Runtime | Long-running review, dispute, coaching, approval, escalation and Skill Forge workflows. | Provide deterministic orchestration and human tasks. | Existing HumanOS workflow runtime | Existing workflow state | Domain events/commands | Workflow states/actions/events | Authoritative foundation | 0+ | Evaluate Temporal/alternative only after documented capability gaps. | HumanOS Platform
Shared HumanOS — Policy, Audit, Secrets & Object | Policy decisions; immutable audit; device/service/evidence keys; evidence objects; regional storage; retention and access tokens. | Provide shared control-plane and evidence infrastructure. | Existing HumanOS services; evaluate OPA where valuable | Policy repo, audit store, KMS/HSM, S3-compatible storage | All Work Intelligence services | Decisions, audit records, object references and security events | Authoritative foundation | 0+ | Evidence-specific extensions require architecture review, not duplicated foundations. | Security / Platform
Shared HumanOS — Event, API & Observability Platform | Kafka-compatible event bus; schema registry; API gateway; service mesh/mTLS; OpenTelemetry; deployment/feature flags. | Provide cross-service contracts, security, operations and regional deployment. | Existing HumanOS platform | Kafka/schema/telemetry/platform stores | All services and agents | Events, APIs, traces/metrics/logs and deployments | Authoritative foundation | 1+ | Operational telemetry must not become the raw employee-evidence store. | Platform / SRE

## MVP Backlog
MVP Backlog
Initial epics and features for the controlled internal pilot.
Epic ID | Epic | Feature / user story | Stage | Owner | Priority | Status | Effort pts | Acceptance criteria | Dependencies | Notes
E01 | Work session control | Employee can start/pause/stop a monitored work session against a HumanOS task. | 3 | Desktop/Backend | Critical | Not Started | 8 | Session event exists; visible status; offline buffering; task ID linked. | Device Agent Gateway | No hidden mode.
E02 | Policy sync | Agent receives tenant/jurisdiction/capture policy before recording. | 3 | Platform/Security | Critical | Not Started | 8 | Policy signature verified; excluded apps/domains applied; audit emitted. | Policy Service | Policy version visible.
E03 | App/window telemetry | Capture foreground app, process, window title and transitions. | 5 | Desktop | Critical | Not Started | 5 | 99% foreground app transition capture in pilot. | Agent foundation
E04 | Click + visual state | Capture mouse click with pre/post visual states and changed region. | 5 | Desktop/AI | Critical | Not Started | 13 | 98% click-to-state correlation in supported pilot apps. | Visual Evidence Store
E05 | Text-state capture | Reconcile physical input, text deltas and resulting artefact changes in approved controls. | 5 | Desktop/Data | Critical | Not Started | 21 | 95% reconstruction in supported controls; zero secure-field leakage. | Policy / UI accessibility | Avoid raw keylogger-only logic.
E06 | File/process telemetry | Capture process tree, file create/modify/delete and build/test process markers. | 5 | Desktop/Data | High | Not Started | 13 | Event causal chain links process -> file/test output. | ETW/macOS process bridge
E07 | Browser adapter | Capture active tab, title, approved URL/domain, navigation and visible page event. | 6 | Integrations | High | Not Started | 8 | Chrome/Edge MV3 extension sends normalized events. | Native messaging
E08 | Terminal adapter | Capture command, cwd, exit code, stdout/stderr summary and process duration. | 6 | Integrations | High | Not Started | 13 | Command event links to resulting processes and files. | Shell/PTTY hooks
E09 | Git adapter | Capture branch, diff summary, commit, PR, changed files and reviewer state. | 6 | Integrations | High | Not Started | 8 | Git diff/commit events linked to task and actor. | GitHub/GitLab connectors
E10 | Codex adapter | Capture Codex prompt/tool/permission/stop lifecycle via hooks. | 6 | AI Integrations | Critical | Not Started | 8 | Agent events mapped to OTel-style spans and provenance graph. | Codex hooks
E11 | Claude Code adapter | Capture Claude Code usage through hooks/OTel/MCP where available. | 6 | AI Integrations | High | Not Started | 8 | Prompt/tool/file/command events normalized. | Claude Code config
E12 | Episode segmentation | Group raw events into meaningful 30-180 second work episodes. | 7 | AI/Data | Critical | Not Started | 21 | Episodes align with human review >=90% in pilot sample. | Evidence graph
E13 | Task alignment classifier | Classify episodes as on-task, supporting, blocked, automated-wait, idle, unrelated. | 7 | AI | Critical | Not Started | 21 | False idle below 5%; confidence calibrated. | Task contracts
E14 | Acceptance criteria validator | Determine task completion evidence and missing verification. | 7 | AI/Product | Critical | Not Started | 21 | Every criterion has evidence, status and confidence. | Task contract
E15 | Capability graph MVP | Create role capability profile and update capability evidence after assessed tasks. | 8 | AI/Backend | High | Not Started | 13 | Capability level, confidence, recency and evidence visible. | Role ontology
E16 | Growth coach MVP | Generate non-disruptive guidance when task risk or capability gap is detected. | 9 | AI/L&D | High | Not Started | 13 | Nudge/assist/teach messages audited; employee can dismiss/correct. | Task intelligence
E17 | Employee portal | Employee can see timeline, report, capability profile and dispute findings. | 10 | Frontend | Critical | Not Started | 13 | Dispute creates review workflow; employee evidence visible. | Reporting/Governance
E18 | Manager console | Lead sees exception-led task report, blockers, quality gaps and training recommendations. | 10 | Frontend/Product | Critical | Not Started | 13 | Manager report cites evidence and confidence. | Task/capability services
E19 | Skill observation log | System logs user/system corrections as candidate skill improvements. | 11 | AI Platform | Medium | Not Started | 8 | Observation includes issue, improvement, principle, evidence and confidentiality class. | Skill Forge
E20 | Pilot validation | Run internal pilot and measure capture accuracy, task alignment, worker trust and manager value. | 12 | Leadership/QA | Critical | Not Started | 21 | Pilot report with acceptance metrics and rollout decision. | All MVP epics

## Event Data Model
Event & Data Model
Core evidence graph, events, entities and provenance relationships.
Model area | Entity/Event | Purpose | Key fields | Producer | Consumer | MVP | Notes | Source/ref
Entity | WorkSession | Tracks a monitored work period and task linkage. | session_id, person_id, device_id, task_id, start/end, policy_version | Device Agent Gateway | Task Intelligence, Reporting | Yes | Supports pause/private/excluded segments.
Entity | TaskExecutionContract | Structured task expectations and acceptance criteria. | objective, criteria, evidence_required, tools, risks, reviewer | Task Intelligence | Task Assurance, Coach | Yes | Compiled from HumanOS task.
Entity | RoleCapabilityContract | Structured role/job description capability requirements. | role, level, capabilities, evidence rubrics, autonomy | Role & Capability | Capability Graph | Yes | Job description becomes measurable contract.
Event | activity.application.changed | Foreground app/window/process transition. | app, pid, window_title, timestamp, confidence | Desktop Agent | Evidence Service | Yes | Universal capture stream.
Event | activity.input.observed | Physical mouse/keyboard input metadata. | input_type, key/button, coordinate, injected_flag, secure_field | Desktop Agent | Evidence Service | Yes | Text stored separately and controlled. | Microsoft SetWindowsHookEx
Event | activity.visual.changed | Visual state changed due to click/app/action. | before_state, after_state, changed_region, screenshot_hash | Desktop Agent | Evidence Service | Yes | Event-driven capture, not brute-force video.
Event | activity.text.changed | Resulting text delta in an approved control/editor. | inserted_ref, deleted_ref, source_control, privacy_class | Desktop Agent/IDE Adapter | Evidence, Task Intelligence | Yes | Authoritative text-state > raw keys.
Event | agent.prompt.submitted | Prompt sent to Codex/Claude/Cursor/etc. | agent, prompt_ref, task_id, turn_id | AI Agent Adapter | Provenance, Coach | Yes | Use official hooks where possible. | Codex hooks
Event | agent.tool.completed | Agent tool command or file operation completed. | tool, input_ref, output_ref, exit_code, files_touched | AI Agent Adapter | Provenance | Yes | Causal parent is prompt or prior tool call. | OpenTelemetry GenAI
Event | process.completed | System command/build/test process ended. | command_ref, cwd, exit_code, duration, stdout_ref | Terminal/OS Adapter | Task Assurance | Yes | Distinguish automated wait from idle.
Event | task.criterion.verified | Task criterion satisfied or failed with evidence. | criterion_id, status, evidence_refs, confidence | Task Intelligence | Reporting/Capability | Yes | Outcome-driven assessment.
Event | capability.evidence.recorded | Capability evidence gained from a task episode. | capability_id, level_signal, confidence, evidence_refs | Role & Capability | Learning/Reporting | Yes | Repeated evidence updates profile.
Event | skill.observation.created | Candidate improvement to HumanOS skill/plugin/evaluator. | issue, improvement, principle, evidence_refs, confidentiality | Skill Forge | Skill Review | Later | Human approval before activation.

## AI Capability System
AI Capability System
How Nessovo verifies capability, improves employees, and improves HumanOS itself.
Level | Name | Meaning | Evidence examples | Manager interpretation | Employee experience
0 | Unverified | Claim exists but no reliable evidence yet. | Onboarding claim, CV, self-assessment. | Do not assume capability; assign baseline tasks. | Skill locked or greyed out.
1 | Learning | Requires direct instruction and close guidance. | Fails routine tasks without support; training in progress. | Needs guided work and mentor review. | Starter quests and basic lessons.
2 | Assisted | Can complete routine work with support. | Completes tasks when guided; recurring review required. | Suitable for scoped tasks. | Progress quests and coaching.
3 | Independent | Reliably completes standard work independently. | Multiple successful tasks with appropriate verification. | Meets normal role requirement. | Core skill unlocked.
4 | Advanced | Handles complex/non-routine work and supports others. | Solves unfamiliar variants; mentors peers; improves playbooks. | Can own complex workstreams. | Advanced challenges and mentor badges.
5 | Mastery | Defines standards, solves novel problems and coaches others. | Creates reusable methods; reviews designs; leads standards. | Can define organisational practice. | Mastery status and skill authoring.
Loop | Input | AI action | Human control | Output
Employee learning loop | Task evidence, errors, coaching response | Detect gap and recommend training/practice | Employee can challenge; manager/mentor reviews | Capability evidence and learning plan
Task assurance loop | Task contract, activity episodes, artefacts | Assess task alignment, progress, quality and completion | Lead/reviewer decides status | Evidence-backed task report
Organisational learning loop | Repeated successful work patterns | Propose playbooks/templates/workflows | Domain expert approves | HumanOS workflow / standard method
Skill Forge loop | User correction, evaluator failure, new research | Propose skill/plugin/evaluator update | Skill reviewer, tests, canary, rollback | Versioned HumanOS skill
Evaluator | Purpose | Runtime | Inputs | Outputs | MVP
Task alignment classifier | Classify episode relative to assigned task. | Python | Episode, task contract, app context, artefacts | classification + confidence + evidence refs | Yes
Provenance classifier | Classify human/AI/automation/system actor. | Python + rules | Input events, agent hooks, process tree, file deltas | actor + confidence + causal edge | Yes
Acceptance criteria verifier | Determine criterion status and missing evidence. | Python + deterministic validators | Task contract, artefacts, tests, screenshots, reports | met/partial/missing + evidence | Yes
Capability updater | Update capability confidence and level from evidence. | Python scoring + Java persistence | Task assessment, difficulty, independence, guidance | capability signal + level update proposal | Yes
Coaching selector | Choose whether/how to intervene. | Python | Risk, confidence, history, user preferences | nudge/assist/teach/escalate/observe | Yes
Skill improvement evaluator | Test proposed skill/plugin changes. | Python | Observation, skill diff, test corpus, policy constraints | pass/fail/regression/risk report | Later

## Governance
Governance and Compliance Control Baseline
Minimum Stage 0 controls. This workbook defines the requirements; legal, DPO, security, HR and worker-consultation approvals remain necessary before an employee pilot.
Control ID | Control area | Mandatory requirement | Implementation direction | Accountable owner | Pilot blocking | Required evidence | Control status | Primary risk reduced | Source / note
GOV-001 | Purpose and necessity | Every collected or derived data category has a specific approved purpose, necessity analysis and less-intrusive alternative assessment. | Purpose Policy Matrix, policy identifiers in events, periodic DPO review. | DPO / Product | Yes | Approved matrix and DPIA. | Draft Ready | Excessive or repurposed surveillance. | ICO monitoring guidance.
GOV-002 | Transparency | Workers understand what is captured, when, why, who can see it, retention, automated analysis and rights. | Clear privacy notice, monitoring policy, onboarding, visible endpoint status and policy version. | DPO / HR / Legal | Yes | Approved notice/policy and acknowledgement record. | Draft Ready | Unfair/opaque processing and trust failure. | GOV.UK / ICO.
GOV-003 | Worker consultation | Affected workers or representatives are consulted before design is frozen and before material policy changes. | Consultation plan, facilitated sessions, issue log, Nessovo response and change record. | HR / DPO | Yes | Consultation record. | Not Started | Lack of worker voice and undiscovered harms. | ICO and UK consultation direction.
GOV-004 | DPIA | High-risk monitoring and employment AI receive a completed DPIA and recorded DPO advice before pilot. | Governance workflow, risk register, mitigation owners, residual-risk acceptance and review date. | DPO | Yes | Completed DPIA and advice. | Not Started | Regulatory and employee harm. | ICO.
GOV-005 | Jurisdiction review | UK and Pakistan/Lahore deployments have separate legal and employment assessments; EU customer deployment receives AI Act/GDPR analysis. | Jurisdiction policy packs, data-flow maps, contractual safeguards and deployment flags. | Legal / DPO | Yes | Legal memoranda and approved policy packs. | Owner Input | Cross-border and local-law non-compliance. | Local counsel required.
GOV-006 | No covert general monitoring | The product has no routine hidden mode; any exceptional investigation is separate, specific, time-limited and legally authorised. | Visible status, signed policy, restricted investigation workflow outside normal product operation. | Legal / DPO / CISO | Yes | Product test and policy approval. | Draft Ready | Unlawful covert surveillance. | GOV.UK.
GOV-007 | Secure-field and secret blocking | Passwords, authentication codes, known secure fields and detected secrets are suppressed before durable storage or upload. | OS secure-control detection, local secret scanning/redaction, exclusion policy, zero-retention suppression event. | CISO / Desktop | Yes | Adversarial leakage test with zero known-secret retention. | Draft Ready | Credential/IP/data breach. | Privacy engineering requirement.
GOV-008 | Application/domain/hour exclusions | Personal/sensitive apps, domains, monitors and out-of-policy hours cannot be captured. | Signed local policy, employee-visible exclusions, fail-safe behaviour and audit. | DPO / HR / Security | Yes | Policy tests and endpoint audit. | Draft Ready | Private-life and special-category exposure. | Purpose Policy Matrix.
GOV-009 | Edge minimisation | Deduplication, event-driven capture, changed regions, redaction and aggregation occur locally wherever feasible. | Native agent pipeline and privacy budget. | CISO / DPO / Desktop | Yes | Data-flow and benchmark evidence. | Draft Ready | Data concentration and cost.
GOV-010 | Raw evidence access | Raw screenshots/text/keystrokes are not default manager content and require role, purpose, task, time and audit authorisation. | Summary-first UX, purpose codes, ABAC/policy decisions, JIT access and immutable access log. | Security / DPO / HR | Yes | Access-control tests and audit review. | Draft Ready | Manager/insider misuse.
GOV-011 | Employee access and correction | Employees can view material evidence and assessments, correct task attribution/context and add explanations. | Employee portal and correction workflow preserving original/corrected lineage. | Product / DPO | Yes | UX test and correction audit. | Draft Ready | False or incomplete conclusions. | ICO accuracy/challenge.
GOV-012 | Dispute and human review | Employees can request review; qualified reviewers consider context and can reject AI findings. | Workflow SLA, reviewer qualifications, evidence package, reasoned decision and override logging. | HR / Legal / DPO | Yes | End-to-end review test. | Draft Ready | Rubber-stamped automated decisions. | ICO human review.
GOV-013 | Consequential decisions | No solely automated dismissal, discipline, pay, promotion, probation or equivalent decision. | Policy and workflow block final decision state without authorised human decision and supporting evidence. | HR / Legal | Yes | Decision audit and policy test. | Draft Ready | Employment harm and automated-decision breach.
GOV-014 | Evidence hierarchy | Authoritative system outcomes and artefacts outrank tool, OS, accessibility, visual and AI inference evidence. | Typed evidence classes and evaluator rules. | Product / Data / AI | Yes | Evaluation tests and report explainability. | Draft Ready | Screenshot/AI narrative overriding facts.
GOV-015 | Confidence and uncertainty | Material AI findings include confidence, evidence, missing evidence, alternative explanation, model/skill version and review status. | Evaluator output schema and report UI. | AI Governance | Yes | Calibration/evidence-grounding test. | Draft Ready | Overconfident false allegation. | NIST AI RMF.
GOV-016 | Prohibited inference | No emotion, personality, honesty, protected-trait, health or mental-state inference from computer activity. | Model-policy deny list, prompt/evaluator tests and review. | AI Governance / DPO | Yes | Prohibited-output red-team results. | Draft Ready | Discriminatory or unlawful inference. | EU employment AI risk context.
GOV-017 | Outcome over activity | Clicks, keys, code volume and hours are not used as standalone productivity or capability scores. | Metric-policy rules and report tests. | Product / HR | Yes | KPI/report review. | Draft Ready | Gaming and unfair management.
GOV-018 | Capability evidence | Capability levels require repeated, context-qualified evidence, independence and quality; one task cannot establish dishonesty or permanent incapability. | Stage 2 ontology, evidence thresholds, contradiction/recency and human review. | Capability Lead / HR | Yes before capability pilot | Ontology/evaluation/fairness tests. | Draft Ready | Career harm and deceptive labels.
GOV-019 | Training use | Detected gaps first support explanation, coaching, training and reassessment; training completion alone does not increase capability. | Learning workflow and applied-evidence rule. | HR / L&D / Product | No for capture pilot; yes for capability use | Learning effectiveness design. | Draft Ready | Punitive or performative learning.
GOV-020 | Retention and deletion | Raw evidence has short purpose-based retention; derived records have justified retention, deletion, export and legal-hold controls. | Per-class retention policy, object lifecycle, deletion verification and employee request workflow. | DPO / Data Governance | Yes | Approved schedule and deletion tests. | Owner Input | Data concentration and over-retention.
GOV-021 | Model/provider governance | Employee evidence only uses approved Model Gateway routes, contracts and regional/private processing appropriate to its classification. | Provider allowlist, no-training/retention terms, egress controls and model audit. | AI Platform / CISO / Legal | Yes | Provider contracts and egress tests. | Owner Input | Third-party retention/training/exposure.
GOV-022 | Prompt injection and tool safety | Observed content is untrusted data; evaluators and coaches cannot expand privileges or follow embedded instructions. | Prompt isolation, tool restrictions, retrieval allowlists, output validation and adversarial tests. | AI Security | Yes before AI pilot | Indirect-injection benchmark. | Draft Ready | Model manipulation and data exfiltration.
GOV-023 | Auditability | Evidence access, policy decisions, AI findings, human reviews, corrections and skill changes are immutably auditable. | Existing HumanOS audit extension and correlation identifiers. | CISO / Audit | Yes | Audit coverage test. | Draft Ready | Undetectable misuse or unaccountable decisions.
GOV-024 | Skill/evaluator governance | System improvements are proposals until evaluation, expert/security review, canary and rollback; confidential data is not leaked into reusable skills. | Skill Forge lifecycle, signed versions, eval suites, internal/open classification and deployment gates. | AI Platform / Governance | Yes before Stage 11 production | Regression and confidentiality tests. | Draft Ready | Unsafe self-modification and IP leakage. | Task Observer/Claude-Mem patterns.
GOV-025 | Pilot participant protection | Pilot outputs are developmental/evaluative and cannot solely or primarily create adverse employment action. | Participant terms, system labels, manager training, review and audit. | Executive Sponsor / HR | Yes | Approved protocol and decision audit. | Draft Ready | Unvalidated pilot harm.
GOV-026 | Incident and stop control | DPO, CISO and executive sponsor can pause affected capture or the pilot when blocking criteria occur. | Agent disable, feature flags, containment, notification, evidence preservation and decision log. | CISO / DPO / Executive Sponsor | Yes | Incident exercise. | Draft Ready | Continued harmful processing.

## Risk Register
Programme Risk Register
Leadership-level risks. The Foundation Threats sheet contains the deeper scenario/control model. Scores use 1–5 likelihood and impact.
Risk ID | Risk | Category | Likelihood | Impact | Inherent score | Primary mitigation | Accountable owner | Relevant stage | Status | Residual target | Trigger / escalation
R-001 | Employees experience the product as punitive surveillance, reducing trust, retention and data quality. | Trust / Adoption | 4 | 5 | 20 | Employee value proposition; worker consultation; own evidence/corrections; pilot protection; no activity scores; manager training. | Executive Sponsor / HR / Product | 0–12 | Open | 8 | Material negative trust shift, high opt-out/complaint rate or repeated manager misuse.
R-002 | Passwords, secrets, customer data or private content are retained or uploaded. | Privacy / Security | 4 | 5 | 20 | Secure-field blocking; exclusions; local redaction; short retention; DLP tests; emergency stop. | CISO / DPO / Desktop | 0,3–12 | Open | 5 | Any known secret or unauthorised private-content retention is pilot blocking.
R-003 | AI task/idle/capability finding is wrong and harms an employee. | AI / Employment | 4 | 5 | 20 | Evidence hierarchy; confidence; alternatives; employee correction; qualified human review; no solely automated consequential decision. | AI Governance / HR / DPO | 0,7–12 | Open | 8 | High-confidence unsupported allegation, material dispute overturn or subgroup error.
R-004 | Legal basis, employment documentation or local monitoring requirements are unresolved. | Legal / Regulatory | 3 | 5 | 15 | Full DPIA; UK and Pakistan counsel; policy/notice; consultation; jurisdiction packs; controlled pilot. | Legal / DPO | 0–12 | Open | 5 | Counsel/DPO advises hold or residual high risk is unaccepted.
R-005 | Managers or administrators misuse raw evidence outside an approved purpose. | Governance / Insider | 3 | 5 | 15 | Summary-first UX; purpose/task/time access; JIT approval; separation of duties; immutable access audit and sanctions. | CISO / HR / DPO | 0,10–12 | Open | 6 | Unauthorised access, repeated curiosity browsing or unreviewed live surveillance.
R-006 | Device agent introduces unacceptable latency, CPU, memory, battery or stability impact. | Endpoint / Technical | 4 | 4 | 16 | Native/event-driven design; adaptive throttling; performance budgets; application compatibility matrix; kill switch. | Desktop Lead / SRE | 3–12 | Open | 6 | Perceptible input latency, typical CPU above target or critical app instability.
R-007 | Endpoint agent or update channel becomes a high-privilege compromise path. | Security / Supply Chain | 3 | 5 | 15 | Least privilege; signing/notarisation; SBOM; dependency scanning; staged updates; attestation; rollback; signing-key controls. | CISO / DevSecOps / Desktop | 3–12 | Open | 5 | Critical endpoint finding or update-signing incident.
R-008 | Human, AI-agent and automation provenance remains incomplete or inaccurate. | Product / AI | 4 | 4 | 16 | Official hooks; process/file correlation; event sequencing; authoritative artefacts; confidence/unknown class; labelled evaluation. | AI Integrations / Data | 6–12 | Open | 8 | Attribution accuracy below pilot threshold or repeated mixed-origin errors.
R-009 | Task Assurance rewards a preferred process instead of valid outcomes and evidence. | Product / Fairness | 3 | 5 | 15 | Task contracts with multiple valid methods; outcome/quality gates; employee explanation; domain reviewer; deterministic evidence. | Product / Domain Reviewers | 2,7–12 | Open | 6 | Novel but valid work method receives repeated negative findings.
R-010 | Capability model overstates certainty, treats one task as proof or implies deception. | Capability / Employment | 4 | 5 | 20 | Repeated context-qualified evidence; neutral claim-discrepancy states; confidence/recency/contradiction; human review and appeal. | Capability Lead / HR / DPO | 2,8–12 | Open | 6 | Permanent capability or honesty label from insufficient evidence.
R-011 | Accessibility accommodations, deep thinking, research or collaboration are misclassified. | Fairness / Inclusion | 3 | 5 | 15 | Outcome over activity; accommodation context; reading/review/collaboration classes; accessibility review; subgroup error tests. | HR / Product / DPO | 0,7–12 | Open | 5 | Disproportionate errors or employee evidence of accommodation-related harm.
R-012 | Skill Forge introduces a harmful, biased, insecure or confidential-data-leaking update. | AI Platform / Governance | 3 | 5 | 15 | Proposal-only observation; evaluation; expert/security/DPO review; internal/open classification; canary; rollback. | AI Platform / Governance | 11–12 | Open | 6 | Regression, policy violation, confidential leakage or failed rollback.
R-013 | Scope expands across HumanOS verticals before the core is technically and ethically proven. | Programme / Scope | 4 | 4 | 16 | Software-development first; domain-neutral ontology; expansion gates; kill criteria and next-vertical business case. | CEO / Product / CTO | 0–12 | Open | 6 | New vertical added before pilot evidence or without domain/legal adapter plan.
R-014 | Microservice fragmentation creates excessive latency, failure modes and operational burden. | Architecture / Delivery | 4 | 3 | 12 | Approximately eight initial deployables; reuse HumanOS foundations; service split triggers; architecture review. | Enterprise Architect | 1–12 | Open | 4 | High cross-service change coupling, excessive synchronous chains or operational ownership gaps.
R-015 | Existing HumanOS foundation services do not meet Work Intelligence security, scale or workflow needs. | Platform / Dependency | 3 | 4 | 12 | Capability inventory; explicit extension/gap decisions; technical spikes; do not duplicate without evidence. | CTO / Platform Architect | 1–4 | Open | 6 | Policy/workflow/audit/object/event capability gap blocks Stage 3/4.
R-016 | Third-party source-available/OSS code is used beyond licence conditions or creates supply-chain exposure. | Legal / Supply Chain | 3 | 4 | 12 | Licence register; counsel review; SBOM; clean-room build where needed; dependency/security scanning. | Legal / Architecture / CISO | 1–12 | Open | 4 | Unapproved dependency or ambiguous commercial/distribution rights.
R-017 | Raw evidence and AI inference costs make the product economically unviable. | Cost / Scalability | 4 | 4 | 16 | Event-driven capture; dedup; edge summarisation; tiered retention; quotas; low/base/high cost model; model routing. | FinOps / Product / Data | 1,4–12 | Open | 6 | Cost per employee/task exceeds approved threshold or grows nonlinearly.
R-018 | Operational telemetry copies sensitive employee evidence into logs or traces. | Privacy / Observability | 3 | 5 | 15 | Separate evidence domain; content-off OTel defaults; classification-aware logging; sampling/redaction; telemetry tests. | SRE / DPO / AI Platform | 1,3–12 | Open | 5 | Prompt/text/screenshot content discovered in general observability backend.
R-019 | Third-party AI provider retains, trains on or transfers employee evidence outside approved conditions. | Vendor / Privacy | 3 | 5 | 15 | Approved Model Gateway; contractual no-training/retention; regional/private models; minimised requests; egress controls. | AI Platform / Legal / CISO | 1,7–12 | Open | 5 | Provider contract or technical behaviour does not meet policy.
R-020 | Prompt injection or malicious observed content manipulates evaluators or coaching agents. | AI Security | 4 | 4 | 16 | Treat observed content as untrusted; prompt isolation; tool restrictions; allowlisted retrieval; output validation; adversarial tests. | AI Security Lead | 7–12 | Open | 6 | Evaluator follows instructions embedded in screen/repository content or attempts unauthorised tools.
R-021 | Pilot data and labels are biased, weak or too small to validate accuracy and fairness. | Evaluation / Data | 4 | 4 | 16 | Representative tasks/roles; employee context; expert labels; holdout sets; disagreement adjudication; confidence intervals. | AI Evaluation / Product / HR | 7–12 | Open | 8 | Low label agreement, sparse edge cases or inability to estimate subgroup performance.
R-022 | Product provides reports but fails to produce measurable employee learning or task-quality improvement. | Product / Commercial | 3 | 5 | 15 | Employee-benefit KPIs; coaching experiments; applied-learning verification; manager and employee qualitative evidence; stop/modify decision. | Product / L&D / Executive Sponsor | 9–12 | Open | 8 | No measurable reduction in rework/gaps or low employee usefulness after controlled trial.

## KPI Dashboard
Programme KPI Dashboard
Formula-driven programme summary. Foundation readiness reflects draft maturity and outstanding gate conditions; it is not a legal or leadership approval.
Programme metric | Value | Stage | Stage name | Effort PW
Total stages | 13 | 0 | Foundation — charter, governance and legal boundary | 16
Total planned duration weeks | 64 | 1 | Foundation — market validation and reference architecture | 20
Indicative total effort person-weeks | 572 | 2 | Role capability and task contract ontology | 21
Critical-priority stages | 8 | 3 | Device agent foundation | 40
High-risk stages | 12 | 4 | Telemetry ingestion and evidence storage | 28
Stage 0 workplan maturity | 65.29% | 5 | Universal capture MVP | 54
Stage 1 workplan maturity | 71.21% | 6 | Development semantics and AI-agent adapters | 54
Stage 0 gate readiness | 57.22% | 7 | Provenance and Task Assurance Engine | 70
Stage 1 gate readiness | 56.67% | 8 | Capability Graph and baseline assessment | 40
Mandatory gate blockers/not-started | 5 | 9 | Growth Coach and learning loop | 40
Open programme risks | 22 | 10 | Employee and manager experiences | 45
High/critical inherent programme risks | 19 | 11 | Skill Forge and governed self-improvement | 48
Residual high/critical foundation threats | 0 | 12 | Security hardening, internal pilot and rollout decision | 96
Open assumptions/questions | 40
Architecture decisions accepted/in-principle | 20
Registered research sources | 82
Leadership interpretation and decision rules
# | Decision rule
1 | Foundation drafting is complete; Stage 0 remains unapproved until DPIA/DPO, legal, worker consultation, security and executive decisions are recorded.
2 | Stage 1 remains unapproved until formal licence, platform inventory, cost, resourcing and Architecture Board decisions are recorded.
3 | Stage 2 and Stage 3 prompts are ready and may be mobilised conditionally, but implementation involving employee monitoring must not bypass Stage 0 conditions.
4 | Build the proprietary evidence/provenance, Task Assurance, Capability Graph, Growth Coach and Skill Forge layers; reuse standards and HumanOS foundation services.
5 | Do not measure productivity through click, keystroke, code-volume or hours alone. Use task outcomes, quality, independence, context and employee response.
6 | Keep operational observability separate from sensitive employee evidence; use references and correlation identifiers rather than copying content into traces.
7 | Pilot success requires employee usefulness and trust evidence as well as capture and model accuracy.

## Source Register
Source Register
Primary and high-value research sources used for the Stage 0–1 foundation package. Sources support planning decisions but do not replace Nessovo legal, security, architecture or procurement approvals.
Source ID | Source / publisher | Type | Supports | Source URL | Priority | Review note / status
SRC-001 | OpenAI — Prompt engineering best practices | Official guidance | Instructions first, delimiters, specificity, output examples and iterative refinement. | https://help.openai.com/en/articles/6654000-best-practices-for-prompt-engineering-with-the-openai-api | High | Used in Master Prompts.
SRC-002 | OpenAI — Prompt engineering best practices for ChatGPT | Official guidance | Clear task, context, format, iterative refinement and examples. | https://help.openai.com/en/articles/10032626-prompt-engineering-best-practices | High | Used in Master Prompts.
SRC-003 | Google Gemini — Prompting strategies | Official guidance | Precise instructions, consistent structure, decomposition, planning and validation. | https://ai.google.dev/gemini-api/docs/prompting-strategies | High | Used in Master Prompts.
SRC-004 | GitHub Copilot — Prompt engineering concepts | Official guidance | Break down complex tasks, provide context/examples and validate outputs. | https://docs.github.com/en/enterprise-cloud@latest/copilot/concepts/prompting/prompt-engineering | High | Used in Master Prompts.
SRC-005 | GitHub Copilot — Best practices | Official guidance | Specific prompts, task decomposition, context and output review. | https://docs.github.com/en/copilot/get-started/best-practices | High | Used in Master Prompts.
SRC-006 | Teramind employee monitoring | Commercial product | Market baseline for screen, keystroke, application/web and active/idle monitoring. | https://www.teramind.co/solutions/employee-monitoring/ | High | Benchmark only; not recommended as product core.
SRC-007 | Teramind live desktop/history playback | Commercial product | Live view and historical screen playback capability. | https://www.teramind.co/features/live-desktop-view-history-playback/ | Medium | Raw monitoring baseline.
SRC-008 | ActivTrak AI Insights | Commercial product | AI-tool adoption, workforce analytics and productivity-impact reporting. | https://support.activtrak.com/hc/en-us/articles/50125731483675-AI-Insights-Add-on | High | Reporting/market signal.
SRC-009 | UiPath Task Capture settings | Commercial documentation | Screenshots around clicks/keyboard actions, UI elements and task capture. | https://docs.uipath.com/task-capture/standalone/2021.10/user-guide/capture-settings | High | Action-level capture reference.
SRC-010 | UiPath Task Mining | Commercial documentation | Task-mining projects and process discovery. | https://docs.uipath.com/process-mining/automation-cloud/latest/user-guide/starting-a-task-mining-project-from-process-mining | High | Process/task mining reference.
SRC-011 | ABBYY Timeline Task Mining | Commercial documentation | Screen snapshots, clicks, text entered, applications and task association. | https://help.abbyy.com/en-us/timeline/6/user_guide/task-mining | High | Task reconstruction reference.
SRC-012 | Microsoft Power Automate AI Recorder | Official documentation | Screen/voice/mouse/keyboard demonstration converted into desktop automation. | https://learn.microsoft.com/en-us/power-automate/desktop-flows/create-flow-using-ai-recorder | Medium | Record/replay and Skill Forge reference.
SRC-013 | Microsoft Power Automate desktop recording | Official documentation | Mouse/keyboard and UI/image/OCR-based automation recording. | https://learn.microsoft.com/en-gb/power-automate/desktop-flows/recording-flow | Medium | GUI capture/replay reference.
SRC-014 | Soroco | Commercial product | Work graph, process variants, workarounds and automation opportunity discovery. | https://soroco.com/ | Medium | Work-graph category reference.
SRC-015 | Workfellow | Commercial product | Process and task mining and workflow analysis. | https://www.workfellow.ai/ | Medium | Process-intelligence reference.
SRC-016 | LinearB AI & Developer Productivity Insights | Commercial product | AI usage, engineering productivity, workflow governance, coaching and business alignment. | https://linearb.io/platform/ai-developer-productivity-insights | High | Adjacent software-development competitor.
SRC-017 | LinearB AI Workflow Governance | Commercial product | AI workflow automation, scalable policy and governance across engineering tools. | https://linearb.io/platform/ai-workflow-governance | Medium | Developer AI governance reference.
SRC-018 | Jellyfish engineering intelligence | Commercial product | AI-integrated engineering intelligence, AI spend/usage, workflow and delivery outcomes. | https://jellyfish.co/ | High | Adjacent software-development competitor.
SRC-019 | Jellyfish Data Hub | Commercial product | Combines Jira/PR/AI usage, DORA and custom engineering metrics. | https://jellyfish.co/platform/data-hub/ | Medium | Engineering data model/reporting reference.
SRC-020 | Jellyfish Claude Code dashboard | Commercial product | Claude Code adoption, usage and delivery impact. | https://jellyfish.co/platform/claude-code-dashboard/ | Medium | AI developer-tool ROI reference.
SRC-021 | GitClear | Commercial product | Code analytics, AI-code quality and developer analytics. | https://www.gitclear.com/ | Medium | Repository/code-quality reference.
SRC-022 | TechWolf Skills Intelligence | Commercial product | Continuously inferred skills from actual work activity and HCM integration. | https://www.techwolf.ai/product/skills-intelligence | High | Directly relevant to capability verification.
SRC-023 | TechWolf platform | Commercial product | Skills, work and market intelligence data layer. | https://www.techwolf.ai/ | High | Skills/work-intelligence category reference.
SRC-024 | Eightfold Talent Intelligence | Commercial product | Models workers, skills, capabilities and work signals for hiring, development and staffing. | https://eightfold.ai/products/ | High | Talent/capability reference.
SRC-025 | Eightfold Talent Management | Commercial product | Employee skills, work signals, career development and workforce readiness. | https://eightfold.ai/products/talent-management/ | Medium | Employee-growth reference.
SRC-026 | Gloat Workforce Graph | Commercial product | Dynamic skills ontology, task-role mapping and workforce graph. | https://gloat.com/platform/workforce-graph/ | High | Capability/workforce graph reference.
SRC-027 | Gloat Agentic HR Platform | Commercial product | Governed, auditable and reversible workforce agents and skills inference. | https://gloat.com/ | High | Agentic HR and governance reference.
SRC-028 | Gloat Work Orchestration Mosaic | Commercial product | Human/AI task-level work planning and orchestration. | https://gloat.com/platform/work-orchestration-mosaic/ | Medium | Human–AI work orchestration reference.
SRC-029 | Degreed Maestro | Commercial product | AI learning, coaching, skill review, pathways and behaviour change. | https://degreed.com/experience/artificial-intelligence/ | High | Learning/coaching reference.
SRC-030 | Degreed platform | Commercial product | Personalised workforce learning and targeted upskilling. | https://degreed.com/ | Medium | Learning-content and LMS integration reference.
SRC-031 | Screenpipe GitHub | Source-available repository | Event-driven screen capture, accessibility, OCR fallback, keyboard/app events, local search and AI pipes. | https://github.com/screenpipe/screenpipe | High | Commercial use requires licence per repository.
SRC-032 | ActivityWatch GitHub | Open-source repository | Local watcher/server architecture for window/browser/AFK events. | https://github.com/ActivityWatch/activitywatch | High | MPL-2.0 verified.
SRC-033 | ActivityWatch window watcher | Open-source repository | Foreground-window event collector. | https://github.com/ActivityWatch/aw-watcher-window | Medium | Reference for endpoint event semantics.
SRC-034 | ActivityWatch web watcher | Open-source repository | Browser tab/title/URL watcher. | https://github.com/ActivityWatch/aw-watcher-web | Medium | Reference for browser adapter.
SRC-035 | OpenAdapt Desktop | Open-source repository | Capture/review/teach desktop architecture and bridge to workflow engine. | https://github.com/OpenAdaptAI/openadapt-desktop | High | MIT; repository states experimental/non-production.
SRC-036 | OpenAdapt Flow | Open-source repository | Record/compile/lint/certify/replay/repair/teach workflow pattern. | https://github.com/OpenAdaptAI/openadapt-flow | Medium | Licence/security review required.
SRC-037 | OpenAdapt Privacy | Open-source repository | Experimental PII/redaction component. | https://github.com/OpenAdaptAI/openadapt-privacy | Medium | Independent evaluation and model-licence review required.
SRC-038 | Claude-Mem GitHub | Open-source repository | Agent lifecycle hooks, local worker, SQLite/FTS5, summaries and memory retrieval. | https://github.com/thedotmack/claude-mem | High | Apache-2.0 in repository metadata.
SRC-039 | Task Observer GitHub | Open-source methodology | Correction/gap observations, cross-cutting principles and human-reviewed skill improvement. | https://github.com/rebelytics/one-skill-to-rule-them-all | High | CC BY 4.0 attribution required.
SRC-040 | WakaTime CLI GitHub | Open-source repository | Developer editor/CLI heartbeat instrumentation. | https://github.com/wakatime/wakatime-cli | Medium | BSD 3-Clause verified.
SRC-041 | OpenTelemetry Semantic Conventions GitHub | Open standard repository | Cross-language trace/metric/log semantic conventions. | https://github.com/open-telemetry/semantic-conventions | High | Operational observability reference.
SRC-042 | OpenTelemetry GenAI Conventions GitHub | Open standard repository | Provider-neutral GenAI/agent/tool/MCP telemetry conventions. | https://github.com/open-telemetry/semantic-conventions-genai | High | Sensitive input/output fields require policy.
SRC-043 | CloudEvents specification GitHub | Open standard repository | Portable event-envelope metadata and bindings. | https://github.com/cloudevents/spec | High | Apache-2.0 verified.
SRC-044 | Open Policy Agent GitHub | Open-source repository | Policy-as-code engine, bundles and decision APIs. | https://github.com/open-policy-agent/opa | High | Reuse HumanOS policy service first; benchmark OPA.
SRC-045 | Temporal Java SDK GitHub | Open-source repository | Durable Java workflows and activities. | https://github.com/temporalio/sdk-java | Medium | Reference only until HumanOS workflow gaps are proven.
SRC-046 | Temporal Python SDK GitHub | Open-source repository | Durable Python workflows and activities. | https://github.com/temporalio/sdk-python | Medium | Reference only.
SRC-047 | OpenAI Codex Hooks | Official documentation | Codex lifecycle instrumentation and policy/validation hooks. | https://developers.openai.com/codex/hooks | High | First-class AI Adapter input.
SRC-048 | OpenAI Record & Replay | Official documentation | Demonstration converted to reusable skill with inputs, steps and verification. | https://developers.openai.com/codex/record-and-replay | Medium | Skill Forge reference; provider-neutral Nessovo design.
SRC-049 | OpenTelemetry semantic conventions | Official documentation | Standard operational telemetry naming and lifecycle. | https://opentelemetry.io/docs/concepts/semantic-conventions/ | High | Keep raw employee evidence outside traces.
SRC-050 | OpenTelemetry GenAI attributes | Official documentation | GenAI request/response/agent/tool attributes and sensitivity warnings. | https://opentelemetry.io/docs/specs/semconv/registry/attributes/gen-ai/ | High | Content capture must be policy-controlled.
SRC-051 | Apache Kafka documentation | Official documentation | Durable event streaming, consumers, replay and distributed data flow. | https://kafka.apache.org/documentation/ | High | Reuse HumanOS compatible event infrastructure.
SRC-052 | CloudEvents | Official project | Standard event envelope and ecosystem. | https://cloudevents.io/ | High | Adopt style if compatible with existing HumanOS contracts.
SRC-053 | Open Policy Agent documentation | Official documentation | Policy decision/enforcement separation and policy bundles. | https://www.openpolicyagent.org/docs | High | Architecture benchmark.
SRC-054 | Spring Microservices | Official documentation | Spring Boot/Cloud microservice architecture. | https://spring.io/microservices | High | Java platform basis.
SRC-055 | Spring Boot 4.1 release | Official release article | Current Spring Boot 4.1 release capabilities and baseline. | https://spring.io/blog/2026/06/10/spring-boot-4-1-0-available-now | Medium | Benchmark, not forced migration.
SRC-056 | Spring Cloud project | Official documentation | Spring Cloud release-train compatibility and distributed-system features. | https://spring.io/projects/spring-cloud/ | High | Confirm against current HumanOS stack.
SRC-057 | OpenJDK JDK 25 project | Official project | Java 25 platform release information. | https://openjdk.org/projects/jdk/25/ | Medium | Java 25 is an LTS release from most vendors; benchmark selectively.
SRC-058 | PostgreSQL | Official documentation | Transactional database platform. | https://www.postgresql.org/docs/ | High | Initial system of record.
SRC-059 | pgvector GitHub | Open-source repository | Vector similarity search in PostgreSQL. | https://github.com/pgvector/pgvector | Medium | Use only for approved/minimised embeddings.
SRC-060 | MinIO | Official documentation | S3-compatible object storage reference. | https://min.io/docs/minio/linux/index.html | Medium | Reuse HumanOS object service where suitable.
SRC-061 | NIST AI Risk Management Framework | Standards/guidance | Govern, Map, Measure and Manage AI risks with testing and monitoring. | https://www.nist.gov/itl/ai-risk-management-framework | High | AI governance/evaluation basis.
SRC-062 | SFIA 9 role-family/job-title resources | Skills framework | Skills and responsibility levels separated from inconsistent job titles. | https://sfia-online.org/en/tools-and-resources/standard-industry-skills-profiles/sfia-9-skills-for-role-families-job-titles | Medium | Stage 2 mapping reference, not sole ontology.
SRC-063 | Microsoft UI Automation overview | Official documentation | Windows accessibility/control tree and programmatic UI events. | https://learn.microsoft.com/en-us/dotnet/framework/ui-automation/ui-automation-overview | High | Windows native bridge reference.
SRC-064 | Microsoft Event Tracing for Windows | Official documentation | Efficient kernel/application event tracing. | https://learn.microsoft.com/en-us/windows/win32/etw/about-event-tracing | High | Process/system telemetry reference.
SRC-065 | Microsoft SetWindowsHookEx | Official documentation | Low-level hook capability and system-wide constraints. | https://learn.microsoft.com/en-us/windows/win32/api/winuser/nf-winuser-setwindowshookexw | High | Input implementation risk reference.
SRC-066 | Windows Graphics Capture | Official documentation | Windows display/window capture primitives. | https://learn.microsoft.com/en-us/windows/uwp/audio-video-camera/screen-capture | High | Windows screen-capture reference.
SRC-067 | Apple ScreenCaptureKit | Official documentation | macOS screen/audio capture framework. | https://developer.apple.com/documentation/screencapturekit | High | Audio disabled for v1.
SRC-068 | Apple Accessibility | Official documentation | macOS accessibility APIs and UI element access. | https://developer.apple.com/documentation/applicationservices/axuielement | High | macOS semantic-state reference.
SRC-069 | Chrome Tabs API | Official documentation | Browser tab metadata and permissions. | https://developer.chrome.com/docs/extensions/reference/api/tabs | High | Browser adapter reference.
SRC-070 | Chrome Native Messaging | Official documentation | Browser extension to native application communication. | https://developer.chrome.com/docs/extensions/develop/concepts/native-messaging | High | Browser-agent bridge.
SRC-071 | XDG Desktop Portal InputCapture | Official documentation | Wayland input-capture permission and compositor constraints. | https://flatpak.github.io/xdg-desktop-portal/docs/doc-org.freedesktop.portal.InputCapture.html | Medium | Supports deferring uniform Linux capture.
SRC-072 | GOV.UK — Monitoring staff at work | Government guidance | Monitoring justification, worker information and covert-monitoring limits. | https://www.gov.uk/data-protection-your-business/monitoring-staff-at-work | Critical | Stage 0 legal/governance basis.
SRC-073 | ICO — Data protection and monitoring workers | Regulator guidance | DPIA, necessity, proportionality, transparency, accuracy and worker challenge. | https://ico.org.uk/for-organisations/uk-gdpr-guidance-and-resources/employment/monitoring-workers/data-protection-and-monitoring-workers/ | Critical | Keystroke/performance monitoring is high-risk.
SRC-074 | ICO — Human review | Regulator guidance | Meaningful human review, authority, competence and independence. | https://ico.org.uk/for-organisations/advice-and-services/audits/data-protection-audit-framework/toolkits/artificial-intelligence/human-review/ | Critical | Consequential-decision safeguard.
SRC-075 | UK Government — Workplace monitoring technologies consultation | Government consultation | Transparency, clarity and worker voice in workplace-monitoring policy. | https://www.gov.uk/government/consultations/make-work-pay-workplace-monitoring-technologies | High | Published July 2026; policy direction may evolve.
SRC-076 | UK Data (Use and Access) Act 2025 explanatory notes | Legislation notes | Automated-decision safeguards and UK data-law changes. | https://www.legislation.gov.uk/ukpga/2025/18/notes/division/10/index.htm | High | Legal counsel must interpret current application.
SRC-077 | EU AI Act Annex III | Regulation reference | High-risk employment, worker-management and access-to-employment AI categories. | https://ai-act-service-desk.ec.europa.eu/en/ai-act/annex-3 | High | Relevant to future EU deployment.
SRC-078 | EU AI Act Article 6 | Regulation reference | Classification rules for high-risk AI and profiling context. | https://ai-act-service-desk.ec.europa.eu/en/ai-act/article-6 | High | Future EU policy pack.
SRC-079 | Pakistan MoITT — Personal Data Protection Bill update | Government source | Pakistan's continuing data-protection legislative development. | https://moitt.gov.pk/NewsDetail/NzdkMmNjZDAtNjZkMi00NTY2LWE1NTYtYjRjMmIxOGZlNWNm | High | Status has evolved; current local counsel confirmation required.
SRC-080 | President of Pakistan — PECA Amendment Bill 2025 assent | Government source | Current cyber-law context and 2025 amendment assent. | https://president.gov.pk/president-asif-ali-zardari-signed-the-electronic-crimes-amendment-bill-2025-peca-2 | High | Does not by itself answer workplace monitoring; local counsel required.
SRC-081 | Pakistan National Cyber Crime Investigation Agency | Government source | Current cybercrime enforcement body and cyber-law context. | https://www.nccia.gov.pk/ | Medium | Local counsel required for employment-monitoring application.
SRC-082 | Pakistan Draft Data Governance Policy 2026 reporting | Current policy reporting | Emerging public-sector data-governance, privacy-by-design and audit direction. | https://www.dawn.com/news/2011804 | Medium | Draft concerns public-sector data and is not a private-sector workplace-monitoring law.

## Master Prompts
Master Prompts — Foundation and Next-Stage Execution
Research-backed prompts used to execute the combined Stage 0–1 foundation workstream, followed by reusable prompts for Stages 2 and 3.
ID | Prompt-design principle | Why it matters | Primary basis | Decision | Source URL
P-01 | Put critical instructions and constraints first. | Reduces missed requirements and establishes the operating frame before context. | OpenAI / Google | Adopted | https://help.openai.com/en/articles/6654000-best-practices-for-prompt-engineering-with-the-openai-api
P-02 | Separate role, context, task, constraints and output using consistent delimiters. | Makes long, multi-disciplinary prompts easier to parse and audit. | OpenAI / Google | Adopted | https://ai.google.dev/gemini-api/docs/prompting-strategies
P-03 | Define the required result, format, detail level and decision criteria explicitly. | Prevents generic narrative output and forces decision-ready deliverables. | OpenAI | Adopted | https://help.openai.com/en/articles/10032626-prompt-engineering-best-practices
P-04 | Break complex work into chained stages and make outputs from one stage inputs to the next. | Improves reliability for research, architecture, governance and delivery planning. | Google / GitHub | Adopted | https://docs.github.com/en/enterprise-cloud@latest/copilot/concepts/prompting/prompt-engineering
P-05 | Provide examples, schemas or expected output structures. | Makes generated work easier to validate and transfer into Excel or implementation artefacts. | OpenAI / GitHub | Adopted | https://docs.github.com/en/copilot/get-started/best-practices
P-06 | Require source grounding and distinguish fact, inference, assumption and recommendation. | Reduces unsupported claims and creates an auditable research trail. | Nessovo control | Adopted | Internal project requirement
P-07 | Plan, execute and validate against explicit acceptance criteria. | Adds a completion check instead of treating first-pass generation as final. | Google / GitHub | Adopted | https://ai.google.dev/gemini-api/docs/prompting-strategies
P-08 | State prohibited outputs and the required alternative behaviour. | Prevents the prompt from drifting into surveillance scoring or unsupported employment conclusions. | OpenAI / Nessovo | Adopted | https://help.openai.com/en/articles/6654000-best-practices-for-prompt-engineering-with-the-openai-api
Applied Stage 0–1 Master Prompt
Prompt section | Exact instruction | Purpose
<identity> | You are an integrated senior delivery team comprising: a product strategist, enterprise architect, Java/Spring platform architect, Python/AI architect, native desktop-agent architect, data architect, security architect, privacy engineer, UK employment/privacy specialist, HR and learning-design specialist, AI evaluation lead, programme manager and employee-experience representative. Work as one team. Resolve conflicts by prioritising lawful and safe operation, factual evidence, employee fairness, HumanOS platform fit, technical feasibility and commercial differentiation—in that order. | Defines the cross-functional decision authority.
<mission> | Create the complete decision-ready foundation for Nessovo HumanOS Work Intelligence by executing Stage 0 and Stage 1 as one combined Foundation & Validation workstream while retaining two independent approval gates. Stage 0 establishes purpose, scope, governance, lawful boundaries, employee rights and pilot authority. Stage 1 validates the market and open-source landscape, makes build/buy/integrate/defer decisions, and defines the HumanOS reference architecture and technical-spike plan. | Establishes the exact objective and the relationship between both stages.
<authoritative_context> | Company: Nessovo. Platform: HumanOS, an existing microservices-based modular platform intended to support business verticals and long-term human development. Existing foundation services should be reused wherever they meet the requirement. Primary backend technologies are Java and Spring Boot; Python is used for AI, multimodal analysis, scoring and evaluation services. Native OS components may use Rust, Swift, C#, C++ or platform APIs where Java/Python are unsuitable. Target product: a task-aware work-intelligence system that records and reconstructs material activity on company-managed computers; links work to assigned tasks and acceptance criteria; distinguishes human, AI-agent, automation and system actions; evaluates task completion and quality; verifies evidence of role capability; provides employee coaching and training; gives authorised managers evidence-linked reports; and improves HumanOS skills and evaluators through a governed learning loop. Initial vertical: AI-assisted software development. Future design must support other HumanOS business verticals without forcing every domain into software-development semantics. | Provides stable product and platform context.
<definitions> | Use these definitions consistently: - FACT: directly supported by a primary source or observed repository artefact. - INFERENCE: a reasoned conclusion derived from identified facts. - RECOMMENDATION: a proposed Nessovo decision. - ASSUMPTION: an unresolved condition used temporarily and explicitly. - ACTIVITY EVIDENCE: captured events or artefacts; not automatically a performance conclusion. - TASK ASSURANCE: evaluation against an approved Task Execution Contract and acceptance criteria. - CAPABILITY EVIDENCE: repeated, context-qualified evidence that a person can perform a defined capability at a defined autonomy level. - CONSEQUENTIAL DECISION: a decision affecting dismissal, discipline, pay, promotion, probation or equivalent employment outcome. - FOUNDATION GATE: a formal approve, conditional approve, hold or reject decision with named authority and evidence. | Prevents ambiguous terminology.
<research_protocol> | 1. Search current primary sources first: official product documentation, regulator/government guidance, standards bodies, authoritative project documentation, GitHub README files, licence files, releases and architecture documents. 2. Record source URL, publisher/project, retrieval date, what the source proves, limitations, licence status and relevance to Nessovo. 3. For GitHub projects, inspect project maturity, architecture, platform support, data captured, local/cloud model, extensibility, licence and commercial-use constraints. Do not equate public source code with unrestricted commercial reuse. 4. Compare commercial products, process/task-mining platforms, workforce analytics, developer-intelligence tools, skills-intelligence platforms, workflow-record/replay systems and AI-agent observability. 5. Separate facts, inferences, recommendations and assumptions in every decision. 6. Where sources disagree or a conclusion is uncertain, record the disagreement and propose a validation spike. 7. Do not claim that no comparable product exists. State precisely which capability combination remains differentiated. | Defines evidence quality and research discipline.
<stage_0_workstream> | Produce: A. Product charter, strategic positioning and initial vertical. B. Allowed uses, prohibited uses and non-goals. C. Purpose-by-data-type necessity and proportionality matrix. D. Governance model: worker transparency, consultation, evidence access, corrections, disputes, meaningful human review, manager decision rights and audit. E. DPIA initiation pack and legal-question register for UK and Pakistan/Lahore deployment; identify where jurisdiction-specific counsel is required. F. Security and privacy principles: secure-field blocking, application/domain exclusions, edge redaction, encryption, retention, access purpose codes and incident handling. G. Stakeholder map and RACI. H. Internal pilot definition, participant protection, success metrics, stop criteria and approval requirements. I. Stage 0 gate checklist with approve/conditional/hold/reject criteria. | Stage 0 deliverable contract.
<stage_1_workstream> | Produce: A. Market landscape and strategic gap analysis. B. GitHub/open-source scan with licence and maturity notes. C. Component-level build/buy/integrate/benchmark/defer decisions. D. Reference architecture aligned to HumanOS. E. Initial bounded contexts and deployment boundaries; avoid premature nano-services. F. Technology decisions for Java/Spring, Python AI services, native device agent, Kafka-compatible event streaming, CloudEvents-style envelopes, schema governance, OPA-style policy-as-code and OpenTelemetry operational/AI traces. G. Data architecture for transactional metadata, evidence objects, search, embeddings and graph queries; defer specialised stores until proven necessary. H. Architecture decision record register. I. Device-agent, privacy, performance, provenance and AI-evaluation technical spikes. J. Stage 1 gate checklist with architecture, licence, threat, cost, ownership and feasibility criteria. | Stage 1 deliverable contract.
<architecture_constraints> | 1. Reuse HumanOS identity, organisation, task/project, workflow, policy, audit, notification, secrets, object/file, model-gateway and event capabilities where suitable. 2. Keep the desktop/device agent separate from cloud business services. 3. Use Java/Spring Boot for durable domain services, API orchestration, policy integration, audit and transactional workflows. 4. Use Python for multimodal interpretation, episode classification, task/capability evaluators, coaching, embeddings and evaluation harnesses. 5. Use native code only for OS capture, secure local storage, permissions, accessibility and performance-critical device functions. 6. Use event-driven contracts with idempotency, signed batches, tenant partitioning, schema versioning and replay. 7. OpenTelemetry is for service and AI operational observability; raw worker evidence and model content must not be copied into traces by default. 8. Start with PostgreSQL and object storage; use pgvector/search as justified; introduce a dedicated graph database only after query and scale evidence. 9. Reuse the HumanOS workflow runtime before introducing another orchestrator. 10. For Java baseline: retain the existing supported HumanOS version unless a measured migration case is approved. For greenfield-compatible services, benchmark Java 25 LTS with Spring Boot 4.1 and the compatible Spring Cloud release train. 11. Every service boundary must have a security, scale, ownership or transactional justification. | Prevents architecture drift and technology novelty bias.
<governance_constraints> | The product must not: - operate as a hidden general-surveillance system; - use click, mouse or keystroke volume as a productivity score; - infer emotions, personality, honesty or mental state from activity; - capture password or known secure-field content; - make solely automated consequential employment decisions; - present uncertain AI classifications as facts; - let managers browse raw evidence without role, purpose, scope and audit controls; - repurpose evidence beyond the approved purpose without a new assessment; - penalise legitimate thinking, reading, accessibility accommodations, meetings or automated execution waits. The product must provide visible monitoring status, employee access to their evidence, correction and dispute routes, confidence and source links, meaningful human review, local minimisation/redaction and jurisdiction-specific policies. | Non-negotiable safety and trust boundary.
<required_deliverables> | Create and populate: 1. Master prompt and prompt-research principles. 2. Foundation dashboard. 3. Detailed Stage 0–1 workplan. 4. Product Charter v1. 5. Purpose Policy Matrix. 6. Stakeholder RACI. 7. Expanded market landscape and GitHub scan. 8. Strategic gap matrix. 9. Build/Buy/Integrate decision matrix. 10. Reference architecture. 11. Architecture decision register. 12. Stage 0–1 gate checklists. 13. Assumptions and open-question register. 14. Foundation threat register. 15. Pilot definition. 16. Updated delivery stages, microservices map, governance, risk, KPIs and source register. 17. Exact execution prompts for Stage 2 and Stage 3. | Makes the output verifiable.
<excel_output_contract> | Use a professional Excel workbook as the system of record. Each researched row must contain a source URL. Each action must have an ID, owner role, dependency, priority, status, effort, deliverable and acceptance criterion. Each decision must record status, rationale, alternatives, risk and revisit trigger. Use formulas for readiness and completion metrics. Apply consistent status values and conditional formatting. Keep raw approvals and organisational decisions marked as pending where they have not actually occurred. Never present a drafted artefact as legally approved or leadership-approved. | Defines spreadsheet semantics and honesty requirements.
<execution_sequence> | Execute in this order: 1. Reconfirm authoritative context and unresolved assumptions. 2. Perform current source research and GitHub due diligence. 3. Map the competitive capability landscape. 4. Define Stage 0 charter, purpose and governance boundaries. 5. Define Stage 1 architecture and build/buy decisions. 6. Build the workplan, decision registers, threat register and pilot. 7. Validate architecture against HumanOS reuse, Java/Python/native boundaries and operational constraints. 8. Validate governance against monitoring necessity, proportionality, worker rights and human review. 9. Calculate gate readiness. 10. Run a final completeness, contradiction, source and formatting check. 11. Produce the next-stage prompts. | Creates a reliable sequence.
<quality_gates> | Reject or hold a recommendation when any of the following is true: - the purpose is vague or could be achieved through a materially less intrusive method that has not been assessed; - passwords/secrets cannot be reliably excluded; - employee visibility, correction, dispute or human review is absent; - the architecture duplicates an existing HumanOS service without justification; - a proposed dependency has unclear commercial rights or unacceptable maturity/security; - a service boundary has no operational or ownership justification; - task/capability conclusions cannot link back to inspectable evidence; - the pilot lacks measurable employee benefit and stop criteria; - the AI/evaluator cannot be calibrated and challenged; - current factual claims are unsupported by primary sources. | Defines when the work must stop rather than continue optimistically.
<completion_criteria> | Stage 0–1 foundation work is complete as a draft package when all required workbook sections are populated, sources are registered, architecture and build/buy recommendations are explicit, gate criteria are calculable, unresolved approvals are clearly marked, and the workbook passes formula and visual-quality checks. Stage 0 and Stage 1 are not organisationally approved until the named Nessovo authorities record their decisions. | Separates document completion from real approval.
Next Execution Prompt — Stage 2
<identity> You are a senior cross-functional team of product architects, organisational psychologists, HR/L&D specialists, domain experts, knowledge-graph engineers, Java/Spring architects, Python/AI engineers, data-governance specialists and employee-experience representatives. </identity> <mission> Execute Stage 2 of Nessovo HumanOS Work Intelligence: design the Role Capability Contract, Task Execution Contract and evidence ontology that will govern how job requirements, employee claims, task evidence, autonomy, quality, training and role readiness are represented. Produce implementation-ready schemas, rubrics, examples, APIs, events, backlog and gate criteria in the existing Excel workbook. </mission> <authoritative_context> Nessovo is building HumanOS as a modular microservices platform. Work Intelligence must support all future business verticals while the first implementation vertical is AI-assisted software development. Java/Spring Boot is the primary durable domain-service stack; Python is used for AI extraction, scoring and evaluation. Existing HumanOS identity, organisation, role, task/project, workflow, policy, audit, notification, model-gateway and event services must be reused. </authoritative_context> <non_negotiable_rules> - A job-description statement is a requirement or claim, not evidence. - A single task failure or success cannot permanently establish capability. - Capability evidence must be context-qualified, confidence-scored, time-aware and linked to inspectable work evidence. - Never classify a claim discrepancy as dishonesty without separate human investigation and evidence. - Capability cannot increase merely because training was completed; it increases after successful application. - Do not infer personality, emotion, protected traits or mental state. - Consequential employment decisions require meaningful human review. - The ontology must support multiple valid work methods and accessibility accommodations. </non_negotiable_rules> <required_workstreams> 1. Define canonical entities and relationships: Role, RoleVersion, Responsibility, Outcome, Capability, CapabilityLevel, BehaviouralIndicator, Tool/Environment, EmployeeClaim, BaselineAssessment, TaskContract, AcceptanceCriterion, QualityGate, EvidenceRequirement, WorkEpisode, Artefact, CapabilityEvidence, Gap, LearningIntervention, ReviewDecision and RoleReadiness. 2. Define capability levels with observable descriptors for knowledge, execution, autonomy, complexity, quality, transfer, recovery and mentoring. 3. Define evidence weighting, confidence, recency, consistency, task difficulty, guidance dependence and contradictory evidence. 4. Define claim statuses and claim-evidence discrepancy workflow. 5. Define Task Execution Contract structure, lifecycle, versioning and approval. 6. Define role-to-task-to-capability traceability. 7. Produce at least four software-development role profiles and twelve representative task contracts with evidence rubrics. 8. Produce domain-neutral extension rules for future HumanOS verticals. 9. Define Java domain models, PostgreSQL logical schema, JSON Schemas, REST/OpenAPI resources and CloudEvents-compatible domain events. 10. Define deterministic rules versus Python/AI-assisted extraction and scoring. 11. Define fairness, human-review, correction, appeal, audit and retention controls. 12. Create a Stage 2 implementation backlog, test/evaluation suite and go/no-go gate. </required_workstreams> <output_contract> Update the workbook with dedicated sheets for ontology, entity dictionary, relationships, capability-level rubric, role templates, task-contract templates, evidence scoring, examples, APIs/events, backlog, risks, decisions, gate and sources. Each row must have IDs, definitions, owner, status, acceptance criteria and source where researched. Distinguish fact, recommendation, assumption and unresolved question. Use formulas for completeness and gate readiness. </output_contract> <validation> Validate that every role requirement can trace to capabilities, every task criterion can trace to evidence, every capability update can trace to multiple qualified evidence items, every AI inference is challengeable, and the model can extend beyond software development without rewriting the core ontology. </validation>
Next Execution Prompt — Stage 3
<identity> You are a senior native-device engineering and platform team comprising Windows, macOS and Linux architects; Rust, Swift, C#/C++ and Java engineers; security and privacy engineers; endpoint-management specialists; performance engineers; QA/SDET leads; threat modellers; HumanOS Spring-platform architects; and employee-experience representatives. </identity> <mission> Execute Stage 3 of Nessovo HumanOS Work Intelligence: design and implement the Device Agent Foundation for company-managed endpoints. The stage must deliver an installable, signed agent skeleton for Windows and macOS, policy synchronisation, explicit work-session controls, secure local journaling, health telemetry, update architecture and a validated technical-spike plan for later capture capabilities. Update the existing Excel workbook with implementation-ready specifications and backlog. </mission> <authoritative_context> The device agent is the universal evidence-collection edge of HumanOS Work Intelligence. It must remain separate from cloud microservices. HumanOS core services use Java/Spring Boot; the native agent may use Rust as the shared core with Swift and Windows-native bridges where required. Python is not the primary always-on capture runtime but may be used in development tools and local model experiments. Stage 3 does not yet implement unrestricted keylogging or complete screenshot capture; it establishes the secure, policy-controlled foundation on which Stage 5 capture will be built. </authoritative_context> <non_negotiable_rules> - No covert mode. - Visible monitoring state and explicit session controls are mandatory. - Password/secure-field blocking and application/domain exclusion architecture must exist before sensitive capture. - The agent must fail safe when policy is unavailable or invalid. - Device credentials and evidence keys must use OS secure storage. - Every event batch must be signed, schema-versioned, idempotent and tenant/device/session scoped. - Local collection must continue safely during temporary network loss. - Software update, rollback, tamper evidence and audit are mandatory. - The agent must not create perceptible keyboard/mouse latency. - Accessibility and employee correction requirements must be included from the beginning. </non_negotiable_rules> <required_workstreams> 1. Produce Windows/macOS/Linux capability and permission matrix; Linux may be deferred with explicit Wayland limitations. 2. Decide shared-core and native-bridge architecture through documented ADRs. 3. Define agent modules: bootstrap, identity/certificates, policy engine/cache, session controller, event journal, encryption/key management, batcher/uploader, health/diagnostics, update/rollback, UI/tray, exclusions, audit and adapter SDK. 4. Define device registration, attestation, certificate rotation, mTLS and revocation. 5. Define local encrypted SQLite/SQLCipher-style journal and content-addressed object cache. 6. Define policy bundle format, signatures, versioning, expiry, offline behaviour and OPA/HumanOS policy integration. 7. Define work-day/task-session state machine and user-visible states. 8. Define event envelope, local sequence numbers, deduplication keys, compression, retry/backoff and telemetry-gap reporting. 9. Define secure update and code-signing pipeline for Windows and macOS. 10. Produce threat model covering agent tampering, privilege escalation, secret capture, malicious updates, evidence exfiltration, spoofed events and insider misuse. 11. Define performance, reliability, storage and battery budgets. 12. Define technical spikes for active window/process, accessibility, secure fields, screenshots, input provenance, file events, browser/native messaging and AI-agent adapters. 13. Produce test strategy: unit, contract, integration, OS-permission, security, performance, chaos/offline, installer/update and employee UX. 14. Produce APIs/events, repository structure, CI/CD plan, implementation backlog, pilot build plan and Stage 3 go/no-go gate. </required_workstreams> <output_contract> Update the workbook with sheets for agent architecture, OS capability matrix, module specification, state machine, security/key model, policy format, event and API contracts, technical spikes, performance budgets, threat model, test matrix, backlog, ADRs, gate and sources. Use Java/Spring contracts for cloud-facing APIs and native/Rust definitions for the agent. Every task requires owner, dependency, effort, deliverable and acceptance criterion. </output_contract> <validation> Validate that the proposed agent can be installed, registered, policy-controlled, started/paused/stopped visibly, operated offline, updated and rolled back without implementing unsafe broad capture. Demonstrate that no future capture component can bypass policy, secure-field exclusion, encryption, signing, audit or employee visibility. </validation>

## Foundation Dashboard
Foundation Dashboard — Stage 0 and Stage 1
Current state: research and draft artefacts are complete; formal Nessovo ownership, legal/DPO, worker, security, architecture and budget approvals remain outstanding.
Foundation KPI | Current value
Combined workplan maturity | 68.21%
Stage 0 workplan maturity | 65.29%
Stage 1 workplan maturity | 71.21%
Stage 0 gate readiness | 57.22%
Stage 1 gate readiness | 56.67%
Mandatory items not started/blocked | 5
Critical/high tasks below draft-ready | 16
Residual high/critical threats | 0
ADRs accepted in principle/accepted | 20
Registered research sources | 82
Stage | Maturity %
Stage 0 workplan | 65.2941 |  | Executive decision state
Stage 1 workplan | 71.2121 |  | Item | Current state
Combined foundation | 68.209 |  | Stage 0 foundation content | Draft package complete
|  |  | Stage 0 organisational approval | Pending legal/DPO/worker/security/leadership review
|  |  | Stage 1 research and architecture content | Draft package complete
|  |  | Stage 1 organisational approval | Pending architecture/licence/cost/resource review
|  |  | Entry to Stages 2 and 3 | Prompt-ready; gate approval still required
Immediate Nessovo decisions required before formal gate approval
Priority | Decision | Decision authority | Why now | Required evidence | Current status
1 | Name executive sponsor, product owner and programme lead. | CEO/CTO | No foundation gate can be accountable without named owners. | Named RACI. | Owner Input
2 | Commission UK and Pakistan/Lahore legal reviews and independent DPO advice. | CEO/Legal/DPO | Keystroke/screenshot/performance monitoring is high risk and jurisdiction-specific. | Legal memoranda and DPIA. | Owner Input
3 | Approve worker consultation approach and participant-protection rules. | HR/DPO/Executive Sponsor | Worker voice is required before the pilot design is frozen. | Consultation plan and record. | Draft Ready
4 | Confirm current HumanOS Java/Spring and foundation-service inventory. | CTO/Enterprise Architect | Technology and service boundaries depend on actual platform capability. | Platform inventory. | Open
5 | Approve proprietary-core versus commodity build/buy strategy. | CTO/Product/Legal | Stage 3 implementation and licences depend on this boundary. | Build/Buy matrix and licence review. | Draft Ready
6 | Approve reference architecture and initial deployment boundaries. | Architecture Board | Avoid duplicated HumanOS services and premature nano-services. | ADRs and architecture map. | In Review
7 | Provide pilot sizing, device, location, tool and retention assumptions. | Product/HR/IT/DPO | Cost, architecture and test planning require realistic inputs. | Resolved assumptions register. | Open
8 | Commit Stage 2–3 team, devices, security review and budget. | CEO/CTO/CFO | The next stages require cross-functional capacity, not engineering alone. | Resource plan. | Owner Input
Foundation package delivered in this workbook
Deliverable | Sheet | State
Master prompt and next-stage prompts | Master Prompts | Complete
Detailed action plan | Stage 0-1 Workplan | Complete
Product charter | Product Charter v1 | Draft complete
Purpose and data policy | Purpose Policy Matrix | Draft complete
Stakeholder accountability | Stakeholder RACI | Role-level draft
Market and OSS evidence | Market Landscape / GitHub OSS Scan | Research complete
Build/buy decisions | Build Buy Decisions | Draft complete
HumanOS architecture | Reference Architecture / Architecture Decisions | Draft complete
Approval gates | Stage 0-1 Gates | Criteria complete; approvals pending
Assumptions, threats and pilot | Assumptions Questions / Foundation Threats / Pilot Definition | Draft complete

## Stage 0-1 Workplan
Stage 0–1 Foundation Workplan
Combined Foundation & Validation workstream. Draft deliverables are complete where marked; real legal, worker, security and leadership approvals remain pending until Nessovo records them.
ID | Stage | Workstream | Task / Decision | Description | Accountable owner | Contributors | Dependencies | Priority | Status | Completion weight | Effort days | Deliverable | Acceptance criteria | Evidence / source | Gate | Target week | Notes
FND-001 | 0 | Programme governance | Confirm naming and product identity | Use Nessovo as the company name and HumanOS Work Intelligence as the working module name. | CEO/CTO | Product | None | Critical | Completed | 100% | 0.5 | Canonical naming decision | All foundation artefacts use Nessovo and no obsolete company name. | User instruction | Stage 0 Gate | W1 | Completed in workbook.
FND-002 | 0 | Programme governance | Appoint executive sponsor | Name the executive accountable for purpose, risk appetite and final foundation approvals. | CEO | Board/CTO | FND-001 | Critical | Requires Owner Input | 30% | 0.5 | Sponsor appointment | Named individual and authority recorded. | Internal decision | Stage 0 Gate | W1
FND-003 | 0 | Programme governance | Appoint product owner and programme lead | Assign accountable owners for product decisions and integrated delivery. | CEO/CTO | Product/PMO | FND-002 | Critical | Requires Owner Input | 30% | 1 | Named ownership | Product owner, programme lead and deputies recorded. | Internal decision | Stage 0 Gate | W1
FND-004 | 0 | Product strategy | Approve Product Charter v1 draft | Define the problem, vision, mission, value, scope, non-scope and strategic fit within HumanOS. | Product Owner | CEO/CTO/Architecture/HR | FND-001 | Critical | Draft Complete | 80% | 2 | Product Charter v1 | Charter contains purpose, beneficiaries, differentiation, principles, scope and kill criteria. | Product Charter v1 sheet | Stage 0 Gate | W1 | Leadership approval pending.
FND-005 | 0 | Product strategy | Confirm market positioning | Position as task execution assurance, capability development and human–AI work intelligence rather than surveillance software. | CEO/Product | Marketing/Legal/Employee Rep | FND-004 | Critical | Draft Complete | 80% | 1 | Positioning statement | Positioning clearly states employee and employer value and avoids activity-volume scoring. | Product Charter v1 / market research | Stage 0 Gate | W1
FND-006 | 0 | Employee value | Define employee value proposition | Specify how the product protects legitimate work, explains blockers, improves AI use, supports learning and allows correction. | Product/HR | L&D/Employee Rep | FND-004 | High | Draft Complete | 80% | 1.5 | Employee value proposition | At least five measurable employee benefits are defined. | Product Charter v1 | Stage 0 Gate | W1
FND-007 | 0 | Employer value | Define employer and team-lead value | Specify task assurance, quality, blocker, capability, coaching and organisational-learning outcomes. | Product | Operations/Engineering Leads | FND-004 | High | Draft Complete | 80% | 1 | Employer value proposition | Outcomes are evidence-based and separated from raw monitoring. | Product Charter v1 | Stage 0 Gate | W1
FND-008 | 0 | Product boundaries | Approve prohibited uses and non-goals | Exclude covert general monitoring, emotion/personality inference, automated employment decisions and activity-volume productivity scores. | Legal/DPO/Product | HR/Security/Employee Rep | FND-004 | Critical | Draft Complete | 80% | 1.5 | Prohibited-use register | All prohibited uses are explicit, testable and enforceable by policy. | Product Charter v1 / Purpose Policy Matrix | Stage 0 Gate | W1 | Formal legal approval pending.
FND-009 | 0 | Pilot scope | Define initial vertical and pilot cohort | Limit initial pilot to AI-assisted software development on company-managed devices. | Product/CTO | Engineering/HR | FND-004 | Critical | Draft Complete | 80% | 1 | Pilot scope statement | Roles, device types, task classes, exclusions and participant count assumptions are stated. | Pilot Definition sheet | Stage 0 Gate | W1
FND-010 | 0 | Ontology foundation | Approve foundation terminology | Define fact, inference, recommendation, assumption, task assurance, capability evidence and consequential decision. | Product/Architecture | Legal/AI/HR | FND-004 | High | Draft Complete | 80% | 1 | Canonical glossary | Terms are unambiguous and reused across artefacts. | Master Prompts / Product Charter v1 | Stage 0 Gate | W1
FND-011 | 0 | Privacy governance | Complete purpose-by-data matrix | Map every proposed data category to purpose, necessity, minimisation, access, retention and prohibited use. | DPO/Product | Security/Architecture/HR | FND-008 | Critical | Draft Complete | 80% | 3 | Purpose Policy Matrix | No data category exists without a defined purpose and minimisation rationale. | Purpose Policy Matrix sheet | Stage 0 Gate | W1 | DPO validation pending.
FND-012 | 0 | Privacy governance | Assess less intrusive alternatives | For every intrusive capture method, assess whether task artefacts or metadata can achieve the purpose first. | DPO/Product | Architecture/Employee Rep | FND-011 | Critical | Draft Complete | 80% | 2 | Alternatives assessment | Alternatives and residual necessity are documented per data type. | Purpose Policy Matrix sheet | Stage 0 Gate | W1
FND-013 | 0 | Privacy governance | Complete DPIA screening draft | Document why the intended keystroke/screenshot/performance use is high-risk and requires a full DPIA. | DPO | Legal/Product/Security | FND-011 | Critical | Draft Complete | 80% | 1 | DPIA screening record | High-risk triggers, affected people and initial risks are recorded. | ICO monitoring guidance | Stage 0 Gate | W1 | Formal DPO advice not yet recorded.
FND-014 | 0 | Privacy governance | Prepare full DPIA input pack | Provide processing description, necessity, risks, safeguards, consultation and residual-risk questions. | DPO | Legal/Security/Product | FND-013 | Critical | Draft Complete | 80% | 3 | DPIA working pack | Pack contains all information needed for an independent DPO/legal assessment. | Governance / Foundation Threats / Purpose Policy Matrix | Stage 0 Gate | W2
FND-015 | 0 | Privacy governance | Obtain and record DPO advice | Independent DPO reviews the DPIA, safeguards and whether the pilot may proceed. | DPO | Legal/Executive Sponsor | FND-014 | Critical | Not Started | 0% | 2 | DPO advice record | Advice, conditions, dissent and residual risks are signed and stored. | Independent review required | Stage 0 Gate | W2
FND-016 | 0 | Legal | UK legal basis and employment-law review | Confirm lawful basis, special-category conditions, interception rules, employment documentation and automated-decision safeguards. | UK Legal Counsel | DPO/HR | FND-014 | Critical | Requires Owner Input | 30% | 3 | UK legal memorandum | Legal counsel identifies permitted pilot scope, conditions and prohibited uses. | UK counsel / ICO / GOV.UK | Stage 0 Gate | W2 | Not legal advice in this workbook.
FND-017 | 0 | Legal | Pakistan/Lahore legal review scope | Commission a separate employment, privacy, interception and cross-border data review for Lahore operations. | Pakistan Legal Counsel | HR/DPO/Security | FND-014 | Critical | Requires Owner Input | 30% | 3 | Pakistan legal memorandum | Applicable laws, notices, consent/consultation, localisation and transfer requirements are documented. | Local counsel required | Stage 0 Gate | W2
FND-018 | 0 | Worker voice | Approve worker consultation plan | Define early consultation, representative participation, feedback capture and response commitments. | HR/DPO | Employee Rep/Product | FND-011 | Critical | Draft Complete | 80% | 1.5 | Consultation plan | Participants, timing, topics, confidentiality and decision-response process are defined. | ICO guidance / Pilot Definition | Stage 0 Gate | W1
FND-019 | 0 | Worker voice | Run and document worker consultation | Consult affected employees or representatives before pilot approval. | HR | DPO/Product/Employee Rep | FND-018 | Critical | Not Started | 0% | 3 | Consultation record | Views, objections, changes accepted/rejected and reasons are documented. | Consultation evidence | Stage 0 Gate | W2
FND-020 | 0 | Transparency | Draft worker privacy notice | Explain what is captured, why, when, who sees it, retention, rights, dispute and contact routes. | DPO/Legal | HR/Product | FND-011 | Critical | Draft Complete | 80% | 2 | Privacy notice outline | Notice is clear, accessible, task-specific and consistent with policy. | Governance sheet | Stage 0 Gate | W2 | Legal review pending.
FND-021 | 0 | Transparency | Draft workplace monitoring policy | Define scope, working hours, personal use, exclusions, manager access, prohibited uses and consequences of misuse. | HR/Legal | DPO/Security/Product | FND-020 | Critical | Draft Complete | 80% | 2 | Monitoring policy outline | Policy is consistent with charter, purpose matrix and employee notice. | Governance sheet | Stage 0 Gate | W2
FND-022 | 0 | Employee rights | Define access, correction and dispute workflow | Employees can view evidence, correct task attribution, explain context and request human review. | Governance Product Owner | DPO/HR/Workflow Team | FND-011 | Critical | Draft Complete | 80% | 2 | Rights workflow | States, deadlines, evidence preservation and reviewer authority are defined. | Governance / Reference Architecture | Stage 0 Gate | W2
FND-023 | 0 | Human review | Define meaningful human-review standard | Reviewers must understand evidence, consider context and have authority to reject AI recommendations. | HR/Legal/DPO | Domain Experts/Product | FND-022 | Critical | Draft Complete | 80% | 1.5 | Human-review standard | Reviewer qualifications, independence, reasoned decisions and override logging are defined. | ICO human-review guidance | Stage 0 Gate | W2
FND-024 | 0 | Access governance | Define raw evidence access model | Restrict screenshots/text/keystrokes by role, purpose code, task scope, time and audit. | Security/DPO | IAM/Audit/Product | FND-011 | Critical | Draft Complete | 80% | 2 | Evidence access policy | No default raw-content access; all access is purpose-limited and logged. | Purpose Policy Matrix / Reference Architecture | Stage 0 Gate | W2
FND-025 | 0 | Data governance | Define retention and deletion principles | Set short raw-evidence retention, longer derived-evidence retention and legal-hold controls. | DPO/Data Governance | Security/Product | FND-011 | Critical | Draft Complete | 80% | 1.5 | Retention schedule draft | Retention is purpose-based, configurable, auditable and supports deletion. | Purpose Policy Matrix | Stage 0 Gate | W2
FND-026 | 0 | Privacy engineering | Define secure-field and exclusion requirements | Block passwords, authentication codes, known secure controls, private apps/domains and out-of-hours capture. | Security/Desktop Lead | DPO/Product/QA | FND-011 | Critical | Draft Complete | 80% | 2 | Capture exclusion specification | Requirements are testable and designated as pilot blocking controls. | Purpose Policy Matrix / Foundation Threats | Stage 0 Gate | W2
FND-027 | 0 | Audit | Define purpose codes and immutable access audit | Every evidence access, AI assessment, review, policy change and skill change must record who, why and what. | Audit/Security | DPO/Platform | FND-024 | High | Draft Complete | 80% | 1.5 | Audit event specification | Required audit events and retention are enumerated. | Reference Architecture | Stage 0 Gate | W2
FND-028 | 0 | Incident response | Define privacy/security incident path | Specify containment, evidence preservation, employee notification, breach assessment and agent-disable path. | CISO/DPO | Platform/HR/Legal | FND-026 | Critical | Draft Complete | 80% | 2 | Incident playbook outline | Named escalation, stop switch and notification responsibilities are defined. | Foundation Threats | Stage 0 Gate | W2
FND-029 | 0 | Programme governance | Approve stop/hold criteria | Define conditions that automatically hold the pilot, including secret capture, high false-classification, excessive overhead or legal uncertainty. | Executive Sponsor | DPO/CISO/Product/Employee Rep | FND-014 | Critical | Draft Complete | 80% | 1 | Stop criteria | Criteria are measurable and linked to decision authority. | Pilot Definition / Stage 0-1 Gates | Stage 0 Gate | W2
FND-030 | 0 | Stakeholders | Complete stakeholder map and RACI | Assign accountability for charter, legal, architecture, security, worker consultation, pilot and review. | Programme Lead | All leads | FND-002,FND-003 | High | Draft Complete | 80% | 1.5 | RACI matrix | Every mandatory foundation deliverable has one accountable role. | Stakeholder RACI sheet | Stage 0 Gate | W1 | Names pending.
FND-031 | 0 | Security | Complete foundation threat model | Identify system, privacy, employment, endpoint, insider and AI-specific threats before design is approved. | CISO/Security Architect | DPO/Desktop/AI | FND-011 | Critical | Draft Complete | 80% | 3 | Foundation threat register | Threats have likelihood, impact, control, owner and validation plan. | Foundation Threats sheet | Stage 0 Gate | W2 | Security review pending.
FND-032 | 0 | Pilot ethics | Define participant protection | Specify voluntary/appropriate participation model, no adverse action from pilot output, employee access and direct support. | HR/DPO | Executive Sponsor/Product | FND-009,FND-018 | Critical | Draft Complete | 80% | 1.5 | Participant protection rules | Pilot participants receive notice, support, challenge rights and no automated adverse decisions. | Pilot Definition sheet | Stage 0 Gate | W2
FND-033 | 0 | Review | Run Stage 0 cross-functional review | Review charter, purpose matrix, DPIA pack, legal questions, threat model, consultation and pilot. | Programme Lead | CEO/CTO/DPO/Legal/CISO/HR/Employee Rep | FND-004:FND-032 | Critical | Not Started | 0% | 2 | Review minutes and actions | All mandatory objections and conditions are recorded. | Stage 0-1 Gates | Stage 0 Gate | W2
FND-034 | 0 | Gate | Record Stage 0 decision | Approve, conditionally approve, hold or reject entry into implementation planning. | Executive Sponsor | DPO/Legal/CISO/CTO/HR | FND-033 | Critical | Not Started | 0% | 0.5 | Stage 0 gate decision | Decision authority, conditions, dates and evidence are recorded. | Stage 0-1 Gates | Stage 0 Gate | W2
FND-035 | 1 | Market validation | Define market-category taxonomy | Separate employee monitoring, task mining, process intelligence, skills intelligence, developer intelligence, record/replay and AI observability. | Product Strategy | Research/Architecture | FND-004 | High | Completed | 100% | 1 | Category taxonomy | Competitors are compared within the correct category. | Market Landscape sheet | Stage 1 Gate | W1
FND-036 | 1 | Market validation | Research employee monitoring category | Document market baseline for screen, keystrokes, app/web, idle, privacy controls and reporting. | Product Strategy | Legal/Security | FND-035 | High | Completed | 100% | 1.5 | Monitoring competitor analysis | Capabilities, positioning and limits are source-backed. | Teramind / ActivTrak sources | Stage 1 Gate | W1
FND-037 | 1 | Market validation | Research task/process mining | Document action capture, workflow discovery, process variants and automation positioning. | Product Strategy | Operations/AI | FND-035 | High | Completed | 100% | 1.5 | Task-mining analysis | UiPath, ABBYY, Soroco and Workfellow are compared. | Market Landscape / Source Register | Stage 1 Gate | W1
FND-038 | 1 | Market validation | Research skills intelligence and learning | Compare inferred skills, evidence, employee review, learning plans and role readiness. | Product/HR/L&D | AI/Data | FND-035 | High | Completed | 100% | 1.5 | Skills-intelligence analysis | Skills platforms and Nessovo differentiation are recorded. | Market Landscape / Source Register | Stage 1 Gate | W1
FND-039 | 1 | Market validation | Research developer and AI-work intelligence | Compare engineering metrics, AI usage, code attribution, review, delivery and coaching. | Product/CTO | Engineering/AI | FND-035 | High | Completed | 100% | 1.5 | Developer-intelligence analysis | Relevant tools and limitations are recorded. | Market Landscape / Source Register | Stage 1 Gate | W1
FND-040 | 1 | Open-source due diligence | Complete GitHub reference scan | Inspect Screenpipe, ActivityWatch, OpenAdapt, Claude-Mem, Task Observer, WakaTime and standards projects. | Architecture/Engineering | Legal/Security | FND-035 | Critical | Completed | 100% | 3 | GitHub OSS scan | Each project has maturity, relevance, licence and reuse recommendation. | GitHub OSS Scan sheet | Stage 1 Gate | W1
FND-041 | 1 | Open-source due diligence | Verify initial licence posture | Record commercial-use constraints and identify items needing legal licence review. | Legal/Architecture | Procurement/Product | FND-040 | Critical | Draft Complete | 80% | 2 | Licence register draft | No project is recommended for incorporation without a recorded licence decision. | GitHub OSS Scan / repository licences | Stage 1 Gate | W1 | Formal legal opinion pending.
FND-042 | 1 | Strategy | Complete market gap matrix | Compare capture, task assurance, provenance, capability, coaching, training, self-improvement and governance. | Product Strategy | Architecture/HR/AI | FND-036:FND-041 | Critical | Draft Complete | 80% | 2 | Gap matrix | Differentiation is stated as a capability combination, not unsupported novelty. | Gap Matrix sheet | Stage 1 Gate | W1
FND-043 | 1 | Strategy | Approve strategic differentiation | Define the proprietary core: evidence graph, task assurance, capability evidence, Growth Coach and Skill Forge. | CEO/Product/CTO | Architecture/HR | FND-042 | Critical | Draft Complete | 80% | 1 | Differentiation decision | Build focus and commodity capabilities are separated. | Product Charter v1 / Build Buy Decisions | Stage 1 Gate | W1 | Leadership review pending.
FND-044 | 1 | Architecture | Create capability-domain map | Map product capabilities to HumanOS services and new bounded contexts. | Enterprise Architect | Product/Platform/AI | FND-043 | Critical | Draft Complete | 80% | 2 | Capability-to-service map | Every capability has a system of record and integration boundary. | Reference Architecture / Microservices Map | Stage 1 Gate | W1
FND-045 | 1 | Architecture | Complete build/buy/integrate/defer matrix | Make component-level decisions based on differentiation, risk, maturity and licence. | CTO/Architecture | Product/Legal/Procurement | FND-040,FND-043 | Critical | Draft Complete | 80% | 2.5 | Build Buy Decisions | Each component has a recommendation, rationale, risk and revisit trigger. | Build Buy Decisions sheet | Stage 1 Gate | W1 | Final procurement/legal review pending.
FND-046 | 1 | Architecture | Define reference architecture layers | Define device edge, ingestion, evidence, intelligence, capability, coaching, governance and reporting. | Enterprise Architect | Security/Data/AI/Desktop | FND-044 | Critical | Draft Complete | 80% | 3 | Reference architecture | Components, runtimes, data, events and HumanOS reuse are explicit. | Reference Architecture sheet | Stage 1 Gate | W1
FND-047 | 1 | Architecture | Set bounded contexts and deployment granularity | Avoid premature splitting; identify initial deployables and future split triggers. | Enterprise Architect | Backend/Platform/SRE | FND-046 | Critical | Draft Complete | 80% | 2 | Service-boundary decision | Each boundary has ownership, scale, security or transactional justification. | Reference Architecture / ADR-012 | Stage 1 Gate | W1
FND-048 | 1 | Technology | Approve Java/Python/native responsibility split | Use Java for durable domain services, Python for AI/evals and native code for endpoint capture. | CTO/Architecture | Java/Python/Desktop Leads | FND-046 | Critical | Draft Complete | 80% | 1.5 | Runtime decision | Responsibility boundaries and interface contracts are stated. | Reference Architecture / ADRs | Stage 1 Gate | W1
FND-049 | 1 | Technology | Assess Java and Spring baseline | Retain current supported HumanOS baseline unless migration is justified; benchmark Java 25/Spring Boot 4.1 for greenfield-compatible services. | Java Platform Lead | Architecture/SRE/Security | FND-048 | High | Draft Complete | 80% | 1.5 | Java baseline recommendation | Compatibility, support, security and migration criteria are recorded. | Spring/OpenJDK sources | Stage 1 Gate | W1
FND-050 | 1 | Event architecture | Define event streaming and schema strategy | Use Kafka-compatible streaming, versioned contracts, idempotency and CloudEvents-style envelope. | Data/Platform Architect | Backend/SRE | FND-046 | Critical | Draft Complete | 80% | 2 | Event architecture decision | Partitioning, ordering, retry, schema and replay principles are defined. | Apache Kafka / CloudEvents | Stage 1 Gate | W1
FND-051 | 1 | Policy and observability | Define OPA and OpenTelemetry usage | Use policy-as-code where it adds value; keep evidence content out of operational traces by default. | Security/Platform Architect | SRE/AI/DPO | FND-046 | High | Draft Complete | 80% | 2 | Policy/observability design | Decision and data boundaries are explicit and sensitive content is opt-in only. | OPA / OpenTelemetry sources | Stage 1 Gate | W1
FND-052 | 1 | Data architecture | Select initial data stores | Use PostgreSQL and object storage first; add vector/search capability as justified; defer graph database until query evidence. | Data Architect | Backend/AI/SRE | FND-046 | Critical | Draft Complete | 80% | 2 | Data-store decision | System-of-record, retention, indexing and future split triggers are stated. | Reference Architecture / ADR-009 | Stage 1 Gate | W1
FND-053 | 1 | Workflow architecture | Confirm HumanOS workflow-runtime reuse | Use existing workflow capabilities for review, coaching, gates and skill lifecycle before adding another orchestrator. | Platform Architect | Workflow Team/Product | FND-046 | High | Draft Complete | 80% | 1 | Orchestration decision | Known runtime gaps and trigger for alternative evaluation are documented. | HumanOS architecture assumption | Stage 1 Gate | W1
FND-054 | 1 | AI architecture | Define evaluator and provenance architecture | Separate deterministic evidence processing from model inference; version prompts, skills, models and confidence. | AI Architect | Data/Product/Governance | FND-046 | Critical | Draft Complete | 80% | 2.5 | AI evaluation architecture | All material findings link to evidence, model/skill version and human-review state. | Reference Architecture / NIST AI RMF | Stage 1 Gate | W2
FND-055 | 1 | Device architecture | Define device-agent foundation principles | Separate edge agent, local policy, encrypted journal, signed batches, health, update and user-visible controls. | Desktop Architect | Security/Platform/DPO | FND-046 | Critical | Draft Complete | 80% | 2.5 | Device-agent architecture principles | Foundation is sufficient to scope Stage 3 without implementing unsafe capture. | Reference Architecture / Foundation Threats | Stage 1 Gate | W2
FND-056 | 1 | Economics | Collect data-volume and usage assumptions | Obtain employee count, active hours, screenshot frequency, retention, regions and AI-analysis volume. | Product Finance | SRE/Data/Product | FND-009,FND-046 | High | Requires Owner Input | 30% | 1.5 | Cost-model inputs | Assumptions are approved and sensitivity ranges are provided. | Assumptions Questions sheet | Stage 1 Gate | W2
FND-057 | 1 | Economics | Produce preliminary cost model | Estimate endpoint, ingestion, storage, AI inference, observability and support costs. | FinOps/SRE | Data/AI/Product | FND-056 | High | Not Started | 0% | 2.5 | Cost and sensitivity model | Low/base/high pilot and scale cases are calculated. | Requires usage assumptions | Stage 1 Gate | W2
FND-058 | 1 | Legal/procurement | Complete formal OSS/commercial licence review | Counsel reviews source-available and OSS dependencies before reuse, modification or distribution. | Legal/Procurement | Architecture/Security | FND-041,FND-045 | Critical | Requires Owner Input | 30% | 3 | Licence approval register | Each dependency has approved use conditions or is excluded. | Repository licence files / counsel | Stage 1 Gate | W2
FND-059 | 1 | Technical validation | Plan screen-capture benchmark | Benchmark native prototype against Screenpipe/OpenAdapt patterns without assuming code reuse. | Desktop Lead | Architecture/Legal/QA | FND-045,FND-055 | High | Draft Complete | 80% | 1.5 | Benchmark plan | Metrics, datasets, legal constraints and decision thresholds are defined. | Build Buy Decisions / Pilot Definition | Stage 1 Gate | W2
FND-060 | 1 | Technical validation | Define Stage 2–3 spike backlog | Specify ontology and device-agent spikes that reduce the highest uncertainty first. | Programme/Architecture | Product/Desktop/AI | FND-046:FND-055 | Critical | Draft Complete | 80% | 2 | Next-stage spike backlog | Each spike has hypothesis, method, metric, owner and decision rule. | Master Prompts / Architecture Decisions | Stage 1 Gate | W2
FND-061 | 1 | Security review | Run architecture threat review | Review endpoint, event, evidence, identity, model, manager-access and supply-chain risks. | CISO/Security Architect | DPO/Architecture/Desktop/AI | FND-031,FND-046 | Critical | In Review | 60% | 2 | Security review record | Critical threats have blocking controls and verification plans. | Foundation Threats | Stage 1 Gate | W2 | Named reviewers pending.
FND-062 | 1 | Architecture governance | Review and accept ADR set | Architecture board reviews core decisions and unresolved alternatives. | Architecture Board | CTO/Platform/Data/AI/Security | FND-046:FND-055 | Critical | In Review | 60% | 2 | Accepted ADR register | Each ADR is accepted, rejected or returned with actions. | Architecture Decisions sheet | Stage 1 Gate | W2
FND-063 | 1 | Research traceability | Complete source register | Record official product, repository, standard, legal and prompt-engineering sources. | Research Lead | Product/Architecture/Legal | FND-035:FND-055 | High | Completed | 100% | 1.5 | Source register | Every material researched claim can be traced to a URL. | Source Register sheet | Stage 1 Gate | W2
FND-064 | 1 | Resourcing | Approve team and budget envelope | Confirm Stage 2–3 staffing, environment, devices, security review and pilot budget. | CEO/CTO/CFO | Programme/HR/Procurement | FND-056,FND-060 | Critical | Requires Owner Input | 30% | 2 | Approved resource envelope | Named team, availability, procurement and funding are recorded. | Internal decision | Stage 1 Gate | W2
FND-065 | 1 | Review | Run Stage 1 architecture and build/buy review | Review research, licences, architecture, threats, spikes, costs and ownership. | CTO/Architecture Board | Product/Legal/CISO/DPO/Engineering | FND-045:FND-064 | Critical | Not Started | 0% | 2 | Review minutes and actions | All mandatory objections and conditions are recorded. | Stage 0-1 Gates | Stage 1 Gate | W2
FND-066 | 1 | Gate | Record Stage 1 decision | Approve, conditionally approve, hold or reject entry into Stage 2 and Stage 3. | CTO/Executive Sponsor | Architecture Board/DPO/CISO/Legal/Product | FND-065 | Critical | Not Started | 0% | 0.5 | Stage 1 gate decision | Decision, conditions, owners and due dates are recorded. | Stage 0-1 Gates | Stage 1 Gate | W2
FND-067 | 1 | Handoff | Issue Stage 2 and Stage 3 execution prompts | Provide exact prompts and workbook output contracts for ontology and device-agent foundation. | Programme Lead | Product/Architecture | FND-060 | High | Draft Complete | 80% | 1 | Stage 2 and 3 prompts | Prompts contain context, constraints, deliverables, validation and Excel contract. | Master Prompts sheet | Stage 1 Gate | W2 | Included in this workbook.

## Product Charter v1
Product Charter v1 — HumanOS Work Intelligence
Decision-ready Stage 0 charter draft. This defines the strategic intent and mandatory product boundaries; it is not an employment-policy or legal approval.
ID | Charter section | Draft decision | Rationale | Accountable owner | Status | Approval evidence | Metric / note
CHR-001 | Company | Nessovo | Canonical company name supplied by the founder. | CEO | Confirmed | User instruction
CHR-002 | Platform | HumanOS | Work Intelligence is a HumanOS module, not an isolated workforce-surveillance product. | CEO/CTO | Draft Complete | Leadership approval pending | Reuse foundation services.
CHR-003 | Working module name | HumanOS Work Intelligence | Conveys execution understanding, assurance, development and organisational learning. | Product | Draft Complete | Brand review pending | Working name only.
CHR-004 | One-sentence definition | A task-aware human-and-AI work intelligence system that reconstructs material work evidence, assures task outcomes, develops employee capability and improves HumanOS operating skills. | Product | Draft Complete | Charter approval | Must remain valid across business verticals.
CHR-005 | Problem | Organisations can see outputs and time records but often cannot reliably explain how work was performed, whether required outcomes were met, where blockers occurred, or what capability development is needed. | Product Strategy | Draft Complete | Market validation | Avoid equating activity with performance.
CHR-006 | Vision | Create an evidence-backed operating layer through which HumanOS helps people and AI perform work more correctly, transparently and progressively. | CEO | Draft Complete | Leadership approval | Long-term HumanOS fit.
CHR-007 | Mission | Observe approved work, connect it to tasks and outcomes, explain provenance, coach people, verify capability and convert validated learning into reusable HumanOS skills. | Product | Draft Complete | Charter approval
CHR-008 | Primary initial user | AI-assisted software-development employee using company-managed Windows or macOS device. | Product/CTO | Draft Complete | Pilot approval | Initial vertical only.
CHR-009 | Secondary users | Team leads, technical reviewers, HR/L&D, security/governance, product and architecture teams. | Product | Draft Complete | RACI and access policy | Each role receives minimum necessary data.
CHR-010 | Employee value | Fair attribution of work and automated waits; faster blocker resolution; transparent evidence; contextual coaching; skill progression; correction and challenge rights. | HR/Product | Draft Complete | Worker consultation | Pilot must measure employee benefit.
CHR-011 | Employer value | Task completion assurance, quality evidence, blocker analysis, capability visibility, targeted training, safer AI-agent use and reusable organisational knowledge. | Product/Operations | Draft Complete | Leadership review | Exception-led reporting, not raw firehose.
CHR-012 | Strategic differentiator | Combine universal work evidence, task acceptance criteria, human/AI provenance, capability evidence, adaptive learning and governed self-improvement in one HumanOS operating model. | CEO/CTO/Product | Draft Complete | Market gap review | Individual components already exist elsewhere.
CHR-013 | North-star outcome | Increase verified, independently completed, high-quality task outcomes while improving employee capability and reducing repeated errors and rework. | Product | Draft Complete | KPI approval | No single productivity score.
CHR-014 | Initial commercial position | Task execution assurance and capability development; monitoring is an underlying evidence mechanism rather than the headline value. | CEO/Product | Draft Complete | Go-to-market review | Avoid bossware positioning.
CHR-015 | Initial vertical | Software engineering, QA, DevOps/platform and related AI-assisted technical work. | CTO/Product | Draft Complete | Pilot approval | Best objective evidence: Git, tests, builds, reviews.
CHR-016 | Future vertical model | Domain-neutral core ontology plus vertical-specific evidence adapters, task templates, evaluators and coaching skills. | Enterprise Architecture | Draft Complete | Architecture board | Finance, support, design and operations can be added later.
CHR-017 | In scope v1 | Task sessions, application/window/process evidence, event-driven visual states, approved text changes, files/Git/terminal, AI-agent hooks, task assurance, employee review and pilot capability evidence. | Product/CTO | Draft Complete | Pilot scope | Controlled internal pilot.
CHR-018 | Out of scope v1 | Audio recording, personal devices, covert mode, global Linux parity, continuous full-motion video, automatic discipline/pay/promotion, broad network payload capture and emotion/personality inference. | Product/DPO/CISO | Draft Complete | Stage 0 approval | Any future inclusion needs new assessment.
CHR-019 | Principle | Outcome over activity | Clicks, keystrokes and hours cannot substitute for quality and acceptance-criteria evidence. | Product | Draft Complete | Policy acceptance
CHR-020 | Principle | Evidence before inference | Authoritative artefacts and system results outrank screenshots and AI interpretations. | AI/Data | Draft Complete | Evidence hierarchy
CHR-021 | Principle | Human, AI and automation provenance | Modern work must distinguish directing, generating, reviewing, rejecting and verifying. | AI/Architecture | Draft Complete | ADR acceptance
CHR-022 | Principle | Employee visibility and agency | Employees must know when capture is active, see their evidence and correct context. | DPO/HR | Draft Complete | Worker consultation
CHR-023 | Principle | Minimum necessary evidence | Prefer semantic artefacts and event-driven capture over unrestricted content collection. | DPO/Security | Draft Complete | Purpose matrix
CHR-024 | Principle | Meaningful human review | AI findings inform but do not make consequential employment decisions. | HR/Legal | Draft Complete | Review policy
CHR-025 | Principle | Learning, not punishment | Capability gaps should first lead to explanation, support, training and reassessment unless separate misconduct evidence exists. | HR/L&D | Draft Complete | HR policy
CHR-026 | Principle | Self-improvement under governance | HumanOS skills may improve only through evidence, evaluation, approval, canary deployment and rollback. | AI Platform | Draft Complete | Skill lifecycle policy
CHR-027 | Pilot success | Demonstrate accurate task attribution and provenance, useful coaching, manager usefulness, employee trust, secure capture and acceptable endpoint overhead. | Programme Lead | Draft Complete | Pilot Definition | Measured through pilot KPIs.
CHR-028 | Pilot failure/hold | Hold when secrets are captured, legal basis is unresolved, false conclusions are excessive, employee rights are not operational, endpoint impact is unacceptable or coaching has no measurable value. | Executive Sponsor | Draft Complete | Stage 0 gate | Immediate stop authority required.
CHR-029 | Consequential-decision boundary | No pilot output may independently determine dismissal, discipline, promotion, pay or probation. | HR/Legal | Draft Complete | Stage 0 approval | Human review plus other evidence required.
CHR-030 | Ownership of evidence | Nessovo is controller for approved workplace processing; access is purpose-limited, employee-visible and audited. Exact legal roles require counsel confirmation. | DPO/Legal | Draft Complete | Legal review pending | Do not treat acknowledgement alone as lawful basis.
CHR-031 | Data location | Prefer edge processing and regional storage; cross-border flows require explicit mapping and legal assessment. | DPO/Security | Draft Complete | Architecture/legal approval
CHR-032 | Release model | Internal controlled pilot → limited production → vertical expansion only after evidence and governance gates. | CEO/CTO | Draft Complete | Programme governance | No broad rollout from prototype.
CHR-033 | Decision status | Foundation package is drafted; Stage 0 and Stage 1 remain formally unapproved until recorded in the gate register. | Programme Lead | Confirmed | Stage 0-1 Gates | Honesty control.

## Purpose Policy Matrix
Purpose Policy Matrix
Stage 0 data-governance draft. Each category must have a specific approved purpose, necessity test, minimisation rule, access boundary and retention decision before collection begins.
ID | Data / activity category | Approved purpose | Task scope | Necessity rationale | Less-intrusive alternative | Minimisation / edge control | Allowed uses | Prohibited uses | Default retention proposal | Employee visibility | Permitted access roles | Pilot decision | Source / approval need
PPM-001 | Device and session identity | Authenticate managed device, person and approved work session. | Working day / selected task | Required to bind evidence to a legitimate session and policy. | Manual timesheet alone cannot establish trusted device or policy state. | Pseudonymous internal IDs in event payload; direct identity resolved through HumanOS IAM. | Session control, evidence integrity, audit. | Tracking personal devices or out-of-scope hours. | Session metadata: 24 months; review during DPIA. | Always visible in employee timeline. | Employee, direct manager summary, governance, security. | Include | HumanOS IAM / DPO approval
PPM-002 | Application and window metadata | Understand work context, task switching and relevant tool use. | Active approved session | Lower-intrusion context signal that reduces dependence on screenshots. | Self-declared task switching; file/Git evidence only. | Capture process/app ID and approved title fields; redact titles by policy. | Task alignment, blocker explanation, tool support. | Productivity ranking by app name alone; personal-app profiling. | Derived episodes 12 months; raw events 30–90 days pilot. | Visible to employee; manager sees episodes by default. | Employee, task reviewer, governance; raw title access restricted. | Include | ActivityWatch pattern / DPIA
PPM-003 | Browser tab, title, domain and approved URL | Classify documentation, testing, project tools and task-related research. | Approved browser profiles during session | Browser context can explain research and web-based work. | Domain only; browser extension task bookmarks. | Default domain/title; URL path/query captured only for allowlisted systems. | Task support classification, evidence links, browser workflow coaching. | Personal browsing content, health/financial/political profiling. | Raw 30 days; derived classification 12 months. | Full own timeline; managers receive domain/category unless investigation approved. | Employee, task reviewer, governance. | Conditional include | Chrome extension permissions / DPO review
PPM-004 | Event-driven screenshots / visual states | Reconstruct material screen transitions, errors and context where semantic events are insufficient. | Approved apps and monitors during task session | Provides evidence for otherwise opaque desktop tools, but is highly intrusive. | Accessibility tree, structured app/terminal/file events. | Capture only on material change; deduplicate; changed regions; exclude apps/monitors; local redaction. | Evidence replay, error diagnosis, dispute resolution, coaching with confidence. | Continuous manager live viewing; personal-content browsing; facial/emotion analysis. | Raw pilot default 7–30 days; derived thumbnails/links longer only when justified. | Employee can view all retained screenshots. | Employee; authorised reviewer on task; governance/security by purpose code. | Conditional include | Screenpipe/OpenAdapt patterns; DPIA mandatory
PPM-005 | Mouse clicks, scrolls and coordinates | Connect action edges between visual/UI states and identify user-initiated transitions. | Approved session | Useful for reconstructing action sequence; volume is not evidence of productivity. | Accessibility/control events and app semantic events. | Event type, coordinates/control only; no raw movement path unless needed for UX research. | Causal timeline, workflow reconstruction, accessibility debugging. | Click-rate scoring, behavioural/personality inference. | Raw 30 days; aggregated episode facts 12 months. | Visible in own event detail. | Employee, authorised technical reviewer. | Include metadata | UiPath/OpenAdapt patterns / policy approval
PPM-006 | Keyboard event metadata | Distinguish active human input, shortcuts, paste, automation and idle states. | Approved non-secure controls | Required for provenance, but raw keys are highly intrusive. | Resulting text deltas, IDE/file events, command history. | Block secure fields; collect categories and timing by default; raw key values only for specifically approved controls. | Human/automation attribution, shortcut/paste classification, task reconstruction. | Key-volume productivity scoring; password/authentication-code capture; personal message capture. | Raw values shortest possible, proposed 7 days or less; metadata 30 days. | Employee access; explicit indicator and policy. | Employee; restricted reviewer under purpose code. | Conditional, narrow | ICO identifies keystroke monitoring as high risk
PPM-007 | Resulting text changes | Understand what text/code was actually inserted, deleted, pasted or generated. | Allowlisted work controls/files | More accurate than raw keylogging and necessary for task/quality evaluation in supported tools. | Git/file diffs; app-level change APIs. | Capture text deltas only in allowlisted work surfaces; encrypt separately; redact secrets locally. | Task evidence, quality checks, AI/human attribution, coaching. | Personal communications; unrestricted cross-application text archive. | Raw content 7–30 days pilot; authoritative artefact governed by source system. | Employee sees captured deltas and source. | Employee, authorised domain reviewer; manager gets summary by default. | Conditional include | Secure-field and DLP validation required
PPM-008 | Clipboard events/content | Distinguish paste from typing and identify transfer of task material. | Allowlisted work apps | Event metadata supports provenance; content is rarely necessary. | Paste shortcut plus resulting text delta. | Capture paste event, source/target app category; content off by default. | Provenance and data-loss controls when separately authorised. | Routine clipboard-content collection; secrets or personal content. | Event metadata 30 days; content none by default. | Visible in event timeline. | Employee; security only under separate policy. | Metadata only | DPO/CISO approval required for content
PPM-009 | Files, repository and Git changes | Establish authoritative work artefacts and code-change provenance. | Approved project folders/repos | High-value, relatively targeted evidence for technical tasks. | Manual employee evidence submission. | Approved roots only; store hashes/diffs/metadata according to project classification. | Task completion, quality, review, capability evidence. | Accessing unrelated personal folders; treating line count as productivity. | Follow project retention; event metadata 24 months. | Employee sees all linked artefacts. | Employee, project reviewers, authorised managers. | Include | Git/source systems are preferred evidence
PPM-010 | Terminal commands, process tree and outputs | Explain builds, tests, scripts, AI-agent actions, failures and automated waits. | Approved shells/workspaces | Necessary to distinguish user work from computer execution and verify results. | Process start/exit metadata only; test/CI results. | Capture command and selected output in approved work contexts; redact environment variables/secrets. | Task evidence, debugging, automated-wait classification, coaching. | Capturing unrelated shell history or secrets; command-count scoring. | Raw output 30 days; verified result 12–24 months. | Employee access to command timeline. | Employee, technical reviewer, security under purpose. | Include with redaction | Shell integration / DLP testing
PPM-011 | AI-agent prompts, tool calls and generated changes | Attribute human direction, agent actions, tool execution and review decisions. | Approved AI tools and task sessions | Core differentiator for human–AI work understanding. | File/process changes alone, which lose intent and agent causality. | Use official hooks; content policy and secret scanning; separate operational traces from evidence. | AI supervision coaching, provenance, task assurance, prompt improvement. | Ranking employees by prompt count; unrestricted model-content logging. | Prompt/tool evidence 30–90 days; derived skill observations 12 months. | Employee sees own agent sessions and assessments. | Employee, technical reviewer, AI governance. | Include | Codex hooks / Claude hooks / OTel GenAI sensitivity warning
PPM-012 | Idle and return events | Distinguish absence from active work and automated execution wait. | Approved working session | Needed for time allocation, but must be contextual. | Self-reported breaks; app/process state only. | Threshold-based metadata; no assumption of poor performance; check builds/agents/meetings first. | Session integrity, break reminders, automated-wait classification. | Automatic misconduct conclusion; disability/accommodation inference. | Raw 90 days; derived time allocation 12 months. | Employee sees and can correct classification. | Employee, manager summary, governance. | Include | ActivityWatch pattern / fairness requirement
PPM-013 | Network metadata | Diagnose application/service failures and confirm approved system interactions. | Approved applications; no payload | Limited metadata may explain blockers; payload capture is excessive for v1. | Application logs and browser events. | Domain/endpoint category and status only; no packet payload/content by default. | Technical diagnostics, security alerts under separate controls. | General browsing surveillance; content interception. | 30 days diagnostic metadata. | Visible when used in task report. | Technical support/security by purpose. | Defer except diagnostics | Separate interception/legal assessment
PPM-014 | Audio, microphone and meeting content | Potential future meeting/task context. | Not in v1 | Highly intrusive and not necessary for initial software-development pilot. | Calendar, meeting metadata, user notes. | No collection in v1. | None in v1. | Any audio capture. | None. | Not applicable. | None. | Exclude v1 | New DPIA and policy required for future use
PPM-015 | Work episodes and task-alignment classifications | Convert raw events into understandable task activity with confidence. | Approved session/tasks | Required for usable reporting; derived inference must remain challengeable. | Manual task diary. | Store evidence links, confidence, alternatives and model/skill version. | Employee coaching, task report, blocker analysis. | Presenting low-confidence classification as fact; automatic discipline. | 12–24 months subject to employment policy. | Employee sees and can correct. | Employee, manager, reviewer, governance. | Include | NIST AI RMF / human-review policy
PPM-016 | Task-quality and acceptance-criteria assessments | Determine whether required outcomes were evidenced and verified. | Approved task contract | Core product purpose and more meaningful than activity metrics. | Manual reviewer only. | Combine deterministic checks with AI inference; preserve evidence and missing-data flags. | Task assurance, quality coaching, reviewer support. | Automatic employment action; claims beyond task contract. | Task/project retention; assessment history 24 months proposed. | Employee sees evidence and can respond. | Employee, task reviewer, manager, governance. | Include | Human review mandatory
PPM-017 | Capability evidence and role-readiness state | Track demonstrated capability, gaps, learning needs and progression. | Repeated tasks and assessments | Core employee-development purpose but high impact; requires cautious longitudinal model. | Manager judgement and formal assessment only. | Use multiple evidence items, context, confidence, recency and contradictions; no protected-trait inference. | Learning plans, role development, supported workforce planning. | Single-task permanent labels; deception claims; solely automated hiring/firing/promotion. | Capability state while employed plus defined post-employment retention; legal review. | Employee sees claims, evidence, level and can challenge. | Employee, HR/L&D, authorised manager, human reviewer. | Conditional include | Stage 2 ontology and legal/fairness review
PPM-018 | Coaching interventions and responses | Help employees recover from errors, use AI safely and apply effective methods. | Current task and learning plan | Direct employee benefit and product differentiation. | On-demand assistant only. | Confidence thresholds, cooldowns, user controls, no sensitive employment labels in prompt context. | Nudge, assist, teach, mentor escalation; training effectiveness. | Harassment, constant interruption, punitive nudges, covert behavioural manipulation. | 12 months for effectiveness; content minimised. | Employee sees and controls coaching history. | Employee, L&D; manager sees agreed summary. | Include later | Stage 9; employee UX testing
PPM-019 | Manager reports and exceptions | Provide evidence-linked outcome, blocker, quality and support information. | Direct reports and assigned tasks | Needed for operational management, but raw evidence is not the default. | Existing task status reports. | Summaries first; raw drill-down restricted; show confidence and employee response. | Task support, workload, review and training decisions with human judgement. | Continuous live surveillance; public leaderboards; unsupported allegations. | Report retention aligned to employment/project policy. | Employee can view material reports about them. | Direct manager, authorised reviewer, HR where necessary. | Include | Human-review/access policy
PPM-020 | Skill and system-improvement observations | Improve HumanOS prompts, skills, evaluators and workflows from validated patterns and corrections. | De-identified/generalised where possible | Core organisational-learning purpose; must not leak confidential or personal data. | Manual retrospective process. | Generalise before reuse; separate internal/open-source; evaluate, approve, canary and rollback. | Propose skill updates, standards and training content. | Automatic production changes; publishing confidential employee/project data. | Observation and version history according to platform policy. | Employees see use of their feedback and attribution policy. | Skill reviewers, AI platform, governance. | Include later | Claude-Mem / Task Observer patterns

## Stakeholder RACI
Stakeholder RACI — Stage 0 and Stage 1
R = responsible, A = accountable, C = consulted, I = informed. Named individuals must replace role placeholders before either foundation gate can be approved.
ID | Deliverable / decision | Executive sponsor | Product owner | Programme lead | CTO / Architecture Board | DPO / Legal | CISO / Security | HR / L&D | Employee representative | Engineering leads | Finance / Procurement | Domain / manager reviewers | Notes
RACI-001 | Product Charter v1 | A | R | C | C | C | C | C | C | I | I | C | Executive purpose and risk appetite.
RACI-002 | Strategic positioning | A | R | C | C | C | I | C | C | I | I | C | Must preserve employee value and avoid bossware framing.
RACI-003 | Purpose Policy Matrix | I | C | C | C | A/R | C | C | C | C | I | I | DPO accountability.
RACI-004 | DPIA and lawful-basis review | I | C | C | I | A/R | C | C | C | I | I | I | Independent DPO/legal review.
RACI-005 | Worker consultation | I | C | C | I | C | I | A/R | R | I | I | I | Views and organisational response documented.
RACI-006 | Monitoring/privacy policy | I | C | C | I | A | C | R | C | I | I | I | Legal and HR approval.
RACI-007 | Employee access and dispute workflow | I | R | C | C | A | C | R | C | C | I | I | HumanOS workflow implementation later.
RACI-008 | Meaningful human-review standard | I | C | C | I | A | C | R | C | I | I | R | Reviewers require authority and domain competence.
RACI-009 | Threat model and security controls | I | C | C | C | C | A/R | I | C | R | I | I | Security gate.
RACI-010 | Pilot definition and participant protection | A | R | C | C | C | C | R | C | C | C | C | No adverse action from pilot-only output.
RACI-011 | Stage 0 cross-functional review | A | R | R | C | C | C | C | C | I | I | I | Programme lead coordinates.
RACI-012 | Stage 0 gate decision | A/R | C | C | C | C | C | C | I | I | I | I | Conditions recorded.
RACI-013 | Market and category research | I | A/R | R | C | C | I | C | I | C | I | C | Source-backed.
RACI-014 | GitHub and licence scan | I | C | C | A/R | C | C | I | I | R | C | I | Formal legal licence approval remains separate.
RACI-015 | Build/buy/integrate decisions | I | R | C | A | C | C | I | I | C | R | C | Commercial and technical decision.
RACI-016 | Reference architecture | I | C | C | A/R | C | C | I | I | R | I | C | Must reuse HumanOS foundation.
RACI-017 | Architecture Decision Records | I | C | C | A/R | C | C | I | I | R | I | I | Architecture Board approval.
RACI-018 | Data-volume and cost model | I | C | C | C | I | I | I | I | C | A/R | C | Input assumptions required.
RACI-019 | Stage 2–3 team and budget | A | C | R | C | I | I | C | I | C | R | I | Leadership allocation.
RACI-020 | Stage 1 architecture review | I | C | R | A/R | C | C | I | I | C | C | C | All major risks and alternatives reviewed.
RACI-021 | Stage 1 gate decision | A | C | C | R | C | C | I | I | I | C | I | Entry to Stage 2 and 3.
RACI-022 | Stage 2 and 3 prompt handoff | I | A | R | C | C | C | C | I | C | I | C | Prompts stored in Master Prompts.

## Build Buy Decisions
Build / Buy / Integrate Decisions
Stage 1 recommendations. Legal licence review, procurement and technical spikes remain mandatory before incorporating third-party code or signing commercial agreements.
ID | Component / capability | Need | Relevant reference | Options considered | Recommendation | Nessovo differentiation | Rationale | Licence / security note | Delivery stage | Revisit trigger | Accountable owner | Source URL
BBD-001 | Universal desktop observation engine | Capture app/window, visual states, input provenance and endpoint context. | Screenpipe, OpenAdapt, ActivityWatch, commercial monitoring tools | Build; license; fork; combine native APIs | Build proprietary core; benchmark references | Medium | Capture is foundational, security-sensitive and tightly coupled to Nessovo policy/provenance. Reference implementations reduce discovery risk but do not satisfy full requirements. | Screenpipe commercial-use licence; OpenAdapt experimental; OS permissions and signing are critical. | 3–5 | A commercial component proves safer, lower-overhead and contractually suitable. | Desktop Architect | https://github.com/screenpipe/screenpipe
BBD-002 | Application/window/AFK watcher | Low-intrusion context and session state. | ActivityWatch | Reuse protocol/pattern; incorporate code; build | Build compatible pattern; inspect MPL obligations | Low | Commodity capability; architecture and watcher pattern are useful. | MPL-2.0 obligations require legal review if code is reused. | 3–5 | ActivityWatch component is adopted under approved licence and security review. | Desktop Lead | https://github.com/ActivityWatch/activitywatch
BBD-003 | Accessibility tree and OCR fallback | Extract structured visible state across applications. | Screenpipe; OS accessibility APIs; OCR libraries | Build wrappers; license SDK; use open libraries | Build OS-native adapters; benchmark OCR libraries | Medium | Policy-aware collection, secure-field handling and provenance are differentiators; OCR itself is commodity. | Models/libraries require licence, model-origin and data-flow review. | 3–5 | Native accessibility coverage is inadequate for target applications. | Desktop/AI Leads | https://github.com/screenpipe/screenpipe
BBD-004 | Screen capture and changed-region deduplication | Capture meaningful visual evidence efficiently. | Screenpipe; Windows Graphics Capture; ScreenCaptureKit | Native build; commercial SDK; screenpipe licence | Build native capture; benchmark Screenpipe performance | Medium | Evidence policy, state graph and secure exclusions are proprietary; OS capture primitives are standard. | Commercial licence needed for Screenpipe use; platform permissions and privacy indicators mandatory. | 3–5 | Benchmark shows unacceptable endpoint overhead or missing platform features. | Desktop Architect | https://developer.apple.com/documentation/screencapturekit
BBD-005 | GUI workflow record/replay | Turn successful workflows into reusable procedural skills. | OpenAdapt / OpenAdapt Flow; Power Automate | Integrate; adapt concepts; build later | Defer runtime replay; adopt evidence and governed-teaching concepts | Medium | Nessovo Skill Forge is broader than desktop automation and must support human review. | OpenAdapt desktop is experimental; automation carries safety and permission risks. | 11+ | A validated HumanOS use case needs deterministic GUI replay. | Skill Forge Lead | https://github.com/OpenAdaptAI/openadapt-desktop
BBD-006 | Browser activity adapter | Tab/domain/navigation context and approved page evidence. | Chrome/Edge extension APIs; ActivityWatch web watcher | Build extension; reuse watcher; buy monitoring SDK | Build minimal HumanOS browser extension | Low/Medium | Task-aware policy, allowlists and evidence linking matter more than tab capture itself. | Browser permissions and store-review requirements; avoid broad page-content capture. | 6 | Browser vendors add a suitable enterprise API or HumanOS adopts a browser-management platform. | Integrations Lead | https://developer.chrome.com/docs/extensions/reference/api/tabs
BBD-007 | Shell/terminal instrumentation | Capture commands, process trees, output and automated waits. | Shell integration, PTY libraries, developer tools | Build shell hooks; infer from screen; buy endpoint telemetry | Build shell/PTY adapter SDK | Medium | Direct command/result semantics materially improve provenance and task assurance. | Secret/environment redaction and shell compatibility required. | 6 | OS process telemetry plus CI APIs provide sufficient fidelity. | Integrations Lead | https://opentelemetry.io/docs/specs/semconv/
BBD-008 | AI-agent lifecycle instrumentation | Prompts, tool calls, file changes, permissions and reviews. | Codex hooks, Claude hooks, Claude-Mem | Official hooks; desktop inference; proxy all model traffic | Integrate official hooks first; provide normalising adapter hub | High | Cross-agent provenance, review behaviour and task/capability linkage are core differentiation. | Prompt/tool content is sensitive; hooks vary by provider/version. | 6 | Provider APIs converge on a stable common standard. | AI Integrations Lead | https://developers.openai.com/codex/hooks
BBD-009 | AI session memory | Searchable compressed observations and session continuity. | Claude-Mem | Integrate; adapt architecture; build | Build HumanOS memory service using hook/worker/search pattern | Medium | Memory must be tenant-aware, policy-controlled and linked to HumanOS tasks/capabilities. | Claude-Mem is Apache-2.0 but provider-specific architecture still needs security review. | 6–11 | A mature cross-agent memory service meets HumanOS governance requirements. | AI Platform Lead | https://github.com/thedotmack/claude-mem
BBD-010 | Skill observation methodology | Capture corrections, gaps and reusable methods. | Task Observer | Use methodology; incorporate templates; build | Adapt methodology with attribution and governed Skill Forge | High | Nessovo requires organisational, role and cross-vertical skill governance. | CC BY 4.0 attribution required for adapted published material. | 11 | Internal methodology diverges materially or another framework is standardised. | Skill Forge Lead | https://github.com/rebelytics/one-skill-to-rule-them-all
BBD-011 | Employee monitoring vendor | Commodity screenshots, keystrokes, app/web and idle tracking. | Teramind, Veriato, Hubstaff, Insightful | Buy; integrate; replace | Do not use as product core; benchmark as market baseline only | Low | Buying may accelerate raw monitoring but creates data-control, differentiation, integration and trust problems. | Vendor processing, cross-border data and opaque controls require deep due diligence. | 0–1 | A vendor offers on-prem/local-first APIs, strong exclusions and acceptable commercial terms. | Product/Procurement | https://www.teramind.co/solutions/employee-monitoring/
BBD-012 | Task/process mining engine | Discover workflows and process variants. | UiPath, ABBYY, Soroco, Workfellow | Buy; partner; build targeted episode mining | Build targeted task-assurance analytics; consider enterprise connectors later | High | Nessovo evaluates assigned-task outcome and capability, not only process discovery. | Commercial platforms may become data sources/partners, not foundational dependencies. | 7+ | A customer already standardises on a task-mining platform and requests integration. | Product Strategy | https://docs.uipath.com/
BBD-013 | Skills intelligence platform | Role skill graph, inferred skills and learning recommendations. | Workday/TechWolf, Eightfold, Gloat, Degreed | Buy; integrate HRIS; build capability evidence core | Build HumanOS Capability Graph; integrate HRIS/LMS content later | High | Evidence from observed work and task contracts is central to Nessovo differentiation. | Employment AI and fairness risks; avoid opaque inferred-skill imports. | 8–9 | Enterprise customer mandates an existing skills platform as system of record. | Capability Product Lead | https://www.techwolf.ai/
BBD-014 | Learning content catalogue | Provide courses, lessons and assessments after gaps are identified. | LMS and content vendors | Build all content; buy catalogue; partner | Build orchestration and evidence loop; buy/partner content selectively | Medium | Gap diagnosis and application-to-work evidence are proprietary; generic content is not. | Content licence, localisation and quality must be reviewed. | 9+ | Internal content library is sufficient or a strategic content partnership is selected. | L&D Lead | https://www.degreed.com/
BBD-015 | Task Assurance Engine | Evaluate task alignment, progress, quality and acceptance criteria. | No single direct equivalent found; task mining and developer analytics are partial | Build; compose commercial rules; outsource AI | Build as proprietary HumanOS core | Very High | This is the principal product intelligence layer and must be explainable, domain-extensible and evidence-linked. | Models may be third party, but decision logic, prompts/evals and evidence contracts remain Nessovo-controlled. | 7 | None unless an enterprise-standard assurance platform emerges. | Product/AI Lead | Internal proprietary
BBD-016 | Human/AI/automation provenance graph | Trace cause from human input through agents, tools, processes and artefacts. | OTel GenAI, Codex hooks, GitClear-style attribution | Build; use observability backend; buy code attribution | Build proprietary provenance model using open standards where possible | Very High | Cross-surface causal attribution is a key moat and required for fair credit and idle classification. | Avoid copying sensitive prompt content into telemetry systems. | 6–7 | Industry standards mature enough to represent complete work causality. | Data/AI Architect | https://opentelemetry.io/docs/specs/semconv/registry/attributes/gen-ai/
BBD-017 | Capability Graph and role readiness | Link job requirements, tasks, evidence, autonomy and learning. | SFIA, HR skills platforms | Use external framework; buy skills platform; build | Build core ontology; map external frameworks as references | Very High | Nessovo capability evidence and game-like progression depend on a transparent, extensible core model. | Employment fairness, protected-trait exclusion and human review are mandatory. | 2,8 | A regulatory/industry framework becomes a mandatory system of record. | Capability Product Lead | https://sfia-online.org/
BBD-018 | Growth Coach | Real-time contextual support and adaptive training. | Copilots, LMS assistants, workforce coaching tools | Buy chatbot; build; use model APIs | Build HumanOS coaching orchestration and evaluations on approved model gateway | High | Task evidence, capability gaps and intervention effectiveness create proprietary context. | Avoid over-coaching, manipulation and unreviewed high-impact advice. | 9 | A coaching platform supports HumanOS evidence and governance contracts. | AI/L&D Lead | Internal proprietary
BBD-019 | Skill Forge | Improve prompts, plugins, evaluators and methods through observed feedback. | Claude-Mem, Task Observer, Record & Replay | Integrate; adapt; build | Build governed HumanOS Skill Forge using referenced patterns | Very High | Cross-vertical skill lifecycle, evaluation, approval and rollback are strategic HumanOS capabilities. | Attribution/licence and confidential-data separation required. | 11 | HumanOS adopts a compatible enterprise skill registry/evaluation platform. | AI Platform Lead | https://github.com/rebelytics/one-skill-to-rule-them-all
BBD-020 | Event streaming backbone | Durable, replayable, partitioned evidence and domain event flow. | Apache Kafka / compatible managed services | Operate Kafka; buy managed Kafka; use existing HumanOS event bus | Reuse HumanOS Kafka-compatible bus; managed service depends on deployment | Low | Commodity infrastructure; HumanOS event semantics are the differentiator. | Data residency, encryption and operations model need review. | 4 | Existing HumanOS event bus lacks ordering, replay or scale requirements. | Platform Architect | https://kafka.apache.org/documentation/
BBD-021 | Event envelope and schema governance | Interoperable event metadata, versioning and contracts. | CloudEvents, JSON Schema/Avro/Protobuf, schema registry | Adopt standard; invent proprietary envelope | Adopt CloudEvents-style envelope plus Nessovo domain schemas | Low/Medium | Standard envelope reduces integration cost; semantic model remains proprietary. | Do not place sensitive content in envelope attributes. | 4 | Existing HumanOS event contract already satisfies equivalent requirements. | Data Architect | https://cloudevents.io/
BBD-022 | Policy engine | Capture, access, jurisdiction and skill-deployment decisions. | Open Policy Agent | Use existing HumanOS policy; add OPA; embed rules | Reuse HumanOS policy service; benchmark OPA for declarative decisions | Medium | Policy content is Nessovo-specific; engine is commodity. | Decision logs can themselves be sensitive; central bundle security required. | 0–4 | Existing policy service cannot express or distribute required rules. | Security Architect | https://www.openpolicyagent.org/docs
BBD-023 | Operational and AI observability | Service traces, metrics, logs and model-operation visibility. | OpenTelemetry | Adopt OTel; vendor-specific agents | Adopt OpenTelemetry with strict content policy | Low | Standard operational telemetry enables portability; raw worker evidence remains separate. | GenAI input/output can contain sensitive data and must be opt-in/filterable. | 3+ | Existing HumanOS observability standard is equivalent and fully compatible. | SRE/AI Platform | https://opentelemetry.io/docs/
BBD-024 | Transactional evidence metadata store | Sessions, tasks, events, reviews, capabilities and policy state. | PostgreSQL | PostgreSQL; document DB; distributed DB | Use existing HumanOS PostgreSQL standard | Low | Reliable transactional model and tooling; avoid premature specialised stores. | Tenant isolation, row-level controls and encryption needed. | 4+ | Measured scale or query profile exceeds the platform. | Data Architect | https://www.postgresql.org/
BBD-025 | Evidence object store | Screenshots, redacted content, artefact snapshots and exports. | S3-compatible object storage / MinIO | Managed object storage; self-hosted; database blobs | Reuse HumanOS object storage with per-object policy and retention | Low/Medium | Content-addressing, encryption and policy metadata are Nessovo design value. | Regional residency, malware scanning and legal holds required. | 4+ | HumanOS object service cannot support policy/retention/audit needs. | Platform/Data | https://min.io/
BBD-026 | Graph database | Complex causal and capability graph traversal. | Neo4j, JanusGraph, Amazon Neptune | Adopt now; PostgreSQL relations; graph projection | Defer; model graph logically in PostgreSQL first | Medium | Graph queries may matter later, but early dedicated infrastructure adds complexity before query evidence. | Licence/managed-service lock-in and operational burden. | 7–8 | Benchmarks show repeated multi-hop queries cannot meet requirements in PostgreSQL. | Data Architect | https://neo4j.com/

## Reference Architecture
HumanOS Work Intelligence — Reference Architecture
Stage 1 architecture draft. Logical bounded contexts are broader than initial deployables to avoid premature nano-services. Existing HumanOS foundation services remain authoritative where suitable.
ID | Layer | Component / bounded context | Primary responsibility | Primary runtime | Primary data | Consumes / receives | Publishes / exposes | HumanOS reuse | Initial deployment boundary | Delivery stage | Decision / scale trigger | Source / basis
ARC-001 | Device edge | Native Device Agent Core | Policy-controlled session state, event correlation, local encryption, batching, offline queue, health and update coordination. | Rust shared core | Encrypted SQLite/SQLCipher-style journal + content cache | Signed policy bundles, session commands, adapter events | Signed event batches, health, telemetry gaps | Device identity, policy, secrets, audit | Endpoint binary | 3–6 | Separate from cloud services; no Python always-on core. | OpenAdapt/Screenpipe patterns + Nessovo security requirements
ARC-002 | Device edge | Windows Native Bridge | Foreground window, process, UI Automation, capture permissions, input provenance and secure-control detection. | Rust FFI + C#/C++ as required | In-memory / local journal | Windows APIs | Normalised device events | Device policy | Endpoint module | 3–6 | Native bridge only; shared semantics remain in Rust core. | Microsoft UI Automation / ETW / Win32
ARC-003 | Device edge | macOS Native Bridge | ScreenCaptureKit, accessibility, application/window events, event monitoring and secure-input awareness. | Swift/Objective-C + Rust FFI | In-memory / local journal | macOS APIs and permissions | Normalised device events | Device policy | Endpoint module | 3–6 | Requires signed/notarised build and explicit TCC permissions. | Apple ScreenCaptureKit / Accessibility
ARC-004 | Device edge | Linux Adapter | Future platform support under Wayland/X11 capability constraints. | Rust + portal/compositor adapters | Local journal | Wayland portals / X11 | Capability-scoped events | Device policy | Deferred endpoint module | Later | Defer from initial pilot; do not claim parity. | Wayland input/screen security model
ARC-005 | Device edge | Browser Extension | Active tab/domain/navigation, approved page metadata, browser task bookmarks and native messaging. | TypeScript extension | Browser local state | Browser extension APIs | Browser events to native agent | Policy/exclusion service | Browser package | 6 | Domain/title by default; URL path/content only allowlisted. | Chrome/Edge extension APIs
ARC-006 | Device edge | Adapter SDK | Common lifecycle contract for IDE, shell, AI agent, simulator and application adapters. | Rust/TypeScript/Java/Python SDKs | Local config | Tool-specific hooks | Normalised adapter events | Schema registry / model gateway | Shared SDK packages | 6 | Versioned, least-privilege adapters. | Codex hooks / Claude-Mem hook architecture
ARC-007 | Device edge | Local Policy Evaluator and Cache | Validate signed capture policy, exclusions, hours, task scope, expiry and fail-safe behaviour. | Rust; optional embedded policy engine | Signed policy cache | Policy bundles | Allow/deny/redact decisions | HumanOS policy service | Endpoint module | 3 | Fail closed for sensitive capture when policy is invalid or expired. | OPA pattern / Nessovo policy model
ARC-008 | Device edge | Local Redaction and Secret Guard | Detect secure controls, secrets and excluded apps/domains before durable storage/upload. | Rust + local models/rules | Temporary buffers only | Raw candidate evidence | Redacted evidence and suppression events | DLP/secrets policies | Endpoint module | 3–5 | Pilot blocking control; raw rejected content is not retained. | ICO minimisation / Screenpipe PII pattern
ARC-009 | Device edge | Local Evidence Journal | Append-only sequence, object hashes, offline durability, retention and safe upload resume. | Rust | Encrypted SQLite + content-addressed cache | Normalised/redacted events | Batched signed envelopes | Device/session identity | Endpoint module | 3–5 | Per-session keys and bounded storage budget. | Claude-Mem SQLite/WAL pattern + Nessovo requirements
ARC-010 | Control plane | Device Control & Policy Gateway | Device registration, certificates, policy distribution, session commands, agent health, revocation and rollout. | Java 21/25 + Spring Boot | PostgreSQL | Device registration/heartbeat | Policy bundles, session commands, device status API | IAM, policy, secrets, audit, notification | Deployable 1 | 3–4 | Initial Java deployable; separate if device fleet scale justifies. | Spring Boot / mTLS / OPA
ARC-011 | Control plane | Telemetry Ingestion & Schema | Authenticate signed batches, validate contracts, deduplicate, order by device/session, enforce quotas and publish events. | Java + Spring Boot + Spring Kafka | Kafka-compatible bus + PostgreSQL metadata | Agent event batches | Normalised event topics, reject/diagnostic events | IAM, tenant, audit, schema registry | Deployable 2 | 4 | High-throughput boundary with idempotent ingest. | Apache Kafka / CloudEvents / schema registry
ARC-012 | Evidence | Evidence & Timeline | Persist activity events, visual-state references, artefacts, provenance edges, retention state and replay timeline. | Java + Spring Boot | PostgreSQL + object storage | Normalised events, task/agent/file events | Evidence API, timeline API, evidence.linked events | Object service, audit, policy | Deployable 3 | 4–7 | Start with relational graph model; split visual storage only if scale/security requires. | PostgreSQL/object storage/event-sourcing patterns
ARC-013 | Evidence | Visual Evidence Subdomain | Changed-region metadata, OCR/accessibility extracts, thumbnails, object policy and redaction lineage. | Java library/module initially | Object storage + PostgreSQL | Visual-state events and objects | Visual evidence references | Object service, DLP, audit | Inside Deployable 3 initially | 4–5 | Future split trigger: independent scale, retention or security domain. | Screenpipe event-driven capture pattern
ARC-014 | Intelligence | Task Assurance Orchestrator | Compile task contracts, coordinate deterministic checks and AI evaluators, maintain criterion state and assessment workflow. | Java + Spring Boot | PostgreSQL | Tasks, evidence, test/build results, review events | Task assessments, blocker and criterion events | Task/project, workflow, policy, audit | Deployable 4A | 2,7 | Java owns durable state and review workflow. | HumanOS task/workflow foundation
ARC-015 | Intelligence | Task/Activity AI Evaluators | Episode segmentation, task alignment, screen/text interpretation, quality reasoning and confidence calibration. | Python + FastAPI/workers | Model/eval store + vector index | Evidence references and approved content | Evaluator findings with evidence links and model/skill version | Model gateway, policy, audit | Deployable 4B | 7 | Python is stateless/worker-oriented; no employment decision authority. | NIST AI RMF / multimodal models
ARC-016 | Capability & learning | Capability Domain Service | Role contracts, capability definitions, claims, evidence state, role readiness and review. | Java + Spring Boot | PostgreSQL | Task assessments, baseline assessments, training outcomes | Capability evidence/state events and APIs | IAM, organisation, HR/role, workflow, audit | Deployable 5A | 2,8 | Transparent evidence model; domain-neutral core. | SFIA-style mapping + Nessovo ontology
ARC-017 | Capability & learning | Capability Scoring and Gap Analysis | Evidence weighting, confidence, recency, consistency, contradiction and gap classification. | Python services/libraries | Evaluation store | Qualified capability evidence | Scoring recommendations and explanations | Model gateway, policy, audit | Deployable 5B or worker pool | 8 | Java service accepts/rejects scoring recommendation under rules. | Bayesian/uncertainty-aware design recommendation
ARC-018 | Capability & learning | Growth Coach & Learning | Intervention selection, learning plans, micro-lessons, practice, mentor escalation and effectiveness tracking. | Java orchestration + Python AI | PostgreSQL + content/vector stores | Task/capability gaps and employee requests | Coaching/learning events and APIs | Workflow, notification, model gateway, HR/L&D | Inside Deployable 5 initially | 9 | Split when learning marketplace/content scale justifies. | HumanOS workflow + L&D integrations
ARC-019 | AI integration | AI Adapter Hub | Normalise Codex, Claude Code, IDE copilots, agent sessions, prompts, tools and permission events. | Python + Java edge/API | PostgreSQL metadata | Provider hooks/adapters | Normalised agent events | Model gateway, schema, policy | Deployable 6A | 6 | Provider-specific adapters behind common contract. | Codex hooks / Claude-Mem
ARC-020 | AI integration | Model and Evaluation Gateway | Model routing, content policy, secret scanning, prompt/skill versions, evaluation, cost and trace metadata. | Python + Java gateway | PostgreSQL + cache/eval store | Approved AI requests | Responses, audit, evaluation results | Existing HumanOS model gateway | Extend existing platform service | 6–11 | Do not duplicate if HumanOS already meets requirements. | OpenTelemetry GenAI / HumanOS foundation
ARC-021 | Governance | Governance & Human Review | Employee access, corrections, disputes, manager evidence requests, human review and consequential-decision safeguards. | Java + Spring Boot | PostgreSQL + immutable audit | Disputes, review requests, evidence-access requests | Review decisions, corrections, access grants | Workflow, IAM, audit, notification, policy | Deployable 7 | 0,7–10 | Mandatory before pilot assessment use. | ICO worker monitoring/human review
ARC-022 | Governance | Evidence Access Policy | Role/purpose/task/time/region decisions for raw evidence and reports. | HumanOS policy service; evaluate OPA | Policy repository + decision logs | Policy queries | Allow/deny/redact decisions | IAM, organisation, DPO policy | Existing policy service / sidecar | 0–4 | OPA only if it adds value beyond current HumanOS policy service. | OPA
ARC-023 | Reporting | Reporting & Analytics | Employee timeline, task assurance, manager exceptions, capability views, pilot KPIs and executive reporting. | Java APIs + BI/analytics | PostgreSQL read models + warehouse later | Task/capability/review events | Reports, exports and analytics APIs | IAM, audit, notification | Deployable 8 | 10 | Raw evidence is drill-down, not default dashboard content. | ActivTrak/process intelligence patterns
ARC-024 | Organisational learning | Skill Forge | Skill observations, proposals, evaluation suites, approvals, canaries, promotion and rollback. | Java lifecycle + Python generation/evals | PostgreSQL + Git/artifact/eval stores | Feedback, corrections, successful patterns | Skill versions and deployment events | Workflow, model gateway, audit, policy | Inside AI platform initially; later deployable | 11 | Separate only when lifecycle scale/ownership justifies. | Claude-Mem / Task Observer / Record & Replay
ARC-025 | Shared HumanOS | Identity and Access | Person, device, service identity, roles, authentication and authorisation context. | Existing HumanOS Java service | Existing IAM store | Identity requests | Tokens/claims/identity events | Authoritative existing service | Reuse | All | No duplicate identity store. | HumanOS foundation
ARC-026 | Shared HumanOS | Organisation and Role | Tenants, teams, reporting lines, employment/role assignments and organisational scope. | Existing HumanOS Java service | Existing store | Organisation changes | Organisation/role events | Authoritative existing service | Reuse | 0,2+ | Capability service references role versions; it does not own employment identity. | HumanOS foundation
ARC-027 | Shared HumanOS | Projects and Tasks | Assigned tasks, plans, due dates, task state and project context. | Existing HumanOS Java service | Existing store | Task commands/integrations | Task events/APIs | Authoritative existing service | Reuse | 2+ | Task Assurance compiles contracts but task service remains task authority. | HumanOS foundation
ARC-028 | Shared HumanOS | Workflow Runtime | Review, dispute, coaching, approval, escalation and skill-lifecycle workflows. | Existing HumanOS service | Existing workflow state | Domain events | Workflow commands/events | Authoritative existing service | Reuse | 0+ | Evaluate another orchestrator only after documented gaps. | HumanOS foundation
ARC-029 | Shared HumanOS | Audit and Compliance | Immutable access, decision, policy, model, review and skill-change audit. | Existing HumanOS Java service | Append-only audit store | Audit events | Audit queries/reports | Authoritative existing service | Reuse/extend | 0+ | Content access logs are themselves sensitive. | HumanOS foundation
ARC-030 | Shared HumanOS | Secrets and Key Management | Service/device credentials, encryption keys, rotation and revocation. | Existing HumanOS secrets service + OS secure stores | KMS/HSM/secure stores | Key requests | Key material references/rotation events | Authoritative existing service | Reuse | 3+ | Device evidence keys must not be centrally exposed without need. | Security architecture
ARC-031 | Shared HumanOS | Object/File Service | Evidence object storage, classification, regional routing, retention and access tokens. | Existing HumanOS service | S3-compatible object storage | Object writes/reads | Object references/events | Authoritative existing service | Reuse/extend | 4+ | Require per-object policy, malware scan, retention and legal hold. | HumanOS foundation
ARC-032 | Data platform | Kafka-Compatible Event Bus | Durable, partitioned, replayable event flow across ingestion and domain services. | Kafka / managed compatible service | Kafka topics | Producers | Consumer streams | Existing HumanOS event infrastructure | Shared platform | 4+ | Reuse existing bus; capacity-test evidence workload. | Apache Kafka
ARC-033 | Data platform | Schema Registry and Contract Governance | Version event schemas, compatibility rules, generated clients and lineage. | Existing registry or Apicurio/Confluent equivalent | Schema registry | Schema changes | Validated contracts | HumanOS platform | Shared platform | 1,4+ | CloudEvents-style envelope plus domain schemas. | CloudEvents / schema registry
ARC-034 | Data platform | PostgreSQL | Transactional source of truth for sessions, evidence metadata, tasks, capability, review and policy state. | PostgreSQL | Relational data | Domain writes | Queries/CDC/events | Existing platform standard | Shared clusters with tenant isolation | 4+ | Partition by tenant/time only after measured need. | PostgreSQL
ARC-035 | Data platform | Object Storage | Screenshots, redacted content, artefact snapshots, exports and evaluation datasets. | S3-compatible | Encrypted objects | Evidence objects | Signed references/events | Existing object service | Shared regional storage | 4+ | Content-addressed, deduplicated and retention-aware. | S3/MinIO
ARC-036 | Data platform | Vector/Search Capability | Semantic search over approved observations, skills and evidence summaries. | pgvector first; OpenSearch later if needed | Embeddings/index | Approved text summaries | Search results | Model gateway / data platform | Library/extension initially | 7–11 | Do not embed unrestricted raw employee content. | pgvector / search patterns
ARC-037 | Data platform | Graph Projection | Causal/provenance and capability traversal. | PostgreSQL relations/materialised views initially | Relational edges | Evidence/provenance events | Graph queries | Evidence/Capability services | Inside domain services | 7–8 | Dedicated graph database deferred until query benchmarks justify. | Architecture recommendation
ARC-038 | Data platform | Analytics Warehouse | Longer-term aggregate product, pilot, quality and training analysis. | Warehouse/lakehouse compatible with HumanOS | De-identified/aggregated data | Domain events/read models | BI datasets | Existing analytics platform | Later shared platform | 10+ | No raw keystrokes/screenshots in general analytics warehouse. | Data minimisation principle
ARC-039 | Cross-cutting | OpenTelemetry | Operational traces, metrics and logs for services and AI operations. | Java/Python/native SDKs + collector | Telemetry backend | Service/model telemetry | Traces/metrics/logs | Existing HumanOS observability | Shared platform | 3+ | Raw worker evidence and model content excluded by default. | OpenTelemetry
ARC-040 | Cross-cutting | API Gateway and Service Security | External/internal API routing, rate limits, mTLS, auth and policy enforcement. | Existing HumanOS gateway | Config/policy | API calls | Routed/authorised requests | Existing platform service | Reuse | 3+ | Device upload path may have dedicated edge gateway. | HumanOS foundation
ARC-041 | Cross-cutting | Deployment and tenancy | Regional clusters, tenant isolation, data residency, feature flags, canary and rollback. | Kubernetes/cloud platform | Platform metadata | Deployments/config | Runtime services | Existing HumanOS platform | Shared platform | All | Pilot uses isolated tenant/environment and restricted feature flags. | Security/governance requirement
ARC-042 | Cross-cutting | Service boundary rule | Create a separate deployable only for clear security, scale, availability, ownership or transactional boundaries. | Architecture governance | N/A | Architecture changes | ADR decisions | Architecture Board | Rule | All | Initial plan uses approximately eight Work Intelligence deployables plus shared HumanOS services. | Microservices design principle

## Architecture Decisions
Architecture Decision Register
Stage 1 ADR drafts. 'Accepted in principle' means the workbook recommends the decision; Architecture Board approval is still required.
ADR | Decision title | Status | Context / problem | Recommended decision | Alternatives considered | Positive consequences | Risks / trade-offs | Validation / evidence needed | Owner / review trigger | Source / basis
ADR-001 | Product boundary | Accepted in principle | Raw monitoring is commoditised and creates a crowded, high-resistance market position. | Build HumanOS Work Intelligence as task assurance, capability development and human–AI work intelligence; treat monitoring as controlled evidence infrastructure. | Employee-monitoring product; task-mining-only product; developer analytics only. | Clearer differentiation, broader HumanOS fit, direct employee benefit. | More complex product and evaluation problem. | Leadership positioning review and worker consultation. | Product Owner / revisit if market evidence changes | Market Landscape / Gap Matrix
ADR-002 | Stage 0 and Stage 1 structure | Accepted in principle | Governance and architecture research are tightly coupled but require different authorities. | Run as one Foundation & Validation workstream with separate Stage 0 governance gate and Stage 1 architecture gate. | Merge into one gate; run sequentially with no overlap. | Faster integrated planning without losing independent approvals. | Programme may confuse document completion with approval. | Gate register and named decision authorities. | Programme Lead | Master Prompt / Stage 0-1 Gates
ADR-003 | Initial vertical | Accepted in principle | Universal work intelligence is too broad for a first implementation. | Pilot AI-assisted software development on company-managed Windows and macOS devices. | All knowledge workers; customer support; finance operations. | Objective artefacts, tests and Git provide high-quality evidence. | May overfit ontology and UX to developers. | Stage 2 domain-neutral extension tests. | Product/CTO / revisit after pilot | Product Charter v1
ADR-004 | HumanOS integration | Accepted in principle | HumanOS already contains foundation microservices. | Implement Work Intelligence as HumanOS bounded contexts that reuse identity, organisation, tasks, workflow, policy, audit, notification, secrets, object, model and event services. | Standalone platform; duplicate services. | Consistency, lower delivery cost, shared governance. | Existing services may have functional gaps or coupling. | Stage 1 service capability assessment. | Enterprise Architect | Reference Architecture
ADR-005 | Runtime responsibility split | Accepted in principle | Cloud domain durability, AI iteration and OS capture have different runtime needs. | Java/Spring for durable domain and workflow services; Python for AI/evaluation workers; Rust/native bridges for endpoint capture. | All Java; all Python; Electron-only agent. | Technology fit, strong platform alignment and endpoint performance. | Multi-language contracts, skills and operations. | Contract tests, shared schemas, staffing plan. | CTO / review at Stage 3 and 4 | User stack + architecture research
ADR-006 | Java/Spring baseline | Proposed | HumanOS current version is not confirmed; newer supported releases exist. | Do not force platform migration. Retain current supported HumanOS baseline unless measured benefits justify migration; benchmark Java 25 LTS with Spring Boot 4.1 and compatible Spring Cloud for greenfield-compatible services. | Mandate Java 25/Boot 4.1 immediately; remain permanently on Java 21/Boot 3.x. | Avoids unnecessary migration while evaluating current LTS capabilities. | Mixed baselines or delayed adoption. | Inventory current HumanOS stack; compatibility/performance/security spike. | Java Platform Lead / when platform baseline known | OpenJDK 25 / Spring Boot 4.1 / Spring Cloud 2025.1.2
ADR-007 | Device-agent architecture | Accepted in principle | Endpoint capture requires low latency, native OS APIs, local policy and secure offline operation. | Use a Rust shared core with Swift and Windows-native bridges; Tauri/native UI may expose visible controls. | Java desktop agent; Python agent; Electron capture process. | Performance, memory safety, cross-platform core and native access. | Rust/native expertise and FFI complexity. | Stage 3 proof of installation, policy, journal, update and performance. | Desktop Architect | OpenAdapt/Screenpipe architecture patterns
ADR-008 | Edge-first minimisation | Accepted in principle | Raw screen, text and input evidence is highly sensitive and expensive. | Apply policy, secure-field exclusion, redaction, deduplication and event correlation locally before upload. | Upload raw stream; cloud-only redaction. | Lower privacy/security risk, bandwidth and storage. | Endpoint models/rules may miss content and are harder to update. | False-negative/false-positive redaction evaluation and signed policy updates. | CISO/DPO / blocking pilot control | ICO minimisation and DPIA requirements
ADR-009 | Event backbone | Accepted in principle | Evidence flow requires durable replay, partitioning, multiple consumers and asynchronous processing. | Reuse HumanOS Kafka-compatible event infrastructure with signed, idempotent, schema-versioned batches. | Synchronous REST only; database polling; new message platform. | Decoupling, replay and scalable consumers. | Operational complexity and schema discipline. | Capacity test and topic/partition design. | Platform/Data Architect | Apache Kafka
ADR-010 | Event envelope | Accepted in principle | Cross-language and cross-service events need consistent metadata. | Use a CloudEvents-style envelope with Nessovo domain schemas and separate references for large/sensitive content. | Proprietary envelope; raw provider payloads. | Interoperability, tooling and clearer contracts. | Additional mapping and version governance. | Schema registry prototype and compatibility policy. | Data Architect | CloudEvents
ADR-011 | Operational observability vs worker evidence | Accepted in principle | OpenTelemetry supports service/AI traces but prompt/content fields may contain sensitive information. | Use OpenTelemetry for operational traces, metrics and logs. Keep worker evidence in the Evidence domain and exclude raw prompts/text/screens by default from traces. | Put all evidence in traces; use vendor-specific observability only. | Clear governance boundary and portability. | Correlation requires identifiers across systems. | Trace/evidence correlation design and content-policy tests. | SRE/AI Platform/DPO | OpenTelemetry semantic conventions and GenAI warnings
ADR-012 | Microservice granularity | Accepted in principle | A long list of logical services can create unnecessary distributed complexity. | Start with approximately eight Work Intelligence deployables plus endpoint agent and shared HumanOS services; split subdomains only on security, scale, availability, ownership or transactional evidence. | One monolith; one deployable per entity/capability. | Balanced autonomy and operational simplicity. | Initial services may become large. | Track change coupling, load, ownership and security boundaries. | Architecture Board / quarterly review | Reference Architecture
ADR-013 | Initial data stores | Accepted in principle | Evidence, tasks and capabilities need transactions, objects, search and graph-like queries. | Use PostgreSQL for transactional metadata, object storage for evidence, pgvector/search selectively; defer a dedicated graph database until benchmarks justify it. | Adopt graph/vector/search databases immediately; single document database. | Lower operational burden and faster MVP. | Complex graph queries may later require migration. | Stage 7/8 query benchmarks and data-volume tests. | Data Architect | Build Buy Decisions
ADR-014 | Policy engine | Proposed | Capture and evidence access require dynamic, auditable, jurisdiction-aware decisions. | Reuse existing HumanOS policy service. Evaluate OPA for declarative local/service decisions where it materially improves expressiveness and distribution. | Embed rules in every service; mandate OPA everywhere. | Avoid duplicate policy systems while preserving policy-as-code option. | Inconsistent decisions if integration is weak. | Capability assessment of existing policy service and OPA spike. | Security Architect / Stage 3 | OPA
ADR-015 | Workflow orchestration | Accepted in principle | Review, disputes, coaching and skill lifecycle need long-running workflows. | Reuse HumanOS Workflow Runtime; introduce Temporal or another orchestrator only after documented capability gaps. | Adopt Temporal immediately; custom state machines per service. | Platform consistency and lower complexity. | Existing runtime may lack developer ergonomics or durability features. | Stage 2/3 workflow capability matrix. | Platform Architect | HumanOS foundation / Temporal as reference only
ADR-016 | AI decision architecture | Accepted in principle | Task/capability conclusions combine facts, deterministic checks and uncertain model interpretation. | Java domain services own state and policy; Python evaluators return versioned findings with evidence, confidence and missing-data flags; humans decide consequential outcomes. | AI service directly writes final employment states; deterministic rules only. | Auditability, rapid model iteration and governance. | Additional orchestration and calibration burden. | Evaluation suites, calibration, human-review workflow. | AI Architect/DPO | NIST AI RMF / ICO human review
ADR-017 | Build/buy capture core | Accepted in principle | Relevant source-available and experimental projects exist but none meets the entire security/governance/product model. | Build the proprietary endpoint core; benchmark and learn from Screenpipe, ActivityWatch and OpenAdapt; reuse code only after legal/security approval. | Commercial monitoring vendor; direct Screenpipe commercial licence; fork OpenAdapt. | Control over privacy, provenance, platform fit and product IP. | Higher engineering cost and OS complexity. | Stage 3/5 benchmarks and licence review. | CTO/Desktop/Legal | GitHub OSS Scan
ADR-018 | Capability system | Accepted in principle | Skills platforms infer capabilities but Nessovo needs task-evidence traceability and employee progression. | Build a transparent HumanOS Capability Graph; map external frameworks and integrate HRIS/LMS systems rather than outsourcing the core evidence model. | Buy skills platform as system of record; manager-only ratings. | Core differentiation, explainability and cross-vertical fit. | Employment fairness and ontology complexity. | Stage 2 ontology evaluation and pilot fairness review. | Capability Product Lead | Skills intelligence market research
ADR-019 | Employee data access | Accepted in principle | Evidence used to assess work can be wrong or incomplete. | Employees receive access to material evidence and assessments, can correct task/context and request meaningful human review. | Manager-only visibility; limited report access. | Trust, fairness, data quality and governance. | Workflow and operational effort; potential disputes. | Pilot UX and dispute SLA tests. | DPO/HR/Product | ICO monitoring guidance
ADR-020 | Pilot employment use | Accepted in principle | Early models and capture controls will not be sufficiently validated for high-impact decisions. | No adverse employment action based solely or primarily on pilot system output; use pilot for product evaluation, coaching and evidence-quality learning. | Normal performance-management use during pilot. | Reduces harm and enables honest feedback. | Limits immediate management value. | Executive/HR policy and participant terms. | Executive Sponsor/HR | Pilot Definition
ADR-021 | Skill self-improvement | Accepted in principle | The system should improve prompts, adapters and evaluators from feedback without uncontrolled self-modification. | Use observation → proposal → offline evaluation → expert/security review → canary → promote/rollback lifecycle. | Automatic live edits; manual improvement only. | Compounding organisational intelligence with governance. | Evaluation maintenance and slower promotion. | Stage 11 Skill Forge implementation and regression metrics. | AI Platform Lead | Claude-Mem / Task Observer patterns
ADR-022 | Audio capture | Accepted | Audio adds significant privacy, policy and storage risk and is not required for the first technical pilot. | Exclude microphone/system audio from v1 pilot. | Capture meetings and calls; optional user-triggered audio. | Reduces risk and scope. | Some work context remains unobserved. | New purpose, DPIA and product decision before introduction. | DPO/Product | Purpose Policy Matrix

## Stage 0-1 Gates
Stage 0 and Stage 1 Approval Gates
Formal readiness checklist. A drafted workbook item is not the same as a Nessovo approval. Mandatory items marked 'Not Started' or 'Blocked' prevent an unconditional go decision.
Gate item | Gate | Category | Mandatory | Requirement | Required evidence | Accountable authority | Status | Readiness weight | Decision / condition | Blocking condition | Notes | Gate readiness summary
G0-01 | Stage 0 | Purpose | Yes | Product purpose and strategic positioning approved. | Signed/recorded Product Charter v1 decision. | Executive Sponsor | Draft Ready | 80% |  | No agreed purpose or value proposition. |  | Metric | Value
G0-02 | Stage 0 | Ownership | Yes | Executive sponsor, product owner and programme lead named. | RACI with named individuals. | CEO | Owner Input | 30% |  | No accountable owner. |  | Stage 0 readiness | 57.22%
G0-03 | Stage 0 | Scope | Yes | Initial vertical, participant cohort, devices, hours, tasks and exclusions defined. | Approved Pilot Definition. | Product Owner / HR | Draft Ready | 80% |  | Scope permits personal devices, covert or out-of-hours capture. |  | Stage 1 readiness | 56.67%
G0-04 | Stage 0 | Prohibited uses | Yes | No covert general monitoring, activity-volume scoring, emotion/personality inference or solely automated employment decisions. | Approved charter and policy controls. | DPO / Legal / HR | Draft Ready | 80% |  | Any prohibited use remains permitted by design or policy. |  | Mandatory blockers | 5
G0-05 | Stage 0 | Purpose limitation | Yes | Every proposed data category has a specific purpose and prohibited uses. | Purpose Policy Matrix reviewed by DPO. | DPO | Draft Ready | 80% |  | Collection exists 'just in case'. |  | Formal decisions recorded | 0
G0-06 | Stage 0 | Necessity | Yes | Less-intrusive alternatives are assessed and residual necessity documented. | Alternatives assessment in purpose matrix/DPIA. | DPO / Product | Draft Ready | 80% |  | Intrusive collection selected without alternatives analysis.
G0-07 | Stage 0 | DPIA | Yes | High-risk monitoring DPIA is completed and independent DPO advice recorded. | Completed DPIA and DPO advice. | DPO | Not Started | 0% |  | Unmitigated high risk or missing DPO advice.
G0-08 | Stage 0 | UK legal | Yes | UK lawful basis, employment, interception and automated-decision conditions confirmed. | UK legal memorandum. | UK Legal Counsel | Owner Input | 30% |  | Legal basis or policy route unresolved.
G0-09 | Stage 0 | Pakistan legal | Yes for Lahore pilot | Pakistan employment/privacy/interception and transfer requirements confirmed. | Pakistan legal memorandum. | Pakistan Legal Counsel | Owner Input | 30% |  | Local-law requirements unresolved for Lahore participants.
G0-10 | Stage 0 | Worker voice | Yes | Affected workers or representatives consulted during planning. | Consultation record and Nessovo response. | HR / DPO | Not Started | 0% |  | No consultation and no documented justification.
G0-11 | Stage 0 | Transparency | Yes | Worker notice and monitoring policy explain what, why, when, access, retention and rights. | Approved notice and policy. | HR / Legal / DPO | Draft Ready | 80% |  | Workers cannot understand when or why monitoring occurs.
G0-12 | Stage 0 | Employee rights | Yes | Employee evidence access, correction, explanation, dispute and review workflow defined. | Workflow specification and service SLA. | DPO / HR / Product | Draft Ready | 80% |  | No operational challenge route.
G0-13 | Stage 0 | Human review | Yes | Reviewers are qualified, independent enough, authorised and able to reject AI output. | Human-review standard. | HR / Legal | Draft Ready | 80% |  | AI recommendation is effectively rubber-stamped.
G0-14 | Stage 0 | Security/privacy controls | Yes | Secure-field blocking, exclusions, local redaction, encryption, audit and emergency disable are mandatory. | Control specification and validation plan. | CISO / DPO | Draft Ready | 80% |  | Passwords/secrets could be retained or uploaded.
G0-15 | Stage 0 | Threats | Yes | Foundation threat model has owners and blocking controls. | Threat register reviewed by CISO/DPO. | CISO | In Review | 60% |  | Critical untreated threat.
G0-16 | Stage 0 | Pilot protection | Yes | Pilot output cannot independently create adverse employment consequences. | Participant terms and HR policy. | Executive Sponsor / HR | Draft Ready | 80% |  | Pilot used as unvalidated disciplinary mechanism.
G0-17 | Stage 0 | Stop criteria | Yes | Pilot hold/stop conditions and authority are measurable and operational. | Pilot Definition and incident path. | Executive Sponsor / CISO / DPO | Draft Ready | 80% |  | No rapid stop mechanism.
G0-18 | Stage 0 | Decision | Yes | Cross-functional review completed and Stage 0 decision recorded. | Meeting minutes, conditions and decision. | Executive Sponsor | Not Started | 0% |  | No formal gate decision.
G1-01 | Stage 1 | Market evidence | Yes | Commercial category research and strategic gap analysis are complete and source-backed. | Market Landscape and Gap Matrix. | Product Owner | Met | 100% |  | Differentiation rests on unsupported novelty claims.
G1-02 | Stage 1 | OSS evidence | Yes | Relevant GitHub projects have maturity, licence, architecture and reuse notes. | GitHub OSS Scan. | Architecture / Legal | Met | 100% |  | Third-party code used without due diligence.
G1-03 | Stage 1 | Licence | Yes | Formal commercial/OSS licence review completed for intended dependencies. | Approved licence register. | Legal / Procurement | Owner Input | 30% |  | Commercial rights unclear.
G1-04 | Stage 1 | Build/buy | Yes | Component decisions separate proprietary core from commodity infrastructure. | Build Buy Decisions approved. | CTO / Product | Draft Ready | 80% |  | Core differentiation outsourced or commodity components rebuilt without reason.
G1-05 | Stage 1 | HumanOS fit | Yes | Reference architecture reuses existing HumanOS foundations and avoids duplicate systems. | Reference architecture and capability assessment. | Enterprise Architect | Draft Ready | 80% |  | Unjustified duplicate identity/task/workflow/policy/audit service.
G1-06 | Stage 1 | Service boundaries | Yes | Initial deployables have security, scale, ownership or transactional justification. | Accepted ADR-012 and service map. | Architecture Board | In Review | 60% |  | Premature nano-services create unmanageable distributed complexity.
G1-07 | Stage 1 | Technology baseline | Yes | Java/Spring, Python and native responsibilities are approved; current HumanOS baseline is inventoried. | Runtime ADRs and platform inventory. | CTO / Platform Lead | Owner Input | 30% |  | Unsupported runtime or forced migration without evidence.
G1-08 | Stage 1 | Event and data architecture | Yes | Event, schema, store, search, retention and sensitive-content boundaries are defined. | Accepted event/data ADRs. | Data / Platform Architect | In Review | 60% |  | Raw content copied into observability or analytics without purpose.
G1-09 | Stage 1 | Security architecture | Yes | Endpoint, ingestion, evidence, access, model and supply-chain threats have controls and spikes. | Security architecture review. | CISO | In Review | 60% |  | Critical architecture threat untreated.
G1-10 | Stage 1 | AI governance | Yes | Evaluator architecture separates evidence, inference, confidence, model/skill version and human decision. | AI architecture and evaluation plan. | AI Architect / DPO | Draft Ready | 80% |  | AI writes final high-impact state without review.
G1-11 | Stage 1 | Technical spikes | Yes | Highest-risk Stage 2–3 hypotheses have measurable spike plans and decision thresholds. | Spike backlog and next-stage prompts. | Programme / Architecture | Draft Ready | 80% |  | Implementation begins without validating endpoint/privacy feasibility.
G1-12 | Stage 1 | Cost model | Yes | Pilot and scale usage assumptions and low/base/high cost model are approved. | Cost model and assumptions. | CFO / FinOps | Not Started | 0% |  | No cost or storage/inference sensitivity.
G1-13 | Stage 1 | Resourcing | Yes | Stage 2–3 team, devices, environments, budget and review capacity are committed. | Resource plan. | CEO / CTO / CFO | Owner Input | 30% |  | No assigned delivery capacity.
G1-14 | Stage 1 | Architecture decisions | Yes | Architecture Board accepts, rejects or conditions the ADR set. | ADR review record. | Architecture Board | In Review | 60% |  | Core architecture remains ambiguous.
G1-15 | Stage 1 | Decision | Yes | Stage 1 review completed and decision to enter Stages 2 and 3 recorded. | Meeting minutes, conditions and decision. | CTO / Executive Sponsor | Not Started | 0% |  | No formal gate decision.

## Assumptions Questions
Assumptions and Open Questions
Items that require Nessovo owners, platform inventories, legal advice or pilot evidence. Current assumptions are temporary and must not be treated as confirmed facts.
ID | Category | Question / decision needed | Current working assumption | Impact if assumption is wrong | Accountable owner | Required by stage | Status | Resolution / evidence | Source / note
AQ-001 | HumanOS platform | What Java and Spring Boot/Spring Cloud versions are currently supported in HumanOS? | Java 21+ and a supported Spring Boot 3.x/4.x baseline. | May change runtime ADR, libraries, migration effort and support policy. | Java Platform Lead | 1 | Open |  | Inventory current repositories and BOMs.
AQ-002 | HumanOS platform | Which foundation microservices are production-ready versus partially built? | Identity, organisation, task/project, workflow, policy, audit, notification, secrets, object and model gateway largely exist. | May require additional Stage 1 architecture and delivery work. | Enterprise Architect | 1 | Open |  | User states base services are mostly built.
AQ-003 | HumanOS platform | Does HumanOS already operate Kafka or a compatible event bus with schema governance? | A reusable event infrastructure exists or can be extended. | Could change ingestion architecture, cost and Stage 4 scope. | Platform/Data Architect | 1 | Open |  | Platform capability assessment required.
AQ-004 | HumanOS platform | Can the current policy service express device capture, jurisdiction, task, time, exclusion and evidence-access decisions? | It handles core authorisation but may need OPA-style policy capabilities. | May create a new policy component or larger extension. | Security Architect | 1/3 | Open |  | Run policy capability matrix.
AQ-005 | HumanOS platform | Can the Workflow Runtime support long-running human review, disputes, coaching and skill approval? | It is the default orchestrator. | Could require Temporal or another workflow engine. | Workflow Platform Lead | 2/3 | Open |  | Do not add another orchestrator without gap evidence.
AQ-006 | HumanOS platform | Does the audit service support immutable, high-volume evidence-access and AI-decision records? | It can be extended. | A separate append-only audit stream may be needed. | Audit/Security Lead | 1/4 | Open |  | Security and scale assessment.
AQ-007 | HumanOS platform | Does the object service support regional routing, per-object policy, legal hold, secure deletion and short retention? | Basic object storage exists; policy features may need extension. | Could create evidence-specific storage boundary. | Platform/Data Lead | 1/4 | Open
AQ-008 | Deployment | What cloud, Kubernetes, database and observability platforms does HumanOS standardise on? | Existing platform standards should be reused. | Affects reference architecture, cost and CI/CD. | CTO/SRE | 1 | Open
AQ-009 | Deployment | Which regions and data-residency zones are required for UK and Pakistan operations? | UK and Pakistan-related data will require explicit regional/transfer design. | Changes storage, support and cross-border controls. | DPO/Security | 0/1 | Open |  | Legal review required.
AQ-010 | Pilot | How many pilot employees and teams will participate? | 10–30 employees across one or two technical teams. | Changes event volume, support load, consultation and evaluation power. | Product/HR | 0/1 | Open |  | Used only as provisional planning range.
AQ-011 | Pilot | Which managed device mix is available? | Windows 11 and recent macOS; Linux excluded initially. | Changes Stage 3 engineering and test matrix. | IT/Desktop Lead | 1/3 | Open
AQ-012 | Pilot | Is MDM/endpoint management available for certificate, policy and signed-agent deployment? | An enterprise endpoint-management path exists. | Manual installation could undermine trust, updates and rollback. | IT/Security | 1/3 | Open
AQ-013 | Pilot | Which development tools must the first pilot support? | Chrome/Edge, common terminals, Git, GitHub, Codex CLI, Claude Code, VS Code/JetBrains, Xcode/Android Studio as applicable. | Adapter backlog and coverage could expand materially. | Engineering Leads | 1/3 | Open |  | Confirm actual Nessovo tool inventory.
AQ-014 | Pilot | Will participants be office-based, remote or hybrid? | Mixed/hybrid work is possible. | Homeworking increases private-life capture risk and policy complexity. | HR/DPO | 0 | Open |  | ICO notes higher privacy risk at home.
AQ-015 | Pilot | Can work devices be used for limited personal activity? | Some personal use may occur and must be excluded/paused. | Changes exclusions, notice, private mode and evidence policy. | HR/Legal/IT | 0 | Open
AQ-016 | Pilot | Will BYOD ever be allowed? | No BYOD in the initial pilot. | BYOD would materially increase legal, privacy and technical risk. | Executive Sponsor/DPO | 0 | Assumed |  | Reassess only with a new DPIA.
AQ-017 | Employment | Which employee contracts, handbooks and policies currently address monitoring and personal use? | Existing documents require amendment. | Could delay pilot and change consultation process. | HR/Legal | 0 | Open
AQ-018 | Employment | Are trade unions, works councils or other worker representatives relevant? | Employee representatives should be involved even if no formal body exists. | Could impose consultation/collective requirements. | HR/Legal | 0 | Open
AQ-019 | Employment | Will the internal pilot use volunteers, selected participants or a whole team? | A controlled cohort with appropriate consultation and protection. | Voluntariness, bias and team dynamics differ. | HR/DPO/Product | 0 | Open
AQ-020 | Employment | Can any pilot output enter formal performance-management records? | No adverse employment action based solely or primarily on pilot output. | Directly affects participant safety and legal risk. | HR/Legal/Executive Sponsor | 0 | Draft decision |  | Pilot Definition and ADR-020.
AQ-021 | Privacy | What raw and derived retention periods will legal/DPO approve? | Raw visual/text evidence 7–30 days; metadata 30–90 days; derived task/capability records longer when justified. | Changes storage cost, evidence availability and rights workflows. | DPO/Data Governance | 0/1 | Open |  | Purpose Policy Matrix proposals only.
AQ-022 | Privacy | Which applications, domains, monitors and secure controls must be excluded? | Passwords, authentication, personal email, banking, health, private messaging and configured apps/domains are excluded. | Incomplete exclusions could block pilot. | DPO/Security/HR | 0/3 | Open
AQ-023 | Privacy | Is clipboard content ever necessary? | No; only paste metadata by default. | Content capture would add major DLP/privacy risk. | DPO/CISO/Product | 0 | Draft decision |  | Purpose Policy Matrix.
AQ-024 | Privacy | Is audio required for the initial vertical? | No audio in v1. | Including audio would materially expand scope and DPIA. | DPO/Product | 0 | Draft decision |  | ADR-022.
AQ-025 | AI | Which model providers and hosting modes are approved for employee evidence? | Only approved Model Gateway routes; sensitive evidence may require regional/private models. | Changes latency, cost, data processing and model availability. | AI Platform/DPO/Security | 1/7 | Open
AQ-026 | AI | Do model/provider contracts allow retention-free processing and no training on submitted data? | This must be contractually controlled. | Could prohibit use of certain providers for raw evidence. | Legal/Procurement/AI | 1/7 | Open
AQ-027 | AI | What confidence thresholds are acceptable for task alignment, idle and capability findings? | Thresholds must be calibrated through pilot data and vary by consequence. | Too low creates false allegations; too high reduces usefulness. | AI Evaluation Lead/DPO | 7/8 | Open
AQ-028 | AI | Who will label and review pilot evaluation datasets? | Domain experts plus employee-context review. | Poor labels will invalidate model metrics. | AI Evaluation Lead/Engineering Leads | 1/7 | Open
AQ-029 | Capability | Which role families and job descriptions are first in scope? | Software engineer, QA engineer, DevOps/platform engineer and technical lead. | Changes Stage 2 ontology examples and assessments. | HR/Product/CTO | 2 | Open
AQ-030 | Capability | Will Nessovo adopt an external framework such as SFIA as a reference? | Use external frameworks as mappings, not the sole ontology. | May affect language, licence and customer interoperability. | HR/L&D/Product | 2 | Open
AQ-031 | Capability | Which HRIS/LMS systems must HumanOS integrate with? | HumanOS may remain the capability system while integrating employment and content systems. | Changes APIs and source-of-truth decisions. | HRIS/L&D Architect | 2/9 | Open
AQ-032 | Manager access | Which managers may see raw evidence, and under what approval? | Managers receive summaries; raw access requires task scope, reason code and audit. | Access model could undermine trust or operations. | DPO/HR/Security | 0/10 | Open
AQ-033 | Commercial | Will the product be internal-only initially or prepared for external multi-tenant customers? | Internal pilot first, architecture remains multi-tenant. | Changes compliance, product packaging, support and isolation. | CEO/Product | 1 | Open
AQ-034 | Commercial | Will enterprise on-premises or sovereign deployment be required? | Possible later; not an initial pilot requirement. | Could change dependencies and SaaS architecture. | Product/CTO | 1 | Open
AQ-035 | Economics | What endpoint CPU, memory, storage, bandwidth and AI cost limits are acceptable? | Target <7% typical CPU, <750 MB memory and bounded configurable local storage. | Determines capture design and model placement. | CTO/SRE/Product | 1/3 | Open |  | Targets require validation.
AQ-036 | Economics | What raw screenshot/event rate and retention assumptions should drive cost modelling? | Event-driven capture; approximately 20–100 meaningful visual states/hour as a scenario range. | Cost estimates are unreliable without workload assumptions. | FinOps/Data/Desktop | 1 | Open |  | Must be measured in technical spikes.
AQ-037 | Security | Which security certifications or customer assurance frameworks are strategic? | ISO 27001/SOC 2-style controls may be future requirements. | Could change SDLC, evidence and vendor choices. | CISO/CEO | 1 | Open
AQ-038 | Security | What is the acceptable response when the endpoint agent detects tampering or policy expiry? | Stop sensitive capture, preserve audit, notify user/admin and recover securely. | Too permissive risks unlawful collection; too strict may lose work evidence. | CISO/Desktop/Product | 3 | Open
AQ-039 | Data | When should a dedicated graph database be introduced? | Only after Stage 7/8 query benchmarks show PostgreSQL is insufficient. | Premature adoption adds cost; delayed adoption may limit graph analytics. | Data Architect | 7/8 | Assumed |  | ADR-013.
AQ-040 | Governance | Who can approve a HumanOS skill/evaluator update that affects employee assessments? | Named domain expert plus AI governance/security review; high-impact changes require DPO/HR review. | Weak approval could cause harmful regression. | AI Platform/HR/DPO | 11 | Open

## Foundation Threats
Foundation Threat Model and Control Register
Initial Stage 0–1 threat register. Scores use 1–5 likelihood and impact. Residual scores are provisional until controls are implemented and tested.
ID | Threat category | Threat scenario | Affected asset / people | Inherent likelihood | Inherent impact | Inherent score | Required controls | Residual likelihood | Residual impact | Residual score | Accountable owner | Validation / test | Gate status
THR-001 | Privacy | Passwords, authentication codes or secrets are captured in keys, text, terminal output or screenshots. | Employees, source code, credentials, customers | 4 | 5 | 20 | Secure-field blocking; local secret detection/redaction; excluded apps/domains; zero-retention suppression; DLP tests; emergency disable. | 2 | 5 | 10 | CISO/Desktop Lead | Adversarial secure-field and secret-corpus test; zero known-secret retention. | Blocking
THR-002 | Privacy | Homeworking capture includes household, family or personal content. | Employees and household members | 4 | 5 | 20 | Company-managed devices; defined hours; visible status; private pause; monitor/app exclusions; minimal visual capture; worker notice. | 2 | 4 | 8 | DPO/HR | Remote-work scenario tests and employee consultation. | Blocking
THR-003 | Governance | Capture policy is too broad, vague or used 'just in case'. | All employees | 4 | 5 | 20 | Purpose Policy Matrix; policy versioning; task/session scope; DPO approval; periodic review; policy-as-code. | 1 | 5 | 5 | DPO/Product | Policy review against approved purposes and less-intrusive alternatives. | Blocking
THR-004 | Governance | Managers misuse raw evidence for curiosity, live surveillance or unsupported allegations. | Employees and organisational trust | 4 | 5 | 20 | Summary-first reports; purpose codes; role/task/time limits; approval for raw access; immutable audit; misuse sanctions. | 2 | 4 | 8 | HR/DPO/Security | Access-control penetration test and audit review exercise. | Blocking
THR-005 | AI fairness | Legitimate thinking, reading, meetings or automated waits are classified as idle. | Employees, performance records | 4 | 4 | 16 | Contextual process/meeting signals; employee correction; confidence; alternative explanation; no automatic adverse action. | 2 | 3 | 6 | AI Evaluation Lead | Pilot false-idle rate by work pattern and accommodation group. | Pilot metric
THR-006 | AI fairness | Supportive research or another assigned task is classified as off-task. | Employees and task reports | 4 | 4 | 16 | Multiple task context; supporting-task class; employee correction; threshold calibration; human review. | 2 | 3 | 6 | AI/Product | Labelled task-alignment evaluation with confusion matrix. | Pilot metric
THR-007 | AI reliability | Model generates a confident narrative unsupported by evidence. | Employees, managers, decisions | 4 | 5 | 20 | Evidence citations; fact/inference separation; calibrated confidence; missing-evidence flags; deterministic validators; human review. | 2 | 4 | 8 | AI Architect/DPO | Hallucination/evidence-grounding evaluation suite. | Blocking
THR-008 | Capability fairness | One failed task permanently lowers a capability or implies deception. | Employees, careers | 4 | 5 | 20 | Multiple evidence requirement; context and task difficulty; contradiction; recency; human review; neutral claim-discrepancy language. | 1 | 4 | 4 | Capability Lead/HR | Synthetic and pilot cases; reviewer agreement; appeal outcomes. | Blocking
THR-009 | Capability fairness | Accessibility accommodations or different valid working styles are treated as poor performance. | Disabled/neurodivergent employees | 3 | 5 | 15 | Outcome-based criteria; reasonable-adjustment context; worker input; fairness tests; no activity-volume scoring. | 1 | 5 | 5 | HR/DPO/Product | Accessibility review and subgroup error analysis. | Blocking
THR-010 | Employment | Unvalidated pilot outputs influence discipline, dismissal, pay, promotion or probation. | Pilot participants | 3 | 5 | 15 | Participant terms; HR policy; system label 'pilot/non-consequential'; human review; audit; executive stop authority. | 1 | 5 | 5 | Executive Sponsor/HR | Decision-audit sampling and manager training test. | Blocking
THR-011 | Insider threat | Privileged administrator or reviewer accesses sensitive evidence outside purpose. | Employees, customers, IP | 3 | 5 | 15 | Separation of duties; just-in-time access; purpose codes; dual approval for sensitive classes; immutable audit; anomaly alerts. | 1 | 4 | 4 | CISO | Privilege abuse simulation and audit review. | Blocking
THR-012 | Cloud security | Central evidence store is breached or misconfigured. | Screens, text, code, employee data | 3 | 5 | 15 | Regional tenant isolation; encryption; per-tenant keys; object policy; short retention; DLP; monitoring; incident response. | 1 | 5 | 5 | CISO/Platform | Threat modelling, pen test, configuration audit and recovery test. | Blocking
THR-013 | Endpoint security | Agent is compromised, tampered with or used for privilege escalation. | Device, credentials, evidence integrity | 3 | 5 | 15 | Least privilege; signed binaries; sandboxing; code review; device attestation; tamper evidence; rapid revoke/update. | 1 | 4 | 4 | Desktop Security Lead | Endpoint penetration test and tamper laboratory. | Stage 3 gate
THR-014 | Evidence integrity | Employee, malware or service fabricates, deletes or reorders events. | Task/provenance reports | 3 | 4 | 12 | Signed batches; device/session sequence; hash chains; idempotency; gap events; authoritative artefact corroboration. | 1 | 3 | 3 | Data/Security | Replay, deletion, duplicate and spoofed-event tests. | Stage 4 gate
THR-015 | Supply chain | Malicious or compromised update reaches endpoint agents. | All managed devices | 3 | 5 | 15 | Code signing; reproducible/provenance builds; staged rollout; update signatures; rollback; SBOM; dependency scanning. | 1 | 5 | 5 | CISO/Desktop/DevSecOps | Update attack simulation and signing-key incident exercise. | Stage 3 gate
THR-016 | Performance | Capture causes keyboard/mouse latency, high CPU, battery drain or application instability. | Employees and delivery | 4 | 4 | 16 | Event-driven capture; budgets; native profiling; backpressure; adaptive throttling; kill switch; benchmark matrix. | 2 | 3 | 6 | Desktop/SRE | Long-duration endpoint performance and application compatibility tests. | Pilot metric
THR-017 | Reliability | Offline queue is lost, corrupted or grows without bound. | Evidence completeness and device storage | 3 | 4 | 12 | Encrypted WAL; checksums; bounded quota; priority retention; safe compaction; health alert; resumable upload. | 1 | 3 | 3 | Desktop/Data | 72-hour offline, crash-recovery and disk-pressure tests. | Stage 3 gate
THR-018 | Distributed systems | Duplicate, late or out-of-order events create incorrect timelines and assessments. | Evidence and AI findings | 4 | 4 | 16 | Idempotency keys; device sequence; event-time/watermarks; late correction; deterministic replay. | 2 | 2 | 4 | Data Architect | Chaos and replay tests with duplicates/out-of-order batches. | Stage 4 gate
THR-019 | Legal/data transfer | Employee evidence crosses borders or processors without valid assessment/contracts. | Employees and Nessovo compliance | 3 | 5 | 15 | Data-flow map; regional storage/routing; transfer mechanism; processor due diligence; model-provider controls. | 1 | 5 | 5 | DPO/Legal | Data-flow audit and contract register. | Blocking
THR-020 | Third-party AI | Model provider retains, trains on or exposes employee evidence. | Employees, IP, customers | 3 | 5 | 15 | Approved Model Gateway; no-training/retention terms; regional/private models; minimised prompts; content filters; vendor review. | 1 | 5 | 5 | AI Platform/Legal/CISO | Provider contract review and technical egress test. | Blocking
THR-021 | Prompt injection | Text visible on screen, webpages or repositories manipulates AI evaluators or coaching agents. | Assessment integrity, data access | 4 | 4 | 16 | Treat observed content as data; tool/capability restrictions; prompt isolation; allowlisted retrieval; output validation; adversarial tests. | 2 | 3 | 6 | AI Security Lead | Indirect prompt-injection benchmark using captured-screen scenarios. | Stage 7 gate
THR-022 | Self-improvement | Skill Forge automatically deploys a harmful or biased prompt/evaluator update. | Employees and system quality | 3 | 5 | 15 | Proposal-only observation; offline eval; domain/security/DPO review; canary; version pinning; rollback; impact classification. | 1 | 4 | 4 | AI Platform/Governance | Regression, red-team and rollback tests. | Stage 11 gate
THR-023 | Confidentiality | Employee/project details leak into reusable or open-source skills. | IP, customers, employees | 3 | 5 | 15 | Internal/open-source classification; generalisation; redaction; source linkage; approval; publication scanning. | 1 | 4 | 4 | Skill Forge/Legal | Confidentiality test corpus and publication review. | Stage 11 gate
THR-024 | Licensing | Source-available or OSS code is used beyond licence terms. | Nessovo IP and commercial product | 3 | 4 | 12 | Licence register; legal approval; SBOM; provenance; clean-room implementation when needed. | 1 | 3 | 3 | Legal/Architecture | Dependency and source-provenance audit. | Stage 1 gate
THR-025 | Architecture | Premature nano-services increase failure modes, latency and operational burden. | Delivery speed and reliability | 4 | 3 | 12 | Bounded contexts; approximately eight initial deployables; split triggers; architecture board review. | 2 | 2 | 4 | Enterprise Architect | Deployment dependency and change-coupling review. | Stage 1 gate
THR-026 | Economics | Screenshot, event, embedding and model costs scale beyond the product value. | Business viability | 4 | 4 | 16 | Event-driven capture; dedup; tiered retention; edge summaries; sampling; low/base/high model; budgets/quotas. | 2 | 3 | 6 | FinOps/Product/Data | Pilot cost per employee/task and scale sensitivity. | Stage 1/pilot
THR-027 | Trust | Employees perceive the product as punitive surveillance and withhold honest feedback or leave. | Adoption, culture and data quality | 4 | 5 | 20 | Employee value; consultation; transparent evidence; correction; coaching; no pilot adverse action; manager training. | 2 | 4 | 8 | HR/Product/Executive Sponsor | Pre/post trust survey, interviews and dispute analysis. | Pilot metric
THR-028 | Gaming | Employees optimise visible activity or route work through unmonitored devices/tools. | Evidence validity and culture | 3 | 4 | 12 | Outcome-based assessment; clear policy; legitimate workflows; employee benefit; evidence triangulation; no activity scores. | 2 | 3 | 6 | Product/HR | Pilot anomaly review without punitive assumptions. | Pilot metric
THR-029 | Management quality | System flags employee gaps when the real cause is poor requirements, access, workload or management. | Employees and organisational decisions | 4 | 5 | 20 | Task contract quality; blocker classes; environment and manager context; team-level process analysis; employee response. | 2 | 3 | 6 | Product/HR/Operations | Root-cause review and manager/employee agreement metrics. | Stage 7/8
THR-030 | Scope | Platform tries to support every HumanOS vertical before proving the core. | Programme cost and quality | 4 | 4 | 16 | Initial software-development vertical; domain-neutral ontology; explicit expansion gates. | 1 | 3 | 3 | CEO/Product/CTO | Pilot outcome and next-vertical business case. | Programme gate

## Pilot Definition
Internal Pilot Definition — Foundation Draft
Controlled Nessovo pilot for AI-assisted software-development work. All targets are initial hypotheses until owners, legal reviewers and employee representatives approve them.
ID | Pilot element | Draft definition / rule | Rationale | Accountable owner | Evidence / metric | Status | Approval / note
PIL-001 | Pilot purpose | Validate technical capture, task/provenance accuracy, employee benefit, manager usefulness, privacy controls and endpoint feasibility. | The pilot is a product and governance evaluation, not a disciplinary programme. | Executive Sponsor/Product | Approved pilot protocol. | Draft Complete
PIL-002 | Pilot vertical | AI-assisted software engineering, QA and platform/DevOps work. | Git, tests, builds, reviews and agent hooks provide comparatively objective evidence. | CTO/Product | Selected teams and role list. | Draft Complete
PIL-003 | Participant range | Planning assumption: 10–30 employees across one or two technical teams. | Enough variety for workflow and trust learning while keeping support manageable. | HR/Product | Final participant roster. | Owner Input | Confirm through consultation and capacity.
PIL-004 | Participant selection | Use an appropriately consulted and protected cohort; document voluntariness/selection logic and bias. | Selection method affects trust and evaluation validity. | HR/DPO | Selection and consultation record. | Draft Complete
PIL-005 | Locations | UK and Lahore participation only after separate jurisdiction-specific legal approval; otherwise restrict pilot to the approved location. | Legal and cross-border conditions differ. | Legal/DPO | UK and Pakistan legal memoranda. | Owner Input | Blocking for each jurisdiction.
PIL-006 | Devices | Company-managed Windows 11 and recent macOS devices; no BYOD; Linux deferred. | Limits permissions, privacy and support uncertainty. | IT/Desktop | Device inventory and MDM readiness. | Draft Complete
PIL-007 | Duration | Technical dry run 2–4 weeks followed by controlled work pilot 6–8 weeks. | Separates system defects from employee-facing evaluation. | Programme Lead | Approved schedule. | Draft Complete | Duration may change after Stage 3–7.
PIL-008 | Working hours | Capture only within approved work-session/task-session states and policy hours. | Prevents continuous out-of-hours monitoring. | HR/DPO/Product | Session-state audit and worker notice. | Draft Complete
PIL-009 | Visible status | Persistent tray/menu status, current task, sensors active, last upload and pause/stop controls. | Employees must understand when and what is active. | Desktop/Product | UX test and screenshots. | Draft Complete | Stage 3 blocking control.
PIL-010 | Task scope | Only approved project tasks with a Task Execution Contract are used for task assurance. | Prevents arbitrary evaluation without agreed criteria. | Product/Engineering Leads | Task contract register. | Draft Complete | Stage 2 dependency.
PIL-011 | Excluded work | Personal activity, HR/medical/legal conversations, authentication, banking, personal email/messages and specifically excluded applications/domains. | High sensitivity and not necessary for pilot purpose. | DPO/HR/Security | Exclusion policy and tests. | Draft Complete
PIL-012 | Audio | No microphone or system-audio recording. | Not required for initial vertical and materially increases intrusion. | DPO/Product | Agent capability disabled and audited. | Draft Complete
PIL-013 | Visual capture | Event-driven screenshots/changed regions only; no default continuous manager live view. | Supports evidence while reducing volume and intrusion. | Desktop/DPO | Capture-rate, dedup and access tests. | Draft Complete
PIL-014 | Keyboard capture | Metadata and approved-control text deltas; raw key values narrowly scoped and never from secure/excluded controls. | Exact work reconstruction requires provenance but unrestricted keylogging is unacceptable. | DPO/Desktop/Security | Secure-field and text-reconciliation evaluation. | Draft Complete | DPIA approval required.
PIL-015 | Manager experience | Exception-led task outcome, quality, blocker and support report; raw evidence drill-down requires purpose and scope. | Managers need usable information, not surveillance firehose. | Product/HR | Manager usability study and access logs. | Draft Complete
PIL-016 | Employee experience | Own timeline, task alignment, evidence, coaching, capability observations, corrections and dispute access. | Employee agency improves fairness and data quality. | Product/HR/DPO | Employee UX study and correction workflow. | Draft Complete
PIL-017 | Human review | Material negative findings and all capability changes require qualified human review during pilot. | Models and policies are not yet validated for high-impact use. | HR/Domain Reviewers | Review record and override rate. | Draft Complete
PIL-018 | Employment boundary | No adverse employment action may be based solely or primarily on pilot output. | Participant protection and honest feedback are required. | Executive Sponsor/HR/Legal | Signed participant/policy terms. | Draft Complete | Formal approval required.
PIL-019 | Coaching | Begin with observe mode; add opt-in or controlled nudge/assist interventions after baseline evaluation. | Avoids contaminating baseline and over-interrupting employees. | AI/Product/L&D | Intervention experiment design. | Draft Complete
PIL-020 | Capability use | Pilot capability results are developmental and provisional; no permanent role-fit label from a single task. | Capability model needs repeated evidence and fairness review. | HR/Capability Lead | Capability review protocol. | Draft Complete | Stage 8 dependency.
PIL-021 | Raw retention | Planning proposal: 7–30 days for screenshots/text, 30–90 days for event metadata, subject to DPIA/legal decision. | Supports debugging and disputes while limiting exposure. | DPO/Data Governance | Approved retention schedule. | Owner Input | Not final.
PIL-022 | Derived retention | Task assessments, corrections and validated capability evidence retained only for approved project/employment purpose and review periods. | Derived records may have longer value but higher employment impact. | DPO/HR | Retention and deletion policy. | Owner Input
PIL-023 | Model routing | Only approved HumanOS Model Gateway routes; sensitive raw evidence uses permitted regional/private configurations. | Prevents uncontrolled third-party processing. | AI Platform/CISO/DPO | Provider contract and egress tests. | Owner Input
PIL-024 | Support model | Named employee support contact, technical support, DPO/privacy contact and rapid agent-disable path. | Employees need immediate resolution and safe escalation. | Programme/HR/Security | Support rota and SLA. | Owner Input
PIL-025 | Stop authority | Executive sponsor, DPO and CISO each have authority to pause affected capture or the pilot for blocking risk. | Safety action must not depend on commercial pressure. | Executive Sponsor/DPO/CISO | Incident and stop procedure. | Draft Complete
PIL-026 | Stop trigger | Any retained password/secret, unauthorised capture, critical breach, unsupported legal basis, persistent high false-classification, unacceptable endpoint impact or inability to operate employee rights. | Defines non-negotiable pilot boundaries. | Executive Sponsor/DPO/CISO | Automated/manual trigger records. | Draft Complete
PIL-027 | Capture completeness target | ≥99% foreground application changes on supported systems. | Measures technical reliability rather than employee productivity. | Desktop/QA | Controlled benchmark result. | Target Draft | Validate in Stage 5.
PIL-028 | Click/state correlation target | ≥98% clicks linked to correct before/after visual state for supported apps. | Core evidence-graph quality target. | Desktop/QA | Labelled interaction benchmark. | Target Draft
PIL-029 | Text reconstruction target | ≥95% resulting-text reconstruction in supported non-secure controls; zero known secure-field content retained. | Supports provenance while making secret leakage a zero-tolerance metric. | Desktop/Security/QA | Adversarial corpus and supported-app benchmark. | Target Draft
PIL-030 | Agent provenance target | ≥95% actor attribution accuracy for instrumented Codex/Claude/tool events. | Fairly separates human direction, AI generation and automation. | AI Integrations/QA | Labelled session benchmark. | Target Draft
PIL-031 | Task alignment target | ≥90% precision for defined pilot task categories, with confidence and correction. | Prevents overclaiming general task understanding. | AI Evaluation/Product | Holdout task-alignment dataset. | Target Draft
PIL-032 | False-idle target | <5% false-idle rate in labelled pilot periods, including builds, reviews, reading and meetings. | Idle errors are high-impact and damage trust. | AI Evaluation/DPO | Context-labelled sample. | Target Draft
PIL-033 | Endpoint budget | Typical CPU <7%, memory <750 MB, no perceptible keyboard/mouse latency; storage and battery budgets configurable. | Agent cannot harm work it is intended to support. | Desktop/SRE | Long-duration performance tests. | Target Draft
PIL-034 | Employee usefulness | ≥70% of participants rate at least one coaching/report feature as useful, with qualitative explanation. | Direct employee benefit is a core product condition. | Product/HR/L&D | Survey/interviews. | Target Draft | Threshold subject to research design.
PIL-035 | Manager usefulness | ≥80% of pilot managers find task/blocker reports more actionable than current status reporting. | Tests operational value. | Product/Operations | Structured manager evaluation. | Target Draft
PIL-036 | Trust and fairness | No material decline in trust attributable to opaque capture; disputes resolved with evidence and measured overturn rate. | Trust is both a governance and product-quality metric. | HR/DPO/Product | Pre/post survey, interviews, dispute data. | Target Draft | Use independent/facilitated feedback.
PIL-037 | Data incident target | Zero unauthorised raw-evidence access and zero known secret/secure-field retention. | Any occurrence is a major control failure. | CISO/DPO | Audit and incident log. | Target Draft | Blocking.
PIL-038 | Decision after pilot | Proceed, modify, restrict or stop based on technical metrics, employee/manager evidence, legal review, cost and strategic value. | Prevents rollout based on enthusiasm alone. | Executive Sponsor/CTO/DPO/CISO | Pilot report and gate decision. | Draft Complete